EPHRAIM MOGALE LOCAL MUNICIPALITY

INTEGRATED DEVELOPMENT PLAN

2011/16  FINAL

Table of Contents

- ABBREVIATIONS………………………………………………………………………………………………………………………………….5

- FORWORD OF MAYOR…………………………………………………………………………………………………………………………..7

CHAPTER 1

3.	EXECUTIVE SUMMARY MUNICIPAL MANAGER…………………………………………………………………………………………….9

3.1	Location of the Municipality…………………………………………………………………………………………………………….9

3.2	Key challenges and opportunities …………………………………………………………………………………………………….9

3.3	Priority Strategies……………………………………………………………………………………………………………………….15

3.4	Legal Framework ……………………………………………………………………………………………………………………….19

3.5	Roll of Local Government………………………………………………………………………………………………………………19

3.6	Objectives of Local Government………………………………………………………………………………………………………26

3.7	Integrated Development Planning Perspective. …………………………………………………………………………………….26

3.8	IDP/Budget Review Structures and Processes…………………………………………………………………………………….. 26

3.8.1	IDP/Budget Review Structures……………………………………………………………………………………………..27

3.8.2	IDP/Budget Review Processes…………………………………………………………………………………………….28

3.9	Assessment of previous IDP………………………………………………………………………………………………………….31

CHAPTER 2 - ANALYSIS PHASE

4.	SITUATIONAL ANALYSIS………………………………………………………………………………………………………………………..32

4.1 	Demographic Analysis………………………………………………………………………………………………………………….32

4.2 	Population………………………………………………………………………………………………………………………………..32

4.3	 Focus Groups…………………………………………………………………………………………………………………………...36

4.4	 Income and Employment (development Challenges)………………………………………………………………………………37

5.	INFRASTRUCTURE AND BASIC SERVICES ANALYSIS……………………………………………………………………………………39

5.1 	Water……………………………………………………………………………………………………………………………………...39

5.2 	Sanitation…………………………………………………………………………………………………………………………………42

5.3	 Electricity…………………………………………………………………………………………………………………………………43

5.4 	Housing……………………………………………………………………………………………………………………………………45

5.5	Waste and Refuse Removal……………………………………………………………………………………………………………46

5.6 	Roads and Storm water Drainage……………………………………………………………………………………………………..48

5.7 	Transport………………………………………………………………………………………………………………………………….50

5.8 	Free Basic Services……………………………………………………………………………………………………………………..51

6.	ECONOMIC, SPATIAL AND ENVIRONMENTAL ANALYSIS………………………………………………………………………………..53

6.1	 Economic Analysis……………………………………………………………………………………………………………………..53

6.2 	Spatial Analysis………………………………………………………………………………………………………………………….59

6.3 	Climate and Environmental Analysis………………………………………………………………………………………………….62

7.	SOCIAL ANALYSIS……………………………………………………………………………………………………………………………… 64

7.1 	Education………………………………………………………………………………………………………………………………..64

7.2 	Health and Social Development………………………………………………………………………………………………………67

7.3 	HIV/AIDS…………………………………………………………………………………………………………………………………70

7.4 	Safety and Security……………………………………………………………………………………………………………………..71

7.5 	Sports, Arts and Culture………………………………………………………………………………………………………………..72

7.6 	Post Offices……………………………………………………………………………………………………………………………...76

8.	INSTITUTIONAL ANALYSIS…………………………………………………………………………………………………………………….78

8.1 	Council…………………………………………………………………………………………………………………………………...78

8.2 	Staff Component………………………………………………………………………………………………………………………..79

8.3 	Human Resource Policies …………………………………………………………………………………………………………….79

8.4 	Organisational Performance Management System (OPMS) and Performance Management System (PMS)………………79

8.4.1	 OPMS………………………………………………………………………………………………………………………...79

8.4.2	 PMS…………………………………………………………………………………………………………………………..94

8.5	Administrative Structure……………………………………………………………………………………………………………….94

8.6    	Organogram…………………………………………………………………………………………………………………………….95

8.7	Employment equity…………………………………………………………………………………………………………………….122

8.8	Skills development…………………………………………………………………………………………………………………….122

9.	FINANCIAL VIABILITY AND MANAGEMENT………………………………………………………………………………………………..122

9.1 	Grants and Subsidies…………………………………………………………………………………………………………………122

9.2 	Credit and Debt Control………………………………………………………………………………………………………………125

9.3 	Investments…………………………………………………………………………………………………………………………….125

9.4 	Audits……………………………………………………………………………………………………………………………………125

9.5 	Budget and Treasury………………………………………………………………………………………………………………….126

9.6 	Revenue Management………………………………………………………………………………………………………………..126

9.7	 Supply Chain Management………………………………………………………………………………………………………….126

9.8 	Asset Management……………………………………………………………………………………………………………………126

10.	GOOD GOVERNANCE AND PUBLIC PARTICIPATION……………………………………………………………………………………126

10.1	Powers and Functions…………………………………………………………………………………………………………………127

10.2 	Communication…………………………………………………………………………………………………………………………128

10.3 	Ward Committees………………………………………………………………………………………………………………………129

10.4 	Community Development Workers……………………………………………………………………………………………………129

10.5 	Traditional Leadership………………………………………………………………………………………………………………….129

10.6 	Intergovernmental Relations…………………………………………………………………………………………………………...129

10.7	Audit, anti-corruption and risk management…………………………………………………………………………………………129

10.8	Special focus groups……………………………………………………………………………………………………………………130

11.   	Swot Analysis………………………………………………………………………………………………………………………………………130

CHAPTER 3 - STRATEGIES PHASE

12.	DEVELOPMENT STRATEGIES…………………………………………………………………………………………………………………139

12.1	Municipal vision…………………………………………………………………………………………………………………………139

12.2	Municipal mission………………………………………………………………………………………………………………………139

12.3	Core values of the municipality………………………………………………………………………………………………………..139

12.4	Strategies………………………………………………………………………………………………………………………………..140

12.4.1	Municipal turn around strategy……………………………………………………………………………………………..140

12.4.2	Summary of turn around strategy………………………………………………………………………………………….155

12.4.3	Strategies according to key performance areas…………………………………………………………………………158

CHAPTER 4 - PROJECTS PHASE

13.	MUNICIPAL PROJECTS ……………………………………………………………………………………………………………………….166

13.1	Summary of identified projects of community including MIG approved budget……………………………………………….. 166

13.2	Projects for which funds have been obtained………………………………………………………………………………………168

14. 	DISTRICT PROJECTS…………………………………………………………………………………………………………………………..198

15. 	SECTOR DEPARTMENTS PROJECTS………………………………………………………………………………………………………199

16. 	STATE OWNED ENTERPRISES PROJECTS……………………………………………………………………………………………….202

CHAPTER 5 - INTEGRATION PHASE

17.	INTEGRATION…………………………………………………………………………………………………………………………………..203

CHAPTER 6 - ADOPTION

18.	ADOPTION……………………………………………………………………………………………………………………………………… 210

1.	ABBREVIATIONS

CBO – Community Base Organizations

CFO – Chief Financial Officer

CMRA – Centre for Municipal Research & Advice

DPLG – Department Local Government

EU – European Union

EXCO – Executive Committee

EPMLM – Ephraim Mogale Local Municipality

FMG – Finance Management Grant

GAMAP/GRAP -  Generally Accepted Municipal Accounting Practice/Generally Recognized Accounting Practice

GSDM – Greater Sekhukhune District Municipality

HIV/AIDS – Human Immunodeficiency Virus/Acquired Immune Deficiency Syndrome

HOD’S – Head of Departments

IDP – Integrated Development Plan

IT – Information Technology

LGWSETA – Local Government Water Sector Education Training Authority

KPA – Key Performance Area

KPI – Key Performance Indicator

LED – Local Economic Development

LNW – Lephele North Water

LUMS – Land Use Management System

MFMA – Municipal Finance Management Act

MIG – Municipal Infrastructure Grant

MSIG – Municipal Systems Improvement Grant

NGO -  Non Governmental Organizations

NSDP – National Strategic Development Plan

OHS – Occupational Health & Safety

OPMS – Organizational Performance Management System

PGDS – Provincial Growth & Development Strategy

PMS – Performance Management System

PR – Porpotional Representative

PRO – Public Relations Officer

RDP – Reconstruction & Development Program

SABS – South African Bureau of Standards

SCM – Supply Chain Management

SDBIP – Service Delivery Budget Implementation Plan

SDF – Spatial Development Framework

SETA – Sector Education Training Authority

SLA – Service Level Agreement

SWOT – Strength Weakness Opportunity Threats

TLC – Transitional Local Council

TRC – Transitional Regional Council

VIP – Ventilated Improved Pit latrine

WTW – Water Treatment Works

WWTW – Waste Water Treatment Works

2.	FOREWORD OF MAYOR

The municipality had developed its 5 year Integrated Development Plan for 2006-2011 in May 2006 and is now undertaking   			the IDP for 5 year period for the new council for 2011 – 2016 .

The Council at a strategic planning exercise held on 8-9 February 2011 taking in consideration outcome 9 of MFMA circular 				54 of 10 December 2010 amended its vision namely  “VIABLE AND SUSTAINABLE MUNICIPALITY THAT PROVIDES QUALITY 			SERVICES AND ENHANCE ECONOMIC GROWTH”.

There is a remarkable progress that has been seen in this municipal area in trying to address the imbalances of the past, to deliver 			quality services and promote better life for all. In order to ensure delivery the municipality embarked on a turn around strategy which 			progress forms part of this IDP.

It is expected of the municipality to offer residents good infrastructural development such as well built and maintained roads, decent 			houses, enough clean and running water, sanitation, electricity, crime free area, clean environment, adequate health services, 			employment, care for the disabled, the sick and the aged, good governance and many other services.  In all of these fields work has 		been done. The limited budget of the municipality, together with grants from the National and Provincial Governments have gone a 			long way to improve the living conditions of our people.

Projects that were implemented and completed are Leeuwfontein Internal Streets, Rathoke/ Matlerekeng Road,Leeuwfontein taxi 			rank,fencing of two cemeteries and 484 houses.

Projects that are in planning,tender phase are Building of bridge :Manotolwaneng, building bridge: Mathukuthela,

Moganyaka access roads, Keerom /Uitvlugt roads, Marble Hall stormwater, Klopper community hall, Vaal bank internal roads

and  Malebitsa internal streets.

During March 2011 the municipality embarked on community consultation to present the IDP and budget for 2011/16 when all 14 			wards were visited and needs identified for inclusion in the IDP.

I want to thank the members of the Executive Committee, Councilors, Officials, all Stakeholders and the members of the 				community for their unwavering support in working together to ensure better life for all.

Mayor

M Y MMAKOLA

CHAPTER 1

3.	EXECUTIVE  SUMMARY

The name of the municipality was changed to Ephraim Mogale Local Municipality by an amendment of section 12 notice in Provincial Gazette No 1721 by General notice 10 of 2010 on 28 January 2010  with new logo and slogan - RE HLABOLLA SETSHABA which means “We develop our people”

The Ephraim Mogale Local Municipality is composed of former Marble Hall New City council ,Moutse west, Leeuwfontein/Moganyaka, portion of former Hlogotlou/Lepele TRC, portion of former Greater Nebo North TRC, the entire erea of former Middle Lepelle TRC, portion of Naboomspruit/Roedtan Thusang TLC area and part of the former Springbokvlakte TLC

The Municipality was established soon after the elections in December 2000 in terms of section 12 notice no.302 dated 1 October 2000.The municipality was a cross boundary municipality which comprises of 16 villages, Marble Hall town and farming areas in Mpumalanga and 2 Townships and 47 villages in Limpopo.The municipality has been incorporated in Limpopo province in accordance with proclomation no.422 dated 27 December 2005.

The municipality have 32 Councilors and 16 wards and  53316 registered voters.The extent of the municipality is 1911.07km²

3.1	Location of Municipality

The Ephraim Mogale Local municipality is situated within an intense farming area supported by the Loskop Dam irrigation water scheme and is 145km east of  Pretoria,100km  south of  Mogalekwena(Potgietersrus)120km  north of  Steve Tshete(Middelburg),150km  south of Polokwane(Pietersburg) and 250km west of  Mbombela(Nelspruit)

3.2	Key challenges and opportunities

KPA  1 Spatial Rationale

| Department | Issues/ Services Delivery | Challenges | Opportunity |
| --- | --- | --- | --- |
| Technical services | Land Ownership and Land Use Management | Ensure lawful security of tenure | To implement land use management system ounce in place |

KPA 2 Service delivery and infrastructure development

| Department | Issues/ Services Delivery | Challenges | Opportunity |
| --- | --- | --- | --- |
| Technical services | Provision of water & purification services | Ageing infrastructure. Process of transferring staff to GSDM too slow. | District is currently developing bulk services plans in Moutse area. GSDM in the process of replacing the asbestos pipes in town. Plans for transferring of staff already in place.the process will be completed by the 30th June 2010. |
|  | Water tanks | Legal issues on registration of water tanks |  |
|  | Provision of roads & maintenance | Obsolete and shortage of equipments, Insufficient funds for purchasing of new equipments | Additional equipments to be purchased in the next financial year |
|  | Electricity | Shortage of material at stores. Delays in purchasing of material by SCM | SCM division to fast track the process of purchasing stores material |
|  | Provision of free basic electricity to indigents in municipal area. | Transformer numbers. Approval for new doc. Budget. Criteria in policy. Non –collectors | Assistance with transformer numbers. Revise budget. Revise policy. De-configure 6mnths non collection. |
|  | Fleet management | To manage and control the utilization of the municipal vehicle fleet. | Installation of tracking system in 20 vehicles |
| Community Services | Environmental services | Environment plan implementation not being monitored Environmental management is a district function, not clear how to be implemented to fit the district plan. Staff inadequate Devolution of services not yet complete pending district function | DEAT willing to allocate budget and assist |
|  | Traffic services and Law enforcement | Need extra warm bodies and office space | Ongoing training by provincial department |
|  | Sport & creation, arts& culture and heritage sites | Lack of warm bodies and office space | On-going training and assistance by provincial department |
|  | Cleaning services | Non payment by community Old fleet and no fleet manager Lack of operational and warm bodies |  |
|  | Registration Authority | Lack of capacity and warm bodies | Provincial assistance |
|  | Disaster and Emergency services | District manage disaster management. Lack of warm bodies and inadequate budget and office space. Poor monitoring of the service No SLA between GMHM and GSDM | District assistance |
|  | Youth, gender& disability programmes | Lack of warm bodies, office space and budget |  |
|  | Library services | Insufficient of tertiary institution books, budget and staff |  |
|  | Security services | Lack of good security management, plan, poor access control and locking of offices after hours Inadequate control of alarm system and supervision |  |
|  | Parks and recreational facilities | Lack of warm bodies No budget to extend service to other areas of GMHM |  |
|  | Hawkers and business trading licences | No supervision and not designated as trading licence authority | Support of the stakeholders |

KPA 3 Local economic development

| Department | Issues/ Services Delivery | Challenges | Opportunity |
| --- | --- | --- | --- |
| Strategic Planning | Plan manage and manage the implementation of LED | Lack of monitoring of implementation of LED.Insufficient staff | Employment and Funding future growth of LED projects |

KPA 4 Good governance

| Department | Issues/ Services Delivery | Challenges | Opportunity |
| --- | --- | --- | --- |
| Corporate Services | Provision logistic & administration support services | Ineffective local labour forum,lack of council resolution register,late submission of items for agenda,insufficient utilization of drivers,ineffective portfolio committees, |  |
|  | Job Evaluation | Delay by GSDM to finalize District J.E. Committee establishment | Respective Unit of the GSDM commenced with local municipalities coordination work |
|  | Fleet management | Inadequate fleet control & monitoring | Trip authorization for every official vehicle and return of vehicle-keys to Records section after each trip. |

KPA 5 Municipal financial viability

| Department | Issues/ Services Delivery | Challenges | Opportunity |
| --- | --- | --- | --- |
| Finance | Revenue enhancement | Most people in the rural communities are not paying their rates accounts and in some instances community members have been sighted saying that their councilor told them not to pay and this contributes to the non recovery of debts regardless of efforts made by administration | Councilors should embark on awareness campaigns during their meetings with community members and encourage them to pay as part of their community work. |
|  | Updating indigent register | Unavailability of councilors during the registration process due to certain commitments often delays the process | Commitment required from all councilors and a pledge to avail themselves when needed in order to fast tract this process. |

KPA 6 Municipal transformation & Institutional development

| Department | Issues/ Services Delivery | Challenges | Opportunity |
| --- | --- | --- | --- |
| Corporate Services |  |  |  |
|  | Human Resources and Development Administration personnel related issues. Industrial relations | Training plans for individual staff not in place,inadequate personnel,lack of coordination of training(no person responsible for training),inadequate implementation of policies(no monitoring).In service training policy. | Good Governance, Local Economic Development (LED) , Services Delivery |
|  | Manage occupational health & safety matters | No OHS committee,budget not used |  |

|  | Manage & provision of IT service | Monitoring of backup(backup register),remote backup. |  |
| --- | --- | --- | --- |
|  | Manage PMS i.r.o.employees | Lack of individual employee workplan,lack of official responsible for monitoring of PMS-employee | Service provider appointed by GSDM to review framework and to cascade PMS to other staff. LED officer receiving training on PMS. |

3.3	Priority Strategies

KPA 1 Spatial Rationale

| Priority strategy | Objective | Outcome | Target | Period |
| --- | --- | --- | --- | --- |
| Land Ownership and Land Use Management | Ensure lawful security of tenure | % of land security tenure | Better quality of life | 2011-2015 |

KPA2	Service delivery and Infrastructure and services

| Priority strategy | Objective | Outcome | Target | Period |
| --- | --- | --- | --- | --- |
| Water Infrastructure and Services | Adequate quality and quantity of affordable water available to all consumers in the municipal area in terms of the Water Sector Plan | % of households having access to quality water | Better quality of life | 2011-2015 |
| Sanitation | Provide an adequate and appropriate sewer system/systems for the urban part of the municipality as well as appropriate measures for the rural conditions | % of households having access to basic sanitation | Better quality of life | 2011-2015 |
| Priority strategy | Objective | Outcome | Target | Period |
| Electrification of Households | Provide affordable and reliable electricity to urban and rural areas in the municipality | % of households with affordable and reliable electricity | Better quality of life | 2011-2015 |
| Roads and Storm Water | Provide safe and appropriate road and storm water networks in the municipal areas | Improved accessibility and safe roads between areas | Better quality of life | 2011-2015 |
| Waste Management and Refuse Removal | Provide a safe, effective and economical waste management and refuse disposal system | % households satisfaction index | Better quality of life | 2011-2015 |
| Transport | Promote an effective and affordable transport system to cater for the whole of the municipal area | Improved transport accessibility between the areas | Better quality of life | 2011-2015 |
| Housing | Ensure that the housing need of people in the municipal area is met | Number of households with basic housing | Better quality of life | 2011-2015 |
| Cemeteries | Provide safe, appropriate and accessible burial space/cemetery space in the municipal area | Number of complaints from bereaved families | Better quality of life | 2011-2015 |
| Post and Telecommunication | To ensure that a basic communication infrastructure is within reach of all the inhabitants in the municipal area | Improved access to communication by inhabitants in the municipal area | Better quality of life | 2011-2015 |
| Health | Promote the development of a healthy community and an effective healthcare environment | - Number reduction in cases of deadly diseases - Change in community behaviour | < 15 cases a month | 2010/2015 |
| Social Welfare | Ensure improved living standards and promote humane living conditions for every member of society | % of households satisfaction index | Better quality of life | 2011/2015 |
| Education | Promote the provision of effective education to all learners and equip people to lead a meaningful life | Number of learners and scholars with accredited qualifications | Better quality of life | 2011/2015 |
| Safety and Security | Ensure a safe, secure and humane environment for inhabitants of the municipality | % reduction in crime statistics | Better quality of life | 2011/2015 |
| Sports and Recreation | Ensure accessibility to Sport and Recreation facilities for all the inhabitants of the municipal area | Number of inhabitants having access to sports and recreation events at the municipal area facilities | Better quality of life | 2011/2015 |
| Arts and Culture | Social and cultural integration as well as conservation of important cultural and historic sites |  | Better quality of life | 2011/2015 |
| Emergency Services | Ensure fire fighting and ambulance services which are safe, secure, humane, prompt and effective | Improved response time to emergencies in minutes | Better quality of life | 2011/2015 |
| Environmental Management | Ensure that the general environment is protected and promoted in a sustainable and ongoing way | % achievement of environmental targets in the Environmental Assessment Plan | Better quality of life | 2011/2015 |

KPA 3	Local Economic Development

| Priority strategy | Objective | Outcome | Target | Period |
| --- | --- | --- | --- | --- |
| Local Economic Development | Ensure economic growth in all sectors of the economy in order to curb unemployment and related negative issues | % of economic growth or GDP contribution to the province | 3% GDP for the area | 2011/2015 |

KPA 4	Good Governance and Public Participation

| Priority strategy | Objective | Outcome | Target | Period |
| --- | --- | --- | --- | --- |
| Service Delivery Standards (Batho Pele) | Implementation of the Batho Pele Principles | Compliance with customer standards | 100% compliance and customer satisfaction | 2011-2015 |
| Performance Management Systems | Develop appropriate key performance indicators | Number of KPIs used for reporting the IDP | According standards | 2011-2015 |

KPA 5 Financial Viability

| Priority strategy | Objective | Outcome | Target | Period |
| --- | --- | --- | --- | --- |
| Financial Management | Improve debtor collection | Improved financial rating of the municipality | 2% and below 8% | 2011-2015 |

KPA 6	 Municipal Transformation and Organisational Development

| Priority strategy | Objective | Outcome | Target | Period |
| --- | --- | --- | --- | --- |
| Training and Skills Development | Improve employee skills and competencies | % of performing employees contributing to productivity | 75% of employees | 2011-2015 |
| Staff Component and Appointments | Appoint employees to all vacant posts | Number reduction in vacancy rate | 15 employees at management level | 2011-2015 |
| Organisational Infrastructure | Implement and upgrade the computer system | Uptime availability and function of the system | 98% uptime and running of the sys. | 2011-2015 |
| Marketing and Corporate Image | Promote and improve the corporate image of the municipality | % of stakeholder satisfaction index | Establish baseline | 2011-2015 |

HIV/AIDS

| Priority strategy | Objective | Outcome | Target | Period |
| --- | --- | --- | --- | --- |
| To provide support services to communities on HIV/AIDS awareness | Appointment of HIV/AIDS coordinator | Appointed coordinator | 100% | 2011-2015 |
| Provide programmes on HIV/AIDS prevention | Minimized HIV/AIDS prevention by hosting campaigns | Programmes led by Community Services Manager | 100% | 2011-2015 |

3.4	Legal Framework

In terms of the Constitution Ephraim Mogale local municipality is a Category B municipality with an Executive committee system.

3.5	Role of Local Government

MFMA circular 54 Annexure A – 12 Outcomes of government

1. Improve the quality of basic education

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Improve quality of teaching and learning 2. Regular assessment to track progress 3. Improve early childhood development 4. A credible outcomes-focused accountability system | Increase the number of Funza Lushaka bursary recipients from 9300 to 18 100 over the 2011 MTEF  Assess every child in grades 3, 6 and 9 every year  Improve learning and teaching materials to be distributed to primary schools in 2014  Improve maths and science teaching | Facilitate the building of new schools by:  Participating in needs assessments  Identifying appropriate land  Facilitating zoning and planning processes  Facilitate the eradication of municipal service backlogs in schools by extending appropriate bulk infrastructure and installing connections |

2. Improve health and life expectancy

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Increase life expectancy to 58 for males and 60 for females 2. Reduce maternal and child mortality rates to 30-40 per 1 000 births 3. Combat HIV/Aids and TB 4. Strengthen health services effectiveness | Revitalise primary health care  Increase early antenatal visits to 50%  Increase vaccine coverage  Improve hospital and clinic infrastructure  Accredit health facilities  Extend coverage of new child vaccines  Expand HIV prevention and treatment  Increase prevention of mother-tochild transmission  School health promotion increase school visits by nurses from 5% to 20%  Enhance TB treatment | Many municipalities perform health functions on behalf of provinces  Strengthen effectiveness of health services by specifically enhancing TB treatments and expanding HIV and AIDS prevention and treatments  Municipalities must continue to improve Community Health Service infrastructure by providing clean water, sanitation and waste removal services |

3. All people in South Africa protected and feel safe

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Reduce overall level of crime 2. An effective and integrated criminal justice system 3. Improve perceptions of crime among the population 4. Improve investor perceptions and trust 5. Effective and integrated border management 6. Integrity of identity of citizens and residents secured 7. Cyber-crime combated |  Increase police personnel  Establish tactical response teams in provinces  Upgrade IT infrastructure in correctional facilities  ICT renewal in justice cluster  Occupation-specific dispensation for legal professionals  Deploy SANDF soldiers to South Africa’s borders |  Facilitate the development of safer communities through better planning and enforcement of municipal by-laws  Direct the traffic control function towards policing high risk violations – rather than revenue collection  Metro police services should contribute by:  Increasing police personnel  Improving collaboration with SAPS  Ensuring rapid response to reported crimes |

4. Decent employment through inclusive economic growth

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Faster and sustainable inclusive growth 2. More labour-absorbing growth 3. Strategy to reduce youth unemployment 4. Increase competitiveness to raise net exports and grow trade 5. Improve support to small business and cooperatives 6. Implement expanded public works programme |  Invest in industrial development zones  Industrial sector strategies – automotive industry; clothing and textiles  Youth employment incentive  Develop training and systems to improve procurement  Skills development and training  Reserve accumulation  Enterprise financing support  New phase of public works programme |  Create an enabling environment for investment by streamlining planning application processes  Ensure proper maintenance and rehabilitation of essential services infrastructure  Ensure proper implementation of the EPWP at municipal level  Design service delivery processes to be labour intensive  Improve procurement systems to eliminate corruption and ensure value for money  Utilise community structures to provide services |

5. A skilled and capable workforce to support inclusive growth

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. A credible skills planning institutional mechanism 2. Increase access to intermediate and highlevel learning programmes 3. Increase access to occupationspecific programmes (especially artisan skills training) 4. Research, development and innovation in human capital |  Increase enrolment in FET colleges and training of lecturers  Invest in infrastructure and equipment in colleges and technical schools  Expand skills development learnerships funded through sector training authorities and National Skills Fund  Industry partnership projects for skills and technology development  National Research Foundation centres excellence, and bursaries and research funding  Science council applied research programmes |  Develop and extend intern and work experience programmes in municipalities  Link municipal procurement to skills development initiatives |

6. An efficient, competitive and responsive economic infrastructure network

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Improve competition and regulation 2. Reliable generation, distribution and transmission of energy 3. Maintain and expand road and rail network, and efficiency, capacity and competitiveness of sea ports 4. Maintain bulk water infrastructure and ensure water supply 5. Information and communication technology 6. Benchmarks for each sector |  An integrated energy plan and successful independent power producers  Passenger Rail Agency acquisition of rail rolling stock, and refurbishment and upgrade of motor coaches and trailers  Increase infrastructure funding for provinces for the maintenance of provincial roads  Complete Gauteng Freeway Improvement Programme  Complete De Hoop Dam and bulk distribution  Nandoni pipeline  Invest in broadband network infrastructure |  Ring-fence water, electricity and sanitation functions so as to facilitate cost-reflecting pricing of these services  Ensure urban spatial plans provide for commuter rail corridors, as well as other modes of public transport  Maintain and expand water purification works and waste water treatment works in line with growing demand  Cities to prepare to receive the devolved public transport function  Improve maintenance of municipal road networks |

7. Vibrant, equitable and sustainable rural communities and food security

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Sustainable agrarian reform and improved access to markets for small farmers 2. Improve access to affordable and diverse food 3. Improve rural services and access to information to support livelihoods 4. Improve rural employment opportunities 5. Enable institutional environment for sustainable and inclusive growth |  Settle 7 000 land restitution claims.  Redistribute 283 592 ha of land by 2014  Support emerging farmers  Soil conservation measures and sustainable land use management  Nutrition education programmes  Improve rural access to services by 2014:  Water - 74% to 90%  Sanitation - 45% to 65%  Sanitation - 45% to 65% |  Facilitate the development of local markets for agricultural produce  Improve transport links with urban centres so as to ensure better economic integration  Promote home production to enhance food security  Ensure effective spending of grants for funding extension of access to basic services |

8. Sustainable human settlements and improved quality of household life

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Accelerate housing delivery 2. Accelerate housing delivery 3. Improve property market 4. More efficient land utilisation and release of state-owned land |  Increase housing units built from 220 000 to 600 000 a year  Increase construction of social housing units to 80 000 a year  Upgrade informal settlements: 400 000 units by 2014  Deliver 400 000 low-income houses on state-owned land  Improved urban access to basic services by 2014:  Water - 92% to 100%  Sanitation - 69% to 100%  Refuse removal - 64% to 75%  Electricity - 81% to 92% |  Cities must prepare to be accredited for the housing function  Develop spatial plans to ensure new housing developments are in line with national policy on integrated human settlements  Participate in the identification of suitable land for social housing  Ensure capital budgets are appropriately prioritised to maintain existing services and extend services |

9. A response and, accountable, effective and efficient local government system

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Differentiate approach to municipal financing, planning and support 2. Community work programme 3. Support for human settlements 4. Refine ward committee model to deepen democracy 5. Improve municipal financial administrative capability 6. Single coordination window |  Municipal capacity-building grants:  Systems improvement  Financial management (target: 100% unqualified audits)  Municipal infrastructure grant  Electrification programme  Public transport & systems grant  Bulk infrastructure & water grants  Neighbourhood development partnership grant  Increase urban densities  Informal settlements upgrades |  Adopt IDP planning processes appropriate to the capacity and sophistication of the municipality  Implement the community work programme  Ensure ward committees are representative and fully involved in community consultation processes around the IDP, budget and other strategic service delivery issues  Improve municipal financial and administrative capacity by implementing competency norms and standards and acting against incompetence and corruption |

10. Protection and enhancement of environmental assets and natural resources

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Enhance quality and quantity of water resources 2. Reduce greenhouse gas emissions; mitigate climate change impacts; improve air quality 3. Sustainable environment management 4. Protect biodiversity |  National water resource infrastructure programme  reduce water losses from 30% to 15% by 2014  Expanded public works environmental programmes  100 wetlands rehabilitated a year  Forestry management (reduce deforestation to <5% of woodlands)  Biodiversity and conservation (increase land under conservation from 6% to 9%) |  Develop and implement water management plans to reduce water losses  Ensure effective maintenance and rehabilitation of infrastructure  Run water and electricity saving awareness campaigns  Ensure proper management of municipal commonage and urban open spaces  Ensure development does not take place on wetlands |

11. A better South Africa, a better and safer Africa and world

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Enhance the African agenda and sustainable development 2. Enhance regional integration 3. Reform global governance institutions 4. Enhance trade and investment between South Africa and partners |  International cooperation: proposed establishment of the South African Development Partnership Agency  Defence: peace-support operations  Participate in post-conflict reconstruction and development  Border control: upgrade inland ports of entry  Trade and Investment South Africa:  Support for value-added exports  Foreign direct investment promotion |  Role of local government is fairly limited in this area. Must concentrate on:  Ensuring basic infrastructure is in place and properly maintained  Creating an enabling environment for investment |

12. A development-orientated public service and inclusive citizenship

| Outputs | Key spending programmes(National) | Role of Local Government |
| --- | --- | --- |
| 1. Improve government performance 2. Government-wide performance monitoring and evaluation 3. Conduct comprehensive expenditure review 4. Information campaign on constitutional rights and responsibilities 5. Celebrate cultural diversity |  Performance monitoring and evaluation:  Oversight of delivery agreements  Statistics SA: Census 2011 – reduce undercount  Chapter 9 institutions and civil society: programme to promote constitutional rights  Arts & Culture: promote national symbols and heritage  Sport & Recreation: support mass participation and school sport programmes |  Continue to develop performance monitoring and management systems  Comply with legal financial reporting requirements  Review municipal expenditures to eliminate wastage  Ensure councils behave in ways to restore community trust in local government |

3.6	Objectives of Local Government

1.	To provide democratic and accountable government for local communities.

2.	To ensure the provision of services to communities in a sustainable manner.

3.	To promote social and economic development.

4.	To promote a safe and healthy environment.

5.	To encourage the involvement of communities and community organizations in the matter of local government.

3.7	Integrated Development Planning Perspective in terms of alignment within the framework of District IDP,LGDS,and NSDP

The process plan of  the municipality is integrated with the framework of the district in that it has been aligned therewith.

The Limpopo Growth and Development Strategy(LGDS) 2005 is aimed at enhancing the competitive advantages of the province and 	the objectives thereof is included in the municipality’s LED strategy.

The National Spatial Development Perspective(NSDP) is the primary spatial lens through which policymakers view socio-economic 	development in the country as a whole and the plan and 5 principles that steer national infrastructure investment and development 	decisions is covered in the Spatial Development framework of the municipality.

3.8	IDP/Budget Review Structures and processes

3.8.1	IDP/Budget Review Structures

The structure that are dealing with the review process of the IDP as well as the budget process are as per the following schedule:

| STRUCTURE | TERMS OF REFERENCE / ROLES & RESPONSIBILITIES |
| --- | --- |
| Council | - To approve the IDP and Budget |
| Executive committee | - To make recommendations to the Council regarding the adoption of the IDP and Budget |
| Technical Services,Finance/Strategic planning,Community services,Corporate services Portfolio Committees and IDP Steering committee | - Consider and comment on inputs from ward committees, sector departments, management team and the IDP Rep Forum. |
| IDP Representative Forum | - Review organisational performance, IDP and discuss future plans - Consider and comment on departmental business plans and the draft budget for the identified projects in the business plans |
| Ward Committees | Review ward development plans in line with changing circumstances by giving details of the progress on implementation of projects in each village. |
| Community Development Workers | - Obtain information regarding status quo information of infrastructure for each village. |
| Members of the Ephraim Mogale local municipality Management Team namely ,Municipal Manager, Acting Manager Strategic Planning, Manager Technical services Manager Community services and Manager Corporate services | - Consider and comment on inputs from ward committees - Compile departmental business plans and draft budget for the proposed projects - Compile SDBIP which is aligned to IDP and budget |

3.8.2	IDP Budget Review Processes

The table below indicates the process that will be followed to compile the Budget and IDP  for  2011/16.

| Phases | Activity | Outputs | Role Players | Tools/Methodology | Time Frame |
| --- | --- | --- | --- | --- | --- |
| Preparatory | Management Meeting Discuss IDP Review and Budget Process | IDP Review and Budget Process Plan | IDP Manager Municipal Manager Departmental Heads | Meeting | 22 Aug 10 |
| Analysis | *Status Quo report *Identification of opportunities and constraints *Strategy Development *Implementation plan | Visit to 14 wards | IDP Manager Unit Managers PRO Ward Committees | Interviews Questionnaires Meetings Desktop | 1 Aug – 31 Aug 2010 |
|  | 1st IDP Representative forum | Presentation of analysis phase | All Stakeholders | Meeting | 30 November 2010 |
| Strategies | Performance and IDP Status Quo Report | Assessment of organizational achievements, problems opportunities and constraints. Consolodation of information from Ward Development plans Recommendations on future plans | Municipal Manager IDP Manager | Interview Desktop | 30 Nov 2010 |
|  | Strategic Planning Session | Institutional challenges and SWOT analysis | Municipal Manager IDP Manager Departmental Heads | Working session | 8-9 February 2011 |
|  | Strategic Planning Session | Priority issues & development of KPA’s & KPI’s | Municipal Manager IDP Manager Departmental Heads Councillors | Working session | 8-9 February 2011 |

| Phases | Activity | Outputs | Role Players | Tools/Methodology | Time Frame |
| --- | --- | --- | --- | --- | --- |
| Projects | Strategic Planning Session | Projects which have funding & wish list which have no funding | Municipal Manager IDP Manager Departmental Heads | Working session | 8-9 February 2011 |
| Integration | Drafting of Annual Departmental/Operational Plans and Departmental budgets | Programmes reflective of :- -Projects/programmes -Objectives -KPI’s and Targets -Cost Estimates -Implementation plan | Departmental Heads Relevant organs of state | -Planning sessions with staff -Planning sessions with officials from various organs of state -Desktop | 8-9 Feb 2011 |
|  | Annual Municipal Business plan (consolidation of Departmental plans) | Consolidated Draft IDP and Budget | IDP Manager Chief Financial Officer | Desktop | 8-9 February 2011 |
|  | Strategic Planning Session | Discuss draft IDP which include annual business/operational plans | Departmental Heads Divisional Managers | Meeting | 8-9 February 2011 |
|  | 1st Draft IDP and draft Budget to IDP/Budget Steering and Portfolio Committees | Political Assessment and recommendations of draft IDP and draft Budget | Departmental Heads IDP/Budget Steering and Portfolio committees members | Meeting | 23 February 2011 |
|  | 2nd IDP Representative forum | Tabling of the 1st draft IDP to stakeholders . Stakeholders comments/inputs | Stakeholders | Meeting | 24 February 2011 |

| Phases | Activity | Outputs | Role Players | Tools/Methodology | Time Frame |
| --- | --- | --- | --- | --- | --- |
|  | 1st Draft IDP and draft Budget to Executive Committee | Political Assessment and recommendations of draft IDP and Budget | Mayor Executive Committee Management | Meeting | 25 February 2011 |

|  | 1st Draft IDP and draft Budget to Council | . Political assessment and approval of draft Budget and IDP | All Councillors Management | Meeting | 28 February 2011 |
| --- | --- | --- | --- | --- | --- |
|  | Invitation for public comments on the Budget an IDP | . Stakeholders comments | -All residents -District Municipality -Stakeholders | Written/oral submissions Public hearings/ Roadshows/Imbizo’s | 1 March- 28 March 2011 |

|  | Development of service delivery and Budget implementation plan | Service delivery and Budget implementation plan | Municipal Manager IDP Manager Heads of departments | Submit final plans to MM/IDPM | 4 April 2011 |
| --- | --- | --- | --- | --- | --- |
| Approval | Final draft to the IDP/Budget Steering and Portfolio committees | Political inputs and recommendations on final draft of the IDP and Budget | IDP/Budget Steering and Portfolio Committees | Meeting | 13 April 2011 |
|  | Final draft to the Executive committee | Political inputs and recommendations on final draft of the IDP and Budget | Executive Committee | Meeting | 18 April 2011 |
|  | Final draft to the Council for approval | Council approval of Budget and IDP | All Councillors Management Members of the public | Meeting | 20 April 2011 |
|  | Development of performance plans and performance agreements | Performance plans and performance agreements | Mayor Municipal Manager | Planning session | 3-7 June 2011 |

| Phases | Activity | Outputs | Role Players | Tools/Methodology | Time Frame |
| --- | --- | --- | --- | --- | --- |
|  | Implementation of IDP, Budget and PMS | Implementation | All staff members | Work | 1 Jul 2011-30 Jun 2012 |
|  | 1st Quaterly Review 2nd Quaterly Review 3rd Quaterly Review 4th Quaterly Review | Review Progress against: Meeting of objectives Time frames Expenditure patterns Development impact | Mayor Municipal Manager Departmental Heads | Meeting/Workshop | Mid Oct 2010 Mid Jan 2011 Mid Apr 2011 Mid July 2011 |
|  | Annual report | Compile annual report | Municipal Manager Departmental Heads |  | Mid July 2011 |

3.9	Assessment of previous IDP

In terms of the DLGH, IDP Assessment report (2010/11) the credible status of the IDP for 2010/11 is High and gaps identified in the assessment was included in this document.

CHAPTER 2 – ANALYSIS PHASE

4.	SITUATIONAL ANALYSIS

4.1	Demographic Analysis

Population density – 91 people per km², Urban rural population – 11.8% urban and 88.2% rural

Age profile – 0-9yrs=90675,20-59yrs=66262,60yrs+= 17438 : Total = 174375

Gender Breakdown – Male = 78796,Female = 95579 : Total = 174375

Education :None =43593,Primary = 45337,Secondary = 38362,Tertiary = 1743,Unspec.= 5231,Population below 5yrs = 20925 – Total = 174375

4.2	PopulationThe table below gives details of the wards, names of villages, population and number of  households:

| Ward | Name of village | Population | No of households |
| --- | --- | --- | --- |
| 1 | Driefontein | 3025 | 550 |
| 1 | Malebitsa(Kwamatabana Vlakplaas) | 6193 | 1126 |
| Total |  | 9218 | 1676 |
| 2 | Rathoke | 5470 | 943 |
| 2 | Uitvluht(Ga-Pota) | 7100 | 1291 |
| Total |  | 12570 | 2234 |
| 3 | Metsanangwana(Keerom Makokomane) | 3870 | 704 |
| 3 | Mmakola(Doornlaagte Klopper) | 3400 | 618 |
| 3 | Spitspunt | 2869 | 522 |
| Total |  | 10139 | 1844 |

| 4 | Zamenkomst(Matlerekeng) | 3832 | 697 |
| --- | --- | --- | --- |
| 4 | Rathoke(Part) | 3330 | 666 |
| Total |  | 7162 | 1363 |
| 5 | Toitskraal Commercial farming | 283 | 51 |
| 5 | Other farming areas | 3912 | 809 |
| 5 | Farming areas | 3988 | 825 |
| Total |  | 8183 | 1685 |

| Ward | Name of village | Population | No of households |
| --- | --- | --- | --- |
| 6 | Matla-a-Ramoshebo(Toitskraal Matlala) | 6952 | 1264 |
| 6 | Mokgwaneng(Tweefontein Holdings) | 1683 | 306 |
| 6 | Mamaneng(Witfontein Holdings) | 1457 | 265 |
| 6 | Matatadibeng(Mahlakodisea) | 280 | 51 |
| 6 | Tshikanosi(Leeukuil) | 2620 | 476 |
| 6 | Ditholong | 1343 | 244 |
| 6 | Toitskraal Agri Holdings(Matswayaneng Kgomotlou) | 397 | 72 |
| Total |  | 14732 | 2678 |
| 7 | Marble Hall | 3377 | 965 |
| 7 | Farming areas | 3687 | 825 |
| 7 | Moosrivier | 300 |  |
| Total |  | 7364 | 1790 |
| 8 | Leeuwfontein A (Moganyaka) | 7590 | 1380 |
| 8 | Leeuwfontein A Ext 1 RDP | 520 | 130 |
| Total |  | 8110 | 1510 |
| 9 | Moganyaka North(Brakfontein A Kgosing) | 1425 | 259 |
| 9 | Moganyaka South(Brakfontein B New Stand | 3119 | 567 |
| 9 | Manapyane(Leeuwfontein B, Manapsane) | 2594 | 472 |
| Total |  | 7138 | 1298 |
| 10 | Makgatle A(Makharankana,Mmakgabe/Klipspruit) | 836 | 152 |
| 10 | Makgatle B(Makharankana, Mmakgabe/Klipspruit) | 1133 | 206 |
| 10 | Mamphokgo(Rietvallei) | 4015 | 730 |
| Total |  | 5984 | 1088 |

| Ward | Name of village | Population | No of households |
| --- | --- | --- | --- |
| 11 | Ragaphela(Rakgwadi, Mohlalaotwane/Vooruitsig) | 6050 | 1100 |
| 11 | Moeding(Welgelegen,Saliesloof) | 1203 | 219 |
| 11 | Selebaneng(Ramoroke) | 314 | 57 |
| 11 | Puleng(Paardenzoek) | 328 | 60 |
| 11 | Puleng B(Masanteng, Paardenzoek) | 219 | 40 |
| 11 | Matilu(Klipkloof) | 469 | 85 |
| 11 | Goru(Makhutse) | 300 | 55 |
| 11 | Ga-Matlala | 3296 | 599 |
| 11 | Makhutso | 500 | 91 |
| Total |  | 12679 | 2306 |
| 12 | Legolaneng(part) | 275 | 50 |
| 12 | Mabitsi A(Goedetrouw) | 800 | 145 |
| 12 | Mabitsi B(Goedetrouw) | 1700 | 309 |
| 10 | Ngwalemong A(Buffelskloof) | 1287 | 234 |
| 12 | Ngwalemong B | 550 | 100 |
| 12 | Mmakgatle(12),(Ga-Hlopa, Klipspruit) | 2300 | 418 |
| 12 | Mmotwaneng | 2611 | 475 |
| 12 | Serithing(Goedetrouw) | 1613 | 293 |
| 12 | Vaalbank(Goedetrouw | 1446 | 263 |
| Total |  | 12582 | 2287 |

| Ward | Name of village | Population | No of households |
| --- | --- | --- | --- |
| 13 | Doornspruit A(Greenside) | 2865 | 521 |
| 13 | Mohlotsi(Buffelsfontein A) | 1100 | 200 |
| 13 | Disanyane(Goedgedacht,Motseleope) | 2200 | 400 |
| 13 | Ga-Masha(Seruleng,Masha) | 1305 | 237 |
| 13 | Ga-Mmela(Monte Video) | 290 | 53 |
| 13 | Gareagopola | 880 | 160 |
| 13 | Manotolwaneng(Ga-Ragopole) | 660 | 120 |
| 13 | Kgaruththu(Frischgewaagd) | 285 | 52 |
| 13 | Mathukhuthela A(Goedgedacht) | 1177 | 214 |
| 13 | Mathukhuthela B(Goedgedacht) | 913 | 166 |
| 13 | Moomane(Goedehoop) | 2833 | 515 |
| 13 | Matseding | 1584 | 396 |
| 13 | Tompi Seleka(Nyakelang, Arabie Agri College) | 1173 | 20 |
| Total |  | 17265 | 3054 |
| 14 | Dichoeung(Doornpoort) | 4650 | 845 |
| 14 | Regae(Van der Merwes Kraal,Tsantsabela) | 11000 | 2000 |
| Total |  | 15650 | 2845 |
| 15 | Elandskraal A(Sevenstad) | 12000 | 2182 |
| 15 | Elandskraal A Ext 1 |  |  |
| 15 | Weltevreden(Mbuzin) | 2488 | 452 |
| 15 | Hinlopen(Morarela) | 2000 | 364 |
| Total |  | 16488 | 2998 |

| Ward | Name of village | Population | No of households |
| --- | --- | --- | --- |
| 16 | Rooibokkop |  |  |
| 16 | Ditholong(Lolamontes) | 2420 | 440 |
| 16 | Mogalatsana(Coetzeesdraai) | 1211 | 220 |
| 16 | Phetwane(Hindostan) | 889 | 162 |
| 16 | Tsimanyane North(Goevertrouwen) | 1577 | 287 |
| 16 | Tsimanyane South(Mooihoek) | 1300 | 236 |
| 16 | Tsimanyane Ext(Mashemong) |  |  |
| Total |  | 7397 | 1345 |
| Grand Total |  | 174375 | 32304 |

4.3	Focus Groups

Five Traditional  leaders are situated in the municipality

Disabillity,Youth and Gender desk has been established in the municipality and there programs are coordinated through the Mayor’s 		office. Reading facilities have been established for the blind at the Marble Hall library.

Number of children under the age of 15 = 90675

Number of pensioners over age of 65     = 17438

108113

4.4	Income and Employment (development challenges)

1.Unemployment Rate in Ephraim Mogale Local Municipality

| YEAR | FORMALLY EMPLOYED | INFORMALLY EMPLOYED | UNEMPLOYED | UNEMPLOYMENT RATE % |
| --- | --- | --- | --- | --- |
| 2002 | 7,165 | 2,987 | 13,791 | 44.0% |
| 2003 | 7,158 | 3,003 | 15,153 | 45.4% |
| 2004 | 7,024 | 3,035 | 15,061 | 44.4% |
| 2005 | 6,985 | 3,645 | 14,516 | 41.8% |
| 2006 | 7,008 | 3,786 | 14,122 | 40.7% |

Source: Global Insight, 2008

2.Employment and occupation sectors

| Sector | Sector % 2006 |
| --- | --- |
| 1 Agriculture | 5.8 |
| 2 Mining | 12.5 |
| 3 Manufacturing | 4.6 |
| 4 Electricity | 3.1 |
| 5 Construction | 1.3 |
| 6 Trade | 12.6 |
| 7 Transport | 8.3 |
| 8 Finance | 21.9 |
| 9 Community services | 29.8 |

3. Annual Household Income Distribution for Marble Hall 2005-2006

| INCOME GROUP | 2005 | 2006 | SHIFT% |
| --- | --- | --- | --- |
| R0-R2,400 | 2,575 | 2,769 | 7.5 |
| R2,401-R6000 | 3,788 | 3,848 | 1.6 |
| R6,001-R12,000 | 3,937 | 3,806 | -3.3 |
| R12,001-R18,000 | 5,734 | 5,638 | -1.7 |
| R18,001-R30,000 | 4,773 | 4,801 | 0.6 |
| R30,001-R42,000 | 3,446 | 3,506 | 1.7 |
| R42,001-R54,000 | 2,386 | 2,500 | 4.8 |
| R54,001-R72,000 | 1,956 | 2,101 | 7.4 |
| R72,001-R96,000 | 1,612 | 1,761 | 9.3 |
| R96,001-R132,000 | 1,234 | 1,364 | 10.5 |
| R132,001-R192,000 | 957 | 1,065 | 11.4 |
| R192,001-R360,000 | 659 | 761 | 15.4 |
| +R360,000 | 457 | 545 | 19.3 |
| Total | 33,514 | 34,465 | 2.8 |

Source: Global Insight, 2008

5.	INFRASTRUCTURE AND BASIC SERVICES ANALYSIS

5.1	Water

The Sekhkhune district municipality is the Water service authority and a Water services development plan has been compiled for the municipality which addresses the water issues.

The main schemes or bulk sources of water in the municipal area are:

Ikangala Water Board for Moutsé west for Ward 1 – 4, ptn 5 & 6).

Loskop Irrigation Scheme - Loskop Dam for Ward ptn 5 & 7).

Lepelle Northern Water and Treatment Plant – Flag Boshielo Dam for Ward 8 - 16.

Rivers, streams and wells.

Boreholes and Fountains.

Water tanks ward 1 – 3 & 6.

| PLANNED INTERVENTIONS | Backlog | Progress Made | Key Challenges | Interventions |
| --- | --- | --- | --- | --- |
| District to return the WSA status . District to fast track the completion of retention dam and reservoir . District to improve the quality at the reservoir . Improve the quality of water at all the households . Expedite the retention of the water service providers | To provide water to 16576 households to RDP level | There are 32304 households and 16576 below RDP level(6225 households in Moutse west receive water by water tanker) | Projects not complete and funding required. No bulk water supply at Moutse. Capacity to deal with maintenance of infrastructure. Meters in 293 towns faulty | District to complete uncompleted infrastructure projects in Mashimong, Makgtle (Ten) Engage the district in the supply of water for Ward 1-4 Expedite the retention of the water service providers |

5.1.1.Community needs – Ward visits : August 2010

| Ward 1 | 1.Bulk water supply from canal at Toitskraal and reservoir steel tank at Spitspunt 2.Valves open/close at Spitspunt, Malebitsa and Driefontein by maintenance team 3.Reticulation Spitspunt extension |
| --- | --- |
| Ward 2 | 1.Bulk water – running water.2.Irrigation – 4 boreholes 3 Mokgwaneng.3. Three boreholes to be fixed at Tshikanoshi |
| Ward 3 | 1.3 Jo-jo tanks per village required 2.Uitvlugt – 2 boreholes require pumps.3.Keerom – test borehole used by |
| Ward 4 | 1.Bulk water required from Loskop dam and reservoir to be build in the ward. 2.Maintenance team required to clean all valves. 3.Water board required to maintain bulk pipes. 4House connections required at Matlerekeng and Rathoke and extension for new stands. 5.Electricity required for six boreholes – check with GSDM who can supply generators. 6.Pre-paid required for each borehole |
| Ward 5 | 1.Pipeline for extension at Thabaneng to be place on ground as ground is hard 2.Motoneng section steep hill need valve after section and before to let water through 3.16 people next to clinic have no water |
| Ward 6 | 1.Water treatment works needs upgrade to be completed to Blue drop standard. 2.Industrial area requires extra pressure and Ext 6 3.Replace, repair and installation of water valves - problems being encountered by the municipality when trying to effect repairs to ageing water lines in town and industrial area are in need of urgent attention and GPS location. 4.Fire hydrants in Marble Hall town to be serviced/repaired where they have been knocked over, painted and recorded by GPS reading of their location 5. +- 20 Houses without water meters in ext 6 that needs to be installed 6.Increase the dameter of the water supply from the rear of the Spar building, that supplies water for road island 4,5 and 6 from a 25mm pipe to a50mm supply line. 7.Increase the diameter of the water supply of water connections running on the left hand side of Railway street from a 25mm to a 50mm water supply. 8.Install water pressure pump to increase the water pressure throughout the town and industrial are |
| Ward 7 | Water debt to be cancelled |
| Ward 8 | 1.Reservoir required for Manapyane extension.2.Yard connections required in all 3 villages.3.Communual meter system not functional. 4.No RDP in some streets.5.Manapyane has no water connections(RDP 200m).6.Require reticulation in all 3 villages. 7.GSDM to enforce bylaws i.r.o. illegal connections.8.Require more vendors to sell coupons- Manapyane cashier |
| Ward 9 | Yard connections for Mamphogo & Makgatle required 70% of homesteads on hill might need reservoir and pump |
| Ward 10 | 1.Yard connections required for the ward.2. Boreholes to be revitalized – Mabitsi’B”(3),Vaalbank(2),Motwaneng(2), Greenside(2)Ngwalemong(4),Klopper(1)Serething(2) |
| Ward 11 | 1.Frishgewaagd/Gareagopola no water.Water tankers required in the interim to take water to fill tanks 2.Disanyane/Mathukhutela have three reservoirs and leakages were fixed .LNW required to open valves at reservoirs 3.All schools need water connections – water tanker required to fill the jo-jo tanks at schools 4.All villages are RDP standard require pipes and a standpipe in each street.5.Mathukutela need house connections. 6.All villages need house connections in next 5 years.7.Boreholes One borehole each required for the followimg villages: Gammela,Moomane,Gamasha,Manotoloaneng new stand,Ga-Ragepola,Mthukhuthela A, Frischgewaght & Thabantsho and two for Moshwatata 6.The following villages have boreholes: Manotoloaneng – 2 situated next to city rovers football ground(equipped but not functioning), water office(vandalized) Mathukathela B – 1 situated next to Mogaladi river(excellent condition) Disanyane – 1 situated next to last bus stop(equipped but not functioning)Hand pump need repairs Mohlalaotwane – 5 situated at Ngwanamashile sch(not equipped),next to Mohthi Mmemeloe (not equiped) next to maize co-operative(functional),next Skabate(not equiped) and Manase Nghoshi( not equiped) Mohlalaotwane new stand – 5 situated beyond Mr Kgopu Tso(no equipment)next to Mr Seje house(equipped but not functioning)next to Makdi Matlala(no equipment)next to Matjedi sch(no equipment)next to Mr Matogkoma(no equipment) |
| Ward 12 | 1.House connections required for all villages including Ditholong new extension except Matseding, Mohlotsi, Mooihoek, Ditholong and Tsimanyane.2.Pipes required at Letebejane ext part of Mashemong and Mogalatsane ext and part Ditholong. 3.Matseding water pipes are broken and water are being wasted.4.Office to be established at Matseding to buy water 5.Water required at Taxi rank at Tsimanyane(main pipe to RDP houses-how to connect?).6.Water required at all cemetries |
| Ward 13 | 1.Elandskraal need dedicated water pump to be installing for Flag Boshielo (Arabie) West.2.Meters to be repaired and serviced regularly 3.Elandskraal need additional water stop valves to each block will reduce shortage of water to all blocks when the problem is base at one block.4.Elandskraal needs COST RECOVERY Campaign. 5.the issue of water at Elandskraal must be on the budget of 2010-2011 not 2011-2015 NB: Community meeting must be held as a matter of urgency before handing the matter of Water and Sanitation issue to the municipality |
| Ward 14 | 1.House connections required at new stands at Regae.2.Water meters to be fixed – no payment are made for water consumption |

  - Sanitation

The Sekhkhune district municipality is the Water service authority and a Water services development plan has been compiled for the municipality which addresses the sanitation issues.

| PLANNED INTERVENTIONS | Backlog | Progress Made | Key Challenges | Interventions |
| --- | --- | --- | --- | --- |
| District to formalise the participation of municipality in the planning, implementation, and M&E District to establish a new sewerage system to cater for the new extension 6 and 1 new school in Marble Hall town District to Maintain plants in marble hall town, eilandskraal, leuwfontein | To provide sanitation to 29169 households to RDP level .Backlog will not be implemented by 2012 | There are 32304 households of which 29169 are below RDP standard | Lack of funding Lack of capacity to maintain infrastructure | District to formalise the participation of municipality in the planning, implementation, and M&E by 01 July 2010. District to establish a new sewerage system to cater for the new extension 6 and 1 new school in Marble Hall town |

5.2.1	Community needs – Ward visits : August 2010

| Ward 1 | VIP toilets next 5 years – Spitspunt 1000, Malebitsa 3000 and Driefontein 1000 |
| --- | --- |
| Ward 2 | No need indicated |
| Ward 3 | Uitvlugt extension require 798 VIP toilets |
| Ward 4 | VIP toilets required for the ward |
| Ward 5 | VIP toilets required for the ward(ward committee to check the number of households) |
| Ward 6 | 1.The need for the M/Hall wastewater plant to be upgraded to allow for additional capacity as the town grows. 2.The urgent need to conclude a contract with an interested party to utilise the excess effluent from the plant, a matter that now has been outstanding since Jan 2008. 3. The need for the remaining manholes through out town and the industrial area need to be covered a programme, which is outstanding now for some years. 4. The need for additional public toilets in town and the industrial area is required. |
| Ward 7 | Toilets for internal houses RDP project required |
| Ward 8 | 1.Ceptic tank at Manapyane hall require to be drained.2.VIP toilets required for the ward.Pit holes need to be drained. 3.Water borne toilets required at Leeuwfontein RDP. 4.Move sewerage ponds at Leeuwfontein over road as sewerage are seeping into houses. |
| Ward 9 | VIP toilets required for all villages |
| Ward 10 | VIP toilets required for all villages accept Goru but not all houses.To do research. |
| Ward 11 | VIP toilets required in all villages |
| Ward 12 | 1.Water borne system required at Tsimanyane,Mashemong and Mooihoek 2.Flush toilets required for all other villages but VIP toilets in mean time |
| Ward 13 | 1.Toilets are needed @ Pay Point for Morarela and Mbuzini.2.Sewer Infrastructure Network at Morarela and Mbuzini 3.proper need for water borne toilets at Elandskraal |
| Ward 14 | Regae require water borne sewerage system |

5.3	Electricity

| PLANNED INTERVENTIONS | Backlog | Progress Made | Key Challenges | Interventions |
| --- | --- | --- | --- | --- |
| Total number of households served against total number of households Total number of households remaining to be served. | To provide 1608 connections. All households will not have access to electricity by 2010 if ESKOM do not provide funds for backlog | There are 32304 households and 30715 are served | Lack of funds Eskom is service provider outside Marble Hall and have to rely on them to improve infrastructure | 449 connection on list of Eskom for 2010/11 |

5.3.1	Community needs – Ward visits : August 2010

| Ward 1 | 1.Appolo lights – Malebitsa 8 one at cemetery,Spitspunt 4 and Driefontein 3.2.House connections – 800 next 5 years |
| --- | --- |
| Ward 2 | 1.New connections required for Doornlaagte(70) , Doornlaagte ext 50 Tshikanosi(50)Toitskraal agri holdings(10)Mamaneng/Mogwaneng area(Bareki)(580).2.High mast lights required for Doornlaagte , Tshikanosi(8 each) , Bareki(8) |
| Ward 3 | 1Apollo lights required at Uitvlugt(8) and Keerom(6).2.100 connections for both villages for next 5 years |
| Ward 4 | 1.High mast lights.reuired at Rathoke (20) and Matlerekeng(10) . 2.Connections next 5 years – Matlerekeng 200 & Rathoke 250 |
| Ward 5 | 1. Require 15 more appolo lights.2.150 connections required for ward.3.1000 connections required for the next 5 years 4.New tribal office require electricity urgently.5.Connections required at compounds on farms. |
| Ward 6 | 1. In view of the excessive ongoing problems being experienced, by the residence relating to the payment of the electrical accounts, it is proposed that an sms system be installed immediately to sms the resident at a fee, advising them that their account was outstanding. This will eliminate the costs and reversal thereof, of charges incorrectly debited against the consumer, as well as the wasted manpower of the municipality to disconnect and reconnect the power, a problem which the municipality is allowing to continue without resolving the matter. 2.The need to complete the power supply from the main board to the individual units at the hawker stall is in need of attention. 3.Consideration of metered power points to farms for labourers housing both existing and yet to be built should be considered either through Eskom or the Municipality for implementation. |
| Ward 7 | 3 high mast lights required at Leeuwfontein extension |
| Ward 8 | 1.Manapyane south and Moganyaka south require 100 connections(far from pole).Check existing boundary. 2.Moganyaka north/south require vending machine 3.Cables on poles are low i.r.o house built at Manapyane ext. next to sewerage works and built over water pipe 4.Eskom satellite office be established to address faults or be serviced by Marble Hall.5.Appolo lights required for all villages. 6.Generators required when lights are out..7.Eskom prepaid to be changed to slip box.8.FBE required for indingents |
| Ward 9 | 1.Makgatle extension-need 120 connections(cables/poles to be provided by municipality)Eskom will provide meters and boxes. 2.Mamphokgo-100 connections not complete.3.Mamphokgo-appolo lights required for north&south(3 each) 4.Appolo lights required at Moeding – one remaining.5. Mmakgatle A & B require 3 appolo lights each 6.Puleng A require 2 appolo lights and Puleng B(1).7.Matilu require 2 appolo lights.8.Vending station required at Moeding and Matilu 9.Upgrade of electricity reticulation needed (plenty power failures) |
| Ward 10 | 20 connections required at Mabitsi B ext,25 at Motwaneng ext,35 at Seretheng ext and 30 at Vaalbank ext,10 at Nkwalemong “A”& 5 at”B”,40 atVaalbank,2 at Mmakgatle,7 at Makhutso and 50 at Manotolwaneng |
| Ward 11 | 1.Gareagapola need electricity – 200 households including new stands of Manotolwaneng 2.Manotolwaneng new stands require 31 connections. 3.Mathukhutela B require 20 connections(list given to J Durie)some areas poles were not installed. 4.Moomane new stands require 20 connections 4 connections are outside existing line 5.Ga-Masha require 16 connection which were left as they are far from existing line(maybe require transformer) 6.Rakgwadi require 8 connections(check list some out of line) and require 10 high mast lights |
| Ward 12 | 1.3200 connections required for the ward.2.Appolo lights required for each village |

| Ward 13 | 1.Need for high Mast Lights at Elandskraal, Morarela and Mbuzini. 2.Elandskraal Extension and Kubela( New Township Establishment) need 2500 household connection. 3.Morarela needs 15 household connections.4.Electricity connection needed to be installed at the Stadium 5.Design of Stadium Electrical Lights 6.Eskom should inform the community before coming to check for the meter boxes and blackout notice. 7.Upgrading of lights at focus Soccer Ground, Basket Ball & Netball |
| --- | --- |
| Ward 14 | 1.Regae require 270 connections.2.Ditchoeung require 80 connections.3.High mast lights required – Regae(5) and Ditchoeung(12) 4.Maintenance by Eskom not good.Register complaint with customer care but are not followed up. 5.Substation required to prevent electricity to go off. |

5.4	Housing

The backlog is 8195 units for the 14 wards. The challenges is to obtain beneficiary lists and for DLGH to allocate units to the municipality. 700 	units was allocated to the municipality during 2010/11 financial year.

5.4.1	Community needs – Ward visits : August 2010

| Ward 1 | 1.Backlog 3 slabs Malebitsa.2.Housing next 5 years – Malebitsa 400, Driefontein 350 and Spitspunt 350 |
| --- | --- |
| Ward 2 | Housing required for the next 5 years : Doornlaagte – 150 , Leeukuil – 150, Mokgwaneng – 60, Mamaneng – 60,Matadibeng - 60 |
| Ward 3 | 1.2010/11 – 50 units per village required.2.Housing required for next 5 years is Uitvlugt(300), Keerom(200) |
| Ward 4 | Housing required for next 5 years: Rathoke(800),Matlerekeng(400) |
| Ward 5 | Housing required for next 5 years – Matlala (1000) and Toitskraal (20 |
| Ward 6 | 1.Urgent application be made for 500 RDP housing at extension 6 phase 3. 2.The 496 sites not developed yet in extension six be considered for development of RDP housing-meeting be arranged with the developer |
| Ward 7 | No need indicated |
| Ward 8 | 1.Housing required for next 5 years is,Moganyaka north(150),Moganyaka south(180)Manapyane(200) and 350 units for the ward for 2010/11.2.50 units at Manapyane to be completed 3.Township establishment for RDP housing at Leewfontein to be checked to establish if Kgoshi handed over the land |
| Ward 9 | 1.500 units required for the ward for the next 5 years.2.Housing required for 2011/12 – Makgatle(100) & Mamphokgo(300) |
| Ward 10 | 1.Housing required as follows : Goru(20 Priority 1),Seretheng new extension(30),Vaalbank(30) Mabitsi A (3 urgently),Mabitsi B(10),Motwaneng(30 priority 2),Ngwalemong “B”(10)&”A”(20) priority 3) ,Klopper(2),Greenside(20),Makgatle(10) |
| Ward 11 | 1.50 units required per village.2.80 units required at Manotoloaneng |
| Ward 12 | 75 houses required per village for next 5 years |
| Ward 13 | Need for housing @ Elandskraal Proper and Extension, Morarela and Mbuzini |
| Ward 14 | 1.Bulk services required for new section at Regae 2.New houses required for Ditchoeung(300) and Regae(500) for next 5 years |

5.5	Waste and Refuse Removal

| PLANNED INTERVENTIONS | Backlog | Progress Made | Key Challenges | Interventions |
| --- | --- | --- | --- | --- |
| DLGH to assist the municipality in sourcing funds for operation and maintenance of landfill site . DLGH and LEDET to assist in Education and Awareness campaign on refuse removal. To service Leeufontein properly when the new vehicles are delivered . | 29959 households require refuse removal service | There are 32304 household of which 2345 are served | Lack of funds and non payment for service at Leeuwfontein | District and LEDET to return the environmental health function to the municipality. |

5.5.1	Community needs – Ward visits : August 2010

| Ward 1 | No need indicated |
| --- | --- |
| Ward 2 | No need indicated |
| Ward 3 | Refuse containers required for both villages |
| Ward 4 | Refuse dump site required |
| Ward 5 | Refuse containers requires |

| Ward 6 | 1.Big amount of plastic bags are placed next to most bins in M/hall, need extra bins to be allocated in the Central Business District. 2.It 2.The turnaround time for maintenance on refuse equipment is chronic and slow and is in need of urgent attention, many times in the recent past equipment standing for months awaiting repair.3.There is an urgent need for this facility to be operated according to the permit issued by DWAF and its conditions for the use of this facility. 4.The need for recycling bins to be made available for the public to use, which in turn could create employment for a number of residences, needs urgent consideration and implementation.These bins could accommodate the following products: Glass,Plastic, Wood,Cardboard, Tin cans, Aluminium waste and Paper 5. The Municipality to engage an urgent consultation with oil recycling companies to legislate and capture all the used oil being dispensed by various companies in town into the storm water system an example being the taxi rank. We seek legislation that all used oil is drummed and recycles by an authorised agent |
| --- | --- |
| Ward 7 | Six refuse bulk bins and dumping site required |
| Ward 8 | 1.Require refuse containers at Tribal authority office in Moganyaka North/South and at the community hall at Manapyane. 2.Require dust bins at all schools.3.Require refuse containers |
| Ward 9 | No need indicated |
| Ward 10 | No need indicated |
| Ward 11 | No need indicated |
| Ward 12 | Refuse removal required in each village and at schools(Provide bulk bins and refuse bags) |
| Ward 13 | 1.Need for fencing of Elandsraal Waste Dumping Site. 2.Need for Bulk Refuse for all villages |
| Ward 14 | Dumpsite and refuse collection required at Regae |

5.6	Roads and Storm water Drainage

The only major route running through the municipal area is the N11 which links Marble Hall with Groblersdal to the south, and Mokopane via Roedtan and with the N1 between Polokwane and Pretoria to the west and north.Provincial roads links Marble Hall with the villages to the west and north .Maintenance of these roads by the relevant authorities is inadequate due to lack of manpower and equipment.

The internal roads in the villages are the responsibility of the Municipality.  Information regarding exact status of the roads, namely public versus local roads, is lacking.   Internal streets within the settlements are generally low quality gravel roads that were never properly planned and constructed.  Basically no provision was made for stormwater drainage. Some of the formal towns have a few tar roads such as Leeuwfontein main roads that are partly tarred, but are deteriorating very quickly.

Backlog is 404km  internal roads to be graded and storm water to be built in all villages . The challenges is to purchase road maintenance equipment to grade roads.

5.6.1	Community needs – Ward visits : August 2010

| Ward 1 | 1.Tar road – Driefontein to Spitspunt to Tshikanoshi.2.Tar road – Driefontein to Malebitsa to Nutfield.3.Grading internal roads 4.Stormwater control |
| --- | --- |
| Ward 2 | 1.Road from Tshikanosi to Malebitsa to be tarred.2.Internal roads to be graded in ward. 3.Tar road required from Maklerekeng road to Ramokgelesane.4.Tar road required from Mokgwaneng to Ramokgelesane.5.Road from Tshikanosi to Keerom to be tarred |
| Ward 3 | 1.Tar road required from Tshikanoshi to Uitvlugt.This is urgently required.2.Acess roads to be maintained |
| Ward 4 | 1.Stormwater control system required at Matlerekeng and Rathoke.2.Expanded public work program required for tarring road passing Moremoso-road to new stand.3.Inner road required to be tarred to RDP to Ramokgeletsane.4.Main bus route to be tarred in both villages. 6.Main road at RDP to be paved – woman project. |
| Ward 5 | 1.Stormwater control required next to tar road befor bridge.2.More speed humps required and community to be consulted for the placing thereof.3.Acess roads to be upgraded with paving(EPWP) including to schools and graveyards .4.Road from Matlala to Kgomotlou require bridge.5.Access road to new tribal office to be paved(EPWP) |
| Ward 6 | 1.N11 trough town proposed widening to 4 lane highway- In view of the heavy congestion of traffic through town, the Sakekamer is preparing a presentation to re-design the entrance to M/Hall from G/Dal, which will propose a four-line highway to accommodate the increased traffic flow apart from other proposals.2.The Urgent need for speed humps to be placed in Akasia Street to slow down the traffic. 3. The need for a robot to control the pedestrian traffic crossing the road N11 from the Wingrin Centre - the present pedestrian crossing is illegal.4. The completion of the drain / storm water canal which has been outstanding since 2006, needs completion before the next rainy season, now only 2 months away.5. The urgent repair and resurfacing of industrial road in front of Obaro is urgently needed, and the extension of this road to join the N11 behind OBARO should be considered to accommodate traffic from the N11. 6. A programme of continues resealing the roads within Marble Hall should be ongoing to avoid further deterioration especially before the coming rainy season. 7. Misspelled and missing street names need to be audited and corrected when necessary, which includes extension six.8. The repair of the many damaged catch pits for stormwater through out town and the industrial area 9. The need for an audit / inspection of all road signs in and around M/Hall and where they are found to be damaged, faded or missing they should be replaced as required. |
| Ward 7 | 1.Paving all internal roads phase 2 & 3.2.Speed humps required on main road |
| Ward 8 | 1. Speed humps required on main road opposite church Moganyaka south and traffic officers required to do speed checks. 2.Pedestrian crossing required at Moganyaka North and South.3.Bridge required between Moganyaka south and north and Manapyane and Manapyane ext..3.Main road from clinic to Moshate to cemetery to be tarred/paved.4.Street by street to be graded. 5.Soil erosion at Moganyaka South and North-reconstruction material required to fill erosion. 6. Drainage required at main road at Moganyaka South/North caused by wetlands |
| Ward 9 | 1.Access roads in all villages to be upgraded .2.Storm water drains required at Mamphogo.3.Road from Moeding to Tafelkop to be tarred. 4.Regravel/grade all access roads and build storm water drains.5.Road to Boshoek to be maintained.6.Stormwater control required in all villages.7.Road Makgatle A & B main access road to be paved approx. 6km(busses) as well as access road and bridge to cemetery. 8.Puleng/Matilu road to be upgraded-link between villages(busses fromMotetema) to be maintained at all times. 9.Speed humps required on main tar road at Mamphogo at primary school and new road to Mushrumela park |
| Ward 10 | 1.Road between Seretheng and Mabitsi B require upgrading and bridge required(low level) urgently.Rock to be blasted 2.Upgrading of road from Manotolwaneng via Makutso to Mmatwaneng with bridges required.3.Road from Ditholong to Mohlalaotwaneto be tarred.4.Access roads Chilwaneg, Mmakgatle(10),Vaalbank,Mmatwaneng andMabitsi to be upgraded/graded 5.New access roads required from Mmatwaneng/Mabitsi A to Serething.6.Maintenance and grading of internal roads required 7.Access road from Ngwalemong B to Makgatle (10) to be tarred.8.Road from Rakgwadi via Seretheng to Ramogwerane require 3 bridges and tarring.9. New grader to be purchased for the ward to grade roads urgently.10.Maintenance of all internal roads in ward required. 11.Upgrading road Makutso via Goru to Rakwadi and low level bridge required at Goru.12.Mabitsi A internal roads and Vaalbank -3 year plan MIG.13.Low level bridge required between Vaalbank and Mabitsi “B” |
| Ward 11 | 1.Road from Lulubar via hospital to Rakgwadi to Ramogwerane to be tarred.2.Road from Arabie to Pokwane to be tarred(Request district to assist with graders to scrape every second week).3.Acess roads and internal streets to be graded/upgraded.4.Bridge required between Mathukhuthela A & B.5.Low level bridge at Manotolwaneng approved to be followed up(check if district road).6.Bridge required at Frischgewaagd.7.Bridge at Mathukhutela not approved – to be followed up.8.Bridge required at Ga-Masha to cemetery.9.Bridge required between Makhutso and Goru.10.Bridge required between Friscgewaagd and Disanyane(Motselope river).11.Gareagapola bridge required in middle of village where river is running.12.Disanyane bridge required in middle of village where river is running |
| Ward 12 | 1.All internal roads require to be maintained.Ditholong require urgent grading.Ditholong/Mogalatsane/Mohlotsi roads need urgent gradingMTS to compile program to be given to ward councilor.2.Streets in villages are in accessable.Letebejane (hand in list from committee at hospital).3.Road from Ditholong via Tsimanyane/Rakgwadi to be tarred(Priority)change financial plan 4.One main street in each village to be paved.5.Low level bridge required between Mogalatsane and Phetwane 6.Road signs for cattle to be installed on the road to Appel crossing and fence to be replaced.7.Stormwater required above Ditholong/Letebejane next to hill.8.Low level bridge required between Letebejane and cemetry |
| Ward 13 | 1.Morarela Internal street paving from Letsiri to Molatudi bus route.2.Elandskraal Storm water drainage at Elandskraal block six from Tsima’s Shop to Maroka .3.Morarela storm water drainage at Morarela from Reservoir .4.Elandskraal Storm water drainage at Elandskraal block Six @ Makola and Mashego streets.5.Elandskraal Paving from Kalekeng Primary to Computer Sports Ground 6.Elandskraal Paving from lepelle to disco.7.Elandskraal Water drainage needed at Z.C.C to main paving.8.Elandskraal Maintenance of disco to lepelle high paving.9.Elandskraal Maintenance from sekwati to Kekana.10.Maintenance of all the streets Morarela, Elandskraal and Mbuzini.11.Elandskraal Development of speed humps @ Elandskraal paving.12.Elandskraal Storm water drainage @ Elandskaal block six next to Kgoshi Moroamoche.13.Elandskraal Paving from block four starting from Ga- Matjie to block Six Disco |
| Ward 14 | 1. Paving,stormwater and speedhumps of main roads of the two villages required.2.Speed humps required on provincial tar road 3.Tar district road at Dichoeung.4.Internal roads to be maintained including stormwater at Regae.4.New stormwater drains required at Ditchoeung.(Beam wall).5.Roads to schools,churches and offices to be paved.6.All streets to be upgraded.7.A storm water drain needed at Regae to direct water away from the sites to the river.(Beam wall).7.Regae require low level bridges in all internal roads 8.Dichoeung internal road require bridge |

5.7	Transport

The taxi rank in Marble Hall is privately owned and is causing various challenges by the taxi associations who are operating from the rural areas. The transport system is also linked with access to education particularly for the rural communities. The railway line between Marble Hall and Pienaarsrivier is out of commission and should be revived and together with air transport provide an opportunity that should be optimally utilised in order to improve the transport system in the area.

Challenge is to transfer existing private taxi rank in Marble Hall to the municipality.

5.7.1	Community needs – Ward visits : August 2010

| Ward 1 | No need indicated |
| --- | --- |
| Ward 2 | No need indicated |
| Ward 3 | No need indicated |
| Ward 4 | No need indicated |
| Ward 5 | 1.Bus stop shelters required next to tar road(Putco).2.Taxi rank required at Elands Cash & Carry.3.Need bus from Great North transport from. Malebitsa to Marble Hall.4.Require school busses for schools |
| Ward 6 | 1.The need for a parking space for overnight trucks (not necessarily behind the hawker stalls) and is now well overdue and in need of urgent discussion.2.Taxi rank Marble Hall - In view of the fact that the contract between the Municipality and the owners of Wingrin Centre is due to expire in the next four years consideration should be given as to whether it would be viable for this facility to be operated by the Municipality. 3.The car wash facility at the taxi rank needs to be closed as it is in complete contradiction of DWAF regulations. 4. The extension and development of the existing airstrip needs consideration and preparation for the increase air traffic and air shows in the future as the town expands. This would include consideration being given for a fuel storage depot on site. 5. The extension of the rail line from Siyabushwa to Marble Hall is in need of consideration in view of the proposed fresh export container depot in Marble Hall to Durban. |
| Ward 7 | No need indicated |
| Ward 8 | 1.Mini taxi rank required at Manapyane and Moganyaka north/south.2.Shelters required at new taxi rank at Leeuwfontein and extension of office |
| Ward 9 | Mamphokgo-upgrade taxi rank |
| Ward 10 | No need indicated |
| Ward 11 | No need indicated |
| Ward 12 | No need indicated |
| Ward 13 | Poor workmanship @ Taxi Rank need for Phase Two Taxi Rank, Hawkers Centre and offices |
| Ward 14 | 1.New taxi rank required at Regae.2.Bus stop shelters required in both villages |

5.8	Free Basic Services

Indigent policy was reviewed by Council on 31 May 2010 which makes provision that an indigent is defined as the total income of all occupants is not more than equal than the amount received by one state pensioner. Indigent register in process of compilation and should be completed during 2011. Indigent register being compiled – 9 wards visited.

Registered indigents receive free basic services for the following services:

1.	Electricity

All registered indigents will receive 50 units of electricity per month free of charge. Unused free electricity units shall not be carried over to the next month. Any meter tampering or dishonesty shall result in the termination of the free service.

Challenge is that 2387 was configured but non active have been de-configured now 2095. Average collection rate 1450/month. 5 				villages new roll out  more than 6000 applications-188 888/month.

2.	Water

All registered and approved indigent consumers will receive the first 6 kilolitres of water fully subsidized. Depending on the availability of funds for this purpose, a subsidy, determined at the beginning of every financial year and not more than the applicable tariff for that year, will be applied for the duration of that particular financial year for consumption in excess of 6 kilolitres per month. The amount of the subsidy will be determined and approved as part of the tariff policy applicable for the financial year. Challenge is for all indigents to register on the indigent register and to verify compliance with policy.

3.	Refuse Removal

All registered destitute indigents shall be fully subsidized for refuse removal. All registered indigents shall be subsidized for refuse removal as determined and provided for by the Council in the annual budget from time to time. Depending on the availability of funds for this purpose a subsidy, determined at the beginning of every financial year and not more than the applicable tariff for that year, will be applied for the duration of that particular financial year. The amount of the subsidy will be determined and approved as part of the tariff policy applicable for the financial year. Challenge is for all indigents to register on the indigent register and to verify compliance with policy.

4.	Sewerage

All registered destitute indigents shall be fully subsidized for sewerage services. All registered indigents shall be subsidized for sewerage services as determined and provided for by the Council in the annual budget from time to time. Depending on the availability of funds for this purpose a subsidy, determined at the beginning of every financial year and not more than the applicable tariff for that year, will be applied for the duration of that particular financial year. The amount of the subsidy will be determined and approved as part of the tariff policy applicable for the financial year.

The challenges are to update the indigent register in order to  provide funds to cater for all the indigents

5.	Site Rental

All registered destitute indigents shall be fully subsidized for the payment of site rental. All registered indigents shall be subsidized for the payment of site rental as determined and provided for by the Council in the annual budget from time to time. Depending on the availability of funds for this purpose a subsidy, determined at the beginning of every financial year and not more than the applicable tariff for that year, will be applied for the duration of that particular financial year. The amount of the subsidy will be determined and approved as part of the tariff policy applicable for the financial year. Challenge is for all indigents to register on the indigent register and to verify compliance with policy.

6.	Property Rates

All registered destitute indigents shall be fully subsidized for the payment of property rates. All registered indigents shall be subsidized for the payment of property rates as determined and provided for by the Council in the annual budget from time to time. Depending on the availability of funds for this purpose a subsidy, determined at the beginning of every financial year and not more than the applicable tariff for that year, will be applied for the duration of that particular financial year. The amount of the subsidy will be determined and approved as part of the tariff policy applicable for the financial year. Challenge is for all indigents to register on the indigent register and to verify compliance with policy.

6.	ECONOMIC, SPATIAL AND ENVIRONMENTAL ANALYSIS

6.1	Economic Analysis

1.	The structure of the economy

The municipality is a major producer of citrus and table grapes. Cotton and vegetable production is also substantial. Cattle ownership among subsistence farmers is significant.

Production areas are scenically attractive and, together with the Flag Boshielo Dam, provide supply side opportunities for tourism development. The Schuinsdraai Nature Reserve, which is adjacent to Flag Boshielo Dam, adds to this opportunity.

Mining activity includes dolomite and dimension stone. Marble Hall town has a very large, but underutilized industrial park. The only manufacturer of note is McCains vegetable processing. Other tenants in the industrial park are mostly distributors and businesses that repair motor vehicles and other equipment.

The local construction industry is very small, but is growing rapidly. Wholesale and retail trade development has always been overshadowed by facilities that are available in the adjacent Groblersdal. A large network of informal traders operates throughout the municipal area.

Economically active persons = 2.7 (108113 unactive persons divided  by 39757 active persons)

2.	Key economic sectors

The  Municipality has a relatively small economy, contributing only 1% to the provincial value of production in 2006. It is more important within the Sekhukhune district context, where it contributed 14% to the value of production in 2006.

GGP per Sector for Greater Marble Hall at current prices for 2006 R’000

| Sector | Year 2005 | Year 2006 | Sector % 2006 | Growth 05-06 |
| --- | --- | --- | --- | --- |
| 1 Agriculture | 59,506 | 72,107 | 5.8 | 21.2 |
| 2 Mining | 130,618 | 155,817 | 12.5 | 19.3 |
| 3 Manufacturing | 50,637 | 56,811 | 4.6 | 12.2 |
| 4 Electricity | 32,955 | 38,976 | 3.1 | 18.3 |
| 5 Construction | 13,437 | 16,639 | 1.3 | 23.8 |
| 6 Trade | 139,259 | 157,007 | 12.6 | 12.7 |
| 7 Transport | 93,223 | 103,611 | 8.3 | 11.1 |
| 8 Finance | 225,444 | 272,885 | 21.9 | 21.0 |
| 9 Community services | 336,396 | 370,560 | 29.8 | 10.2 |
| Total Industries | 1,081,474 | 1,244,414 | 100.0 | 15.1 |
| Taxes less Subsidies on products | 171,372 | 202,254 |  |  |
| Total (Gross Domestic Product - GDP) | 1,252,846 | 1,446,668 |  |  |

Source: Global Insight 2008

3.	Development corridors

Zamenkomst – Rathoke – Malebitsa is seen as a future development corridor with the main growth point at Rathoke.

In a north/south direction, the main development corridor of the Greater Marble Hall area, is from Marble Hall to be along the N1 in an eastern direction to Leeuwfontein and then in a northern direction along road D4100, to Matseding. Road D4358 and from there along Road D3600 to Elandskraal and ending at Dichoeung in the north.

The main proposed east/west development corridor along Road D4285 (Tsimanyane South, Ragaphela, Mmolwaneng) along a priority link road to link up with settlements (for example Maseremule Park) in the adjacent Greater Tubatse Municipality, as well as provide linkage with the north/south corridor.

4.	Local Economic Development Projects (EULED,DPLG DTI)

4.1	The Limpopo LED approved a project amounting to R1 396 887 (R1 257 198) EU grant R139 689 Council 				contribution) to the municipality under the Local Government support fund to compile a feasibility study and business 			model for the proposed Marble Hall logistic hub. The business model is completed and implementing entity to be 			appointed during 2011.

4.2	DTI approved a project for organic farming amounting to R25 040 000 to be implemented over a period of 3 				years. Co-operatives with farms have been identified for implementation of the project and the payment received for 			the first year of R15 159 850 will be spent by 31 March 2011.The project will support more than  400 sustainable jobs 		and also impact on the livelihood amounting to at least 2800 people

5.	LED - Community needs – Ward visits : August 2010

| Ward 1 | 1.Driefontein – Dress making need shelter, Motlisi co-operative need fence and tank.2.Malebitsa – Letihabile need pump for borehole to water vegetables, Kgetolopele need water,tank and fence for (baking & vegetable) . Malebitsa home base care need funding. 3.Tlhakanang project(cleaning) need funding.4.Itosheng business plan submitted-need water ,borehole not working 5.Itereleng garden/refuse removal need funding/ assistance.6.Bambanane at Spitspunt – cotton project,need assistance 7.Cattle at Spitspunt(5000)fencing required for camps and rangers to look after fences(Dept of Forestry |
| --- | --- |
| Ward 2 | No need indicated |
| Ward 3 | 1.Mahlomola HBC at Uitvlugt require office,electricity,water and funds.2.Semunye at Uitvlugt require water and electricity(agr proj). 3.Kopanang hydrophonic farming at Keerom require water and borehole.4.Itsoseng environmental cleaning at Uitvlugt for recycling require office and funds.5.Phologang HBC at Keerom require office, electricity and funding.6.Tshitele Todi beekeeping at Keerom require office, water ,electricity and finance .7.Cleaning of dams at Keerom |

| Ward 4 | 1.Shopping mall required at Matlerekeng.2.Satelite bank required at Matlerekeng.3.Irrigation system required for agriculture projects. 4.Proper structure required for dipping of animals.5.Rebone bakery,Tsosanang poultry,Somang Ka Matla poultry& Abbato and Khentsane dairy need assistance/toilet.Ward committee identify interest groups to take forward.6.Moutse west co-op need 24hr operation and new pump for petrol,diesel and paraffin.Extend to cater for all farmers for tractors etc.(approach IDT/DBSA/SEDA) request LIBSA to assist with business plan |
| --- | --- |
| Ward 5 | 1.More projects required.2.Funding.training,management and monitoring of existing projects required. 3.Marble Hall town to be developed to create jobs.4.ATM required at KTT tavern Teffo. 5.Shopping complex required next to secondary school. |
| Ward 6 | 1.The on going state that the municipality has allowed the hawker stalls in Marble Hall town to deteriorate to, continues to present a problem, and the need for power connections to be reinstalled (after they where vandalised) and sanitation facilities which are non functional and in need of urgent attention. There is also an urgent need to immediately remove the unauthorised stalls now being erected within the complex.2.Replace the imitation thatch roofing of the hawker stalls in Railway street that have blown off. 3. To develop infrastructure near the waters edge in and around the Flag Boshielo Dam to be completed, so as to allow the town to host large fishing competitions presently being hosted in the province of Mpumalanga at the Loskop Dam. 4. The extension of the rail line from Siyabushwa to Marble Hall is in need of consideration in view of the proposed fresh export container depot in Marble Hall to Durban. |
| Ward 7 | Hawkers business stalls. |
| Ward 8 | 1.Moganyaka south- Diraolaetse concrete project require training – not functioning at present.2.Bakery – Phela-o-Phedise require assistance.3.Piggery project next to olifants river require assistance.4.Hlapi-ke-Bophelo pillow co-operative require assistance. 5.Medicine plants project require assistance.6.Home based care project require assistance |
| Ward 9 | 1.Ikageng Mamphokgo – Borehole for irrigation and office and toilets required.2.Baloyko FarmersYouth Mamphokgo - Borehole for irrigation and office required.3.Mmakgatle Diphiri land care project – Water for animals and office required. 4.Mantsosa bosego brick project – Water and office required.5.Mamokwale home base care – Office required.6.Mmatilo gardening project – Water and office required.7.Kodumela Trading co-operative(peanut butter) at Puleng require another borehole(present one blocked) and cultivate new bigger site(current field is small & yield less than harvest) |
| Ward 10 | 1.Fish and crocodile project to be developed.2.Employment to be created.3.Agricultural development of small scale farmers 4.Financial assistance required for Co-operatives.5.Selebaneng community project(vegetable garden) require water and soil preparation. |
| Ward 11 | 1.Cleaning of dams required in all villages.2.Irrigation systems required for crops.3.Disanyane dam to be fixed.4.Gamasha require dam for cattle and irrigation.5.Emerging farmers and emerging contractors need assistance.6.Madisa a Mathamaga Agric Co-operative at Rakgwadi(poultry) require fencing, erection of chicken pans, electricity and water. |
| Ward 12 | 1.Irrigation schemes approved to be implemented and fenced (check with Dept.Agr.) 2.Communial farming land to be established at Mohlotsi 440 h/a and underground water and fencing required 3.Dams need to be cleaned for drinking water for cattle. 4.Cattle pen for dipping at Tsimanyane ,Mogalatsane,Letebejane and Mohlotsi to be upgraded and Stand for cattle auction to be build.5.Shopping complex required at Matseding.6.Ditholong require farm for cattle but not in ploughing fields.7.Grazing camps for cattle required in each village.8.Phakane garden project at Phetwane require fencing,soil to be tested,water and electricity. |
| Ward 13 | Need for funding of Elandskraal Irrigation Balimi Scheme (EBIS), Siyaya Dairy Project, Elandskraal Bricks Making, Elandskraal Glassing Project, Kodumela Poultry Project, Morarela project and Mbuzini project.Need to establish internet tele centre at Elandskraal |
| Ward 14 | 1.Youth development for sustainable jobs.2.Itsosheng gardening –Regae: Need water, tank to store water & toilet.3.Phuthanang brick making – Regae: Need borehole & pump, vehicle, reservoirmachinery for brickmaking, shelter for storing bricks & slab.4.Etsosheng Batsofadi-Dichoeung: cultural activities need funding and old age centre.5.Ekageng Bakone Bakery-Dichoeung: Need funds for building, ovens and vehicle.6.Phuthitsoga poultry and vegetables- Regae: Need marketing ,financial skills and borehole.7.Lehlabile Bakery – Regae: Require building, generator and vehicle.8.Momang disabled project vegetables/sewing at Regae require financial assistance 9.Marketing and skills development required for all projects.10.Shopping complex plaza required at Regae to include ATM and filling station, |

6.	Competitive and comparative advantages

The municipality is designated a “provincial growth point” and is regarded as one of Limpopo’s more economically developed local municipalities.

Municipal area makes a significant contribution to the District GGP, mainly from public sector, agriculture, agro-processing, wholesale and retail, trade, services and transport, storage and communication sectors. According to STATS SA 2001 census, agriculture is the largest contributor to employment, followed by the public sector, private households, wholesale and trade.

The local conditions (business environment) in which the local business operate from provides comparative advantage and disadvantages, favouring certain types of industry sectors. The municipality boasts a pleasant climate, particularly suitable for table grapes and citrus. Fertile soils, large dams and irrigation provide comparative advantage for production of a variety of crops and livestock.

Municipality has limited mineral deposits, mainly marble and lime.

The best natural tourism attractions are the Flag Boshielo Dam and the adjacent Schuinsdraai Nature Reserve, which are not yet utilized or developed as major tourist attractions.

The municipality has well serviced transport routes in comparison to the rest of the province

The existing tourism sector has grown around business visitors, a few game lodges and agricultural educational tours.

7.	Local constraints to growth

The municipality remains dependent on fiscal allocations from outside the province. The municipality’s annual budget is over R 180 million, of which R 127 million is raised within the municipality. Within the municipality 15,664 economically active people are required to support over 100,000 economically un-active people (2001 figures), a statistic that exposes the extent of under-development and dependency.

Land ownership is the single biggest constraint to economic growth in the rural areas. The land issue permeates as a constraint through all sectors - from commercial level investment to undermining the scale and viability of emerging farmers and capital appreciation of property values for everyone living in the area. The current regulatory system creates investment uncertainty and slows or blocks the process of investment.

8.	State of local skills

The state of the local skills are indicated in the table below and is based on 33514 economically active persons.

| Highest Educational Level | Persons |
| --- | --- |
| No Schooling | 9383 |
| Some Primary | 6367 |
| Complete Primary | 2345 |
| Some Secondary | 8378 |
| St. 10 (Grade 12) | 4021 |
| Higher | 2345 |
| Illiteracy Rate | Percentage |
| All Ages | 17.3% |

Source: Global Insight, 2008

The challenges is to obtain the necessary funds from sectors to capacitate those without skills and the advantages is the availability of 		the Agricultural college and LIBSA  in the municipality to train unskilled labor.

9.	Job creation

Following table indicates jobs created in the municipalities through LED  initiatives from 2007.

| Project | Jobs created |  |  |
| --- | --- | --- | --- |
|  | Men | Woman | Youth |
| Water reticulation | 303 | 321 | 426 |
| Mast lights | 30 | 40 | 55 |
| SLASH(fertilizer) | 3 | 5 | 2 |
| Brick paving manufacturing | 7 | 8 | 5 |
| Sports stadiums /community halls | 38 | 45 | 17 |
| Bakery and piggery | 2 | 8 |  |
| Beadmaking jewelery |  | 8 | 7 |
| Tar roads and storm water | 280 | 310 | 352 |
| Egg production |  | 20 | 5 |

10.	Conclusion

Marble Hall is a relatively small economy with a predominantly rural character. The general impression is that physical and social infrastructure, as well as service delivery standards, are inadequate to provide the platform that is required for accelerated economic growth and job creation.

LED strategy was approved on 25 June 2008 and proposals to improve the rate of economic development and the quality of life of the citizens of Marble Hall Municipality is Service  Delivery Improvements, Horticulture Cluster Promotion, Meat Cluster Promotion ,Tourism Cluster Development and Informal Economy Support.

6.2	Spatial Analysis

1.	Settlement patterns

The configuration of the municipal area and the existing spatial pattern (topography, population distribution, sprawl) together with causal factors (land ownership, established land uses) are impediments to the successful implementation of a Development Strategy to achieve the four developmental outcomes proposed in the White Paper on Local Government.

Restricted access to land by the Municipality due to inhibitive land cost (privately owned land) and statutory deterrents (state – owned land under tribal custodianship) would exacerbate attempts by the Council to orchestrate and encourage the development of a beneficial spatial pattern within the municipal area.

The settlement hierarchy of the municipality is as follows:

1.1	First Order Settlements (Growth Points) [GP]

Growth points are further divided into three categories,  viz.

Provincial growth Point [PGP];

District Growth Point {DGP]; and

Municipal growth Point [MGP].

1.2	Second order Settlements (Population Concentration points) [PCP]

1.3	Third Order Settlements (Local Service Points) [LSP]

1.4.	Fourth Order Settlements (Village Service Areas) [VSA]

1.5	Fifth Order Settlements (Remaining Service Areas) [SS]

2.	Land use

Urban Sprawl - The fragmented and spread out nature of the urban component has caused inefficient provision of basic services and hinders the creation of a core urban complex, which is essential for a healthy spatial pattern.

High Potential Agricultural Land – the most central area of the municipality can be regarded as high potential agricultural land (irrigation) which will indefinite contribute towards a division of the area.  It is imperative that this resource be protected for the economic well being of the area.

Other Land Uses – The existing 2 lime mines and mineral rights directly to the east of Marble Hall limits eastwards extension of the township.

3.	Land use management

The main challenge is that sector departments have certain mandates on land development e.g. Subdivision of agricultural land, environmental impact assessment, roads and ribbon development as well as land claims that the LUMS will have to contend with.

The Flag Boshielo Dam which can provide supply side opportunities for tourism development. The Schuinsdraai Nature Reserve, which is adjacent to Flag Boshielo Dam, adds to this opportunity. Further opportunity is the industrial land available in Marble Hall town which is in ownership of the municipality.

Economic development projects can be established as follows:

1.Eco tourism  - Flag Boshielo  : Community land Ghoshi Matlatla

2.Industries – Marble Hall town : Council owned land

Conflict of laws – Municipal Systems Act, vs. the Ordinance 15 of 1986, vs. the Development Facilitation Act, Proclamation R188 and R293.

Weak enforcement: In urban areas slightly better although the springing of informal settlements attests to this point- Rural areas – left to the goodwill of traditional leaders. They too did not have a legal leg to stand on.

Municipality does not have a dedicated workforce of law enforcement.

The cost of managing land use would be more expensive than the returns thereof. It is not a fund generating exercise.

Weak interface among land use management and other programmes of government like agricultural development, environment, mining, roads and transport etc.

Rural areas whilst divided into farms do not have plans for settlements which make zoning complicated.

Whilst different acts allude to schemes of the municipality there is no interface. National and Provincial departments are still continuing to render services that are supposed to be rendered by the municipality.

Delineation of zones is complicated by lack of property surveyed boundaries.

Existing structures old and new need to be streamlined to play an active role in land management.

Simmering tension on powers and functions between municipality & traditional leadership.

New councillor not properly orientated towards land use management issues.

Municipality administer different system and schemes based on previous policies ( pre- democracy era)

Some areas do not have maps as mapping was done for specific programmes.

Draft LUMS have been compiled by service provider appointed by GSDM and the new system should address the above defects and ensure that a new system gains support from communities and business people alike.

4.	Recent trends

A relatively large municipal land area extending approximately 1 911km²;

A fragmented residential component consisting of 4 formal towns, 21 semi formal villages, 31 rural villages and 18 scattered villages.  Therefore 42% of the settlement areas are rural;

Two (2) significant clusters of villages, one to west of Marble Hall and one to the north and east of Marble Hall;

A clear distinction between high and low potential agricultural land being utilized for intensive or extensive agricultural activities;

Significant area of land owned by the state under custodianship of Tribal and or Traditional authorities, as well as private owned land;

Environmental sensitive areas mainly along stream areas.

5.	Land issues may lead to future social tensions

Simmering tension on powers and functions between municipality & traditional leadership.

6.3	Climate and Environmental Analysis

1.	Climate

The average temperatures show moderate fluctuation with average summer temperature 23°C, with a maximum of 28°C and a minimum of 18°C. In winter the average is 13,5°C with a maximum of 20°C and a minimum of 7°C as measured at the Sekhukhuneland Weather Station.

2.	Geology

The south-western part of the municipal area is underlain by the acid and intermediate intrusive rocks of the Waterberg Group, as well as small areas of mafic and ultramafic formations.  The western portion is underlain by extensive Karoo Supergroup formations, principally basalts of the Lebombo Group and Clarens Formation sandstones, with smaller areas of Ecca Group shales, siltstones and mudstones.  The central and eastern portions are underlain by a variety of rocks of the Bushveld igneous Complex.  The most important of these are the Lebowa Granite suite, with outcrops of the Rashoop Granophyre Suite, followed by rocks of the Rustenburg Layered Suite further to the north and east.  Much of the northern part of the area is underlain by rocks of the Transvaal Sequence, with the silicified sandstones and quartzites of the Black Reef Quartzite Formation being very prominent, together with Chuniespoort dolomites and Pretoria group shales, hornfels and quartzites.

According to Soils occurring in the municipal area can be divided into the following groups:

In the west: Shallow to moderately deep sandy-clay loam soils on flat and undulating terrain overlying rocks of the Ecca Group, principally shales and silicified sandstones;

In the east: Deep, black, blocky vertisols of the Springbok Flats;

Moderate to deep sandy loam soils lining long stretches of the Olifants River valley in its middle reaches.

Most of the soils are suitable for commercial agriculture when sufficient water is available.  Virtually all of the areas with suitable soils, particularly the area downstream of the Loskop and Flag Boshielo dams, are contained within the jurisdiction of formal irrigation boards or Government Water Control Areas.  Further away from the main river channels, land use is given over to small- and medium-scale livestock farming operations.  A relatively wide variety of crops are produced on the irrigated and rain-fed areas, primarily maize, wheat, sorghum, cotton, tobacco, lucerne, potatoes, vegetables, sunflowers and soya bean.

3.	Topography

To the south-west of the municipal area the Olifants River is located on an open floodplain area and to the north the river is 	located in a valley surrounded by the Strydpoort Mountains (parallel hills and lowlands).

Strips of erosion can be found in the valleys alongside most of the perennial and non-perennial rivers.

4.	Water scarcity

4.1 Water

Due to the predominantly rural character of the municipality’s area of jurisdiction there is no bulk water provided in most of the villages in Moutse west . Water is provided by means of water tanker trucks and boreholes. Provision has been made for bulk reticulation and cost recovery in Moutse to be implemented in  2011/12 according to water sector program, PGDS  targets.

One very large impoundment on the Olifants River, the Flag Boshielo (Arabie) Dam, provides water supplies to numerous small towns and settlements in the sub-catchment, as well as large volumes of water for irrigation schemes along both banks of the Olifants River.  Nine other medium-sized dams are also located in this sub-catchment and supply water for domestic use and for irrigation.  Many of the mines and industries in this sub-catchment, as well as numerous small and large settlements, rely on water supplied from these ten dams, or use local boreholes or direct run-of-river abstraction from perennial rivers and streams.  There are also over 500 small farm dams located in this sub-catchment and these trap water for domestic purposes and for limited areas of small-scale irrigation, as well as livestock watering.

4.2 Water pollution

The following activities can be expected to have an impact on water resources in the Middle Olifants sub-catchment:

- Landfills and solid waste disposal sites at all towns and larger settlements;

- Disposal of liquid (domestic, light and heavy industrial) effluent at all towns;

- Moderate volumes of runoff from towns, as well as all other urbanized areas;

- Non-point domestic effluent from numerous small settlements and farms;

- Minor non-point impact from non-intensive commercial or subsistence agriculture;

- Non-point impact of agricultural return flows from intensive irrigation areas; and

- Litter and domestic garbage discarded alongside the many roads that traverse the sub-catchment.

5.	 Air quality and pollution

Air pollution resulting from the use of fire wood for energy purposes and dust from gravel roads have also been identified as environmental problems (albeit with a lower significance) Burning of tyres adjacent to potato fields ,OTK in and around Marble hall.

6.	 Surface pollution

Surface pollution is caused by the spraying of crops with pesticides

The challenges for the above is the capacity to prevent pollution

7.		SOCIAL ANALYSIS

7.1	Education

The following table indicates the education facilities available in the municipality

Available education facilities

| Ward | Pre-primary | Primary | Secondary |
| --- | --- | --- | --- |
| 1 | 7 | 4 | 2 |
| 2 | 7 | 9 | 3 |
| 3 | 3 | 3 | 2 |
| 4 | 4 | 3 | 2 |
| 5 | 2 | 3 | 1 |
| 6 | 3 | 2 |  |
| 7 | 3 | 2 | 1 |
| 8 | 4 | 2 | 1 |
| 9 | 3 | 5 | 4 |
| 10 | 6 | 12 | 7 |
| 11 | 1 | 8 | 5 |
| 12 | 5 | 6 | 5 |
| 13 | 3 | 5 | 2 |
| 14 | 3 | 3 | 2 |
| Total | 54 | 66 | 38 |

7.1.1	Education Backlog – Ward visits : August 2010

| Ward 1 | High school - Spitspunt |
| --- | --- |
| Ward 2 | Temporary classes for Refiloe ss at Doornlaagte |
| Ward 3 | 1.Refiloe high school to be relocated to Keerom/Doornlaagte. 2.Good buildings for pre school education required Keerom(1) and Uitvlugt(1) . 3.Admin blocks required at Metsanangwana PS and Makalakanye PS. |
| Ward 4 | 1.New Primary school required at Rathoke new stands.2.New primary school at Matlerekeng(Rooikop) has been completed 3.Fully fledged admin blocks required at all schools.4.Five classrooms and roofing of 3 rooms required at Ramgohu crèche at Rathoke as well as Matlerekeng creche.5.Disaster at Rathoke primary, 2 block classrooms required.6.Ramogohu primary school require 1 block classrooms.7.Mbake school require electric pump for borehole.8.Raphogile H/S require Library and laboritry flushing toilet with borehole. |
| Ward 5 | 1.Mashung school require admin block,scholar patrol signs over main road and speed humps on road.(maintenance/infrastructure to be done from budget allocated to school).2,Mahlakodisha school require computer room.(maintenance/infrastructure to be done from budget allocated to school).3.New primary school required next to community hall(technical/tersiary) 4.Creche required –social services(forms to be completed & submitted urgently) |
| Ward 6 | No need indicated |
| Ward 7 | Skills development centre required |
| Ward 8 | 1.New primary and high school required at Leeuwfontein RDP.2.3 blocks c/rooms and renovation required at Manokwena sec ,admin block and furniture at Goshetseng prim at Moganyaka north.2.New primary school required at Manapyane ext. and Moganyaka north. 3.Moganyaka north pr sch require 2 blocks for classrooms and water.4.Library,laboritry,paving,lawns,caretaker,cleaning gardens,security renovating and proper toilets required at all schools except the 2 schools mentioned in two above . 5.Fully fledged Technicon for multi skills training required for the ward.6.Bursaries required for school leavers. 7.ELC required at Manpyane |
| Ward 9 | Creches required in all villages |
| Ward 10 | 1.ELC /Creche required in ward.2.Dissabillity centre required.3.Pedestrian crossing at schools required |
| Ward 11 | 1.Frischgewaght-primary 1 block c/rms and toilets required.2.Mathukhutela-Kgopolobotse prm.toilets required. 3.Disanyane-Ngwanasenana prm.1 block required.4.Manotolwaneng-Morerichoenyane sec.1 block & toilets required 5.Makwetla sec.toilets required.6.Following schools are not electrified: (1) Gareagopola – Gareagopola (2)Disanyane – Makwetle and Ngwanasenana. (3)Mathukhuthela – Kgopolo-E-Bojse and Mpitsa.7.Manotolwaneng – Nteteleng pr. require toilets.Creche need one block 8.Ga-Masha – Katisa pr. require one block and toilets.9.Rakgwadi – Ngwanamashile sec require one block and toilets 10.Rakgwadi – Rakgoadi pr. require crèche.11.Moomane require toilets and renovation roof 12.Swaranang crèche toilets and one block required.13.Moomane sec require toilets |
| Ward 12 | 1.Mohlotsi sch is dilapidated and require renovation.2.New primary sch required at Ditholong/Mooihoek.3.Mooihoek sec sch require additional one block.4.Admin block required at some schools except Letebejane pr sch.5.Libraries and laboritries required at all schools 6.Phetwane-Mogoma Matlala high need upgrade of fence.7.Toilets at all schools are not up to standard and need upgrade. 8.Mogalatsane sec need renovation.9.Tsimanyane pr. require sports field as well as all other schools.10.Tsimanyane circuit require new building.11.Kotole high sch at Ditholong need 1 block c/rooms.12.Secondary school required at Matseding. 13.Primary school Letebejane/Ditholong/Mooihoek crossing change for humps |
| Ward 13 | 1. Need for FET College at KOKA SHOPING CENTRE.2.Need for ABET Centre |
| Ward 14 | 1.Dichoeung-Lewelery Matlala high: Require 1 admin block, Laboratory , store room, sports ground and library .Primary school need admin block.2.Regae- primary require 10 c/rms, new furniture, strong room for computers, funding for school projects, new site for pre-school and security & high school need admin blocks, roofing renovations and furniture.3.Shilela Creche-Dichoeung: New building to be completed. 4.Two crèches at Regae (Bauba/Hunani Gobetse) require funding.5.New building required for pre-school at Ditchoeung 6.ECD cenrtre’s required in both villages .7.Regae – Mohlahlane pr sch need media centre, laboratory, admin block, electricity for one block, sports ground, security guards. borehole for vegetable project, new furniture , trenches for pipes to be dug with TLB and 6 toilets. Structure for pre-sch/creche and fencing.8.Regae – Majatladi sec. need 16 toilets, computer center, sports ground, borehole and security 9.Allschools need renovations |

7.2	Health and Social Development

The following table indicates the Health facilities available in the municipality.

1.Health facilities

| Facility | Standard Per households | Number of Households | Existing Nr |
| --- | --- | --- | --- |
| Hospital | 1 : 10 000 | 31971 | 1 |
| Health Centre | 1 : 5 000 | 31971 | 2 |
| Clinic | 1 : 2 000 | 31971 | 11 |
| Mobile Clinics | 1 : 2 000 | 31971 | 28 |

1.1	Backlog – Ward visits : August 2010

| Ward 1 | Clinic - Malebitsa |
| --- | --- |
| Ward 2 | Clinic – Mokgwaneng and Doornlaagte |
| Ward 3 | 1.Require staff-clerks, medicine and budget at Keerom clinic.2.Require mobile clinic at Uitvlugt. |
| Ward 4 | 1.Clinic at Rathoke required to be upgraded to 24 hour service with nurses home plus toilets. 2.24 hour clinic/hospice required for Matlerekeng – Uncedo woman development group to be checked |
| Ward 5 | 1.24 hr operation of clinic required and nurses home to be extended.2.Need 4 additional professional nurses 3.Security fence to be replaced. Very old. |
| Ward 6 | 1.The re-establishment and refurbishing of EMS as contained in the document forwarded to the MEC of the Provincial Treasury by Sakekamer. 2.Require that the present clinic be upgraded, and that the health authorities concentrate on making the rural clinic’s operational and not allowing them to go on as they please, with poor service and poor stock levels being the order of the day, hence the result, whereby the non residence come to Marble Hall for service. If this Municipality, has any intention of offering a 24 hour service they will have to locate competent staff to run the facility first, failing which, they will have the same problem being experienced at the new facility at Keerom which was planned as a 24hr facility which stands unused to date due to the lack of competent staff? A prime example of the availability of competent staff can be seen at the old age home in Marble Hall where the present competent staff have all passed retirement age due to the shortage.3. Urgent need for an extension to be made to the M/Hall clinic, to house an ARV clinic. At present the clinic is not suited to offer this facility due to the complete lack of privacy and confidentiality and the lack of the correct ARV medical supplies.At present HIV sufferers must go to G/Dal for medical supplies and treatment.It should be noted that the present clinic building is owned by the Municipality, even though the service is offered from it, are that of National Government 4. The establishment of an eye clinic operating from the present site of the clinic on a once a month basis initially to service the 70 registered diabetics apart from other eye ailments. At present all eye problems are revered to G/Dal hospital, most of these referral patients at present, due to the excess transport costs involved, ignore the instruction, thus aggravating the problem. 5. It has been established that the offices for the two mobile clinics situated in Marble Hall are placed some 42km and 22km away from Marble Hall respectively. Surely common sense suggests that offices should be made available in Marble Hall to avoid these vehicles having to travel excessive mileages so as to allow the staff to complete their work |
| Ward 7 | No need indicated |
| Ward 8 | 1.Mobile clinics required at Manapyane,Moganyaka south and Leeuwfontein RDP housing village.2.Home based care require structure. 3.Drop in centre require structure |
| Ward 9 | Clinics required at Mamphogko ,Magatle & Matilu |
| Ward 10 | Clinic required at Ngwalemong “A” and Greenside |
| Ward 11 | Gareagapola require Health centre for 24 hour service |
| Ward 12 | 1.New clinic required at Matseding.2.Structures required for mobile clinics and mobile stop in each village not less than 5km. 3.Mogalatsane need clinic |
| Ward 13 | Need daily Mobile Clinic @ Morarela and Mbuzini |
| Ward 14 | 1.New Clinic required at Ditchoeung.2.More land required at Van der Merweskraal clinic for nurses home & other health matters including store room.3.Home based care building required at Regae |

2. Accessibility and other issues

33% of the communities are within 20km from hospitals and 67% outside 20km

47% of the communities have access to clinics within 5km and the majority (53%) is more than 5km away from clinics

3. Social welfare

Available Welfare Facilities and Services

| Ward | Old age home | Child care | Disabled | Pension pay point | Services points |
| --- | --- | --- | --- | --- | --- |
| 1 | 0 | 0 | 0 | 3 | 1 |
| 2 | 0 | 0 | 0 | 4 | 2 |
| 3 | 0 | 0 | 0 | 0 | 0 |
| 4 | 0 | 0 | 0 | 2 | 2 |
| 5 | 0 | 0 | 0 | 1 | 1 |
| 6 | 1 | 0 | 0 | 1 | 3 |
| 7 | 0 | 0 | 0 | 1 | 1 |
| 8 | 0 | 0 | 0 | 2 | 2 |
| 9 | 0 | 0 | 0 | 4 | 0 |
| 10 | 0 | 0 | 0 | 6 | 0 |
| 11 | 0 | 0 | 0 | 5 | 0 |
| 12 | 0 | 0 | 0 | 7 | 0 |
| 13 | 0 | 0 | 1 | 3 | 2 |
| 14 | 0 | 0 | 0 | 2 | 2 |
| Total | 1 | 0 | 1 | 43 | 16 |

3.1	BACKLOG – Ward visits August 2010

| Ward 1 | Shelters for pensioners - Driefontein |
| --- | --- |
| Ward 2 | Facility for day care centre at Doornlaagte required(Phafogang day care centre letter 20/9/10) |
| Ward 3 | 1.Pension halls required at Keerom and Uitvlugt to be used as paypoints 2.Home based care – offices, training and funds required for both villages |
| Ward 4 | No need indicated |
| Ward 5 | Home based carrers require offices urgently next to Mashung primary school |
| Ward 6 | No need indicated |
| Ward 7 | No need indicated |
| Ward 8 | 1.Paypoint required at Moganyaka south.2.Social security office required in ward(Leeuwfontein).3.Home base care require assistance |
| Ward 9 | Shelters required for pension paypoints |
| Ward 10 | 1.Shelters and toilets required in the interim for pension paypoints with Serething to be first. 2.Pension paypoints required for Makhutso and Makgatle. 3. Drop in centre require building and support at Mabitsi”B” |
| Ward 11 | 1.Shelters required for paypoints in all villages.2.Ga-Masha and Manotoloaneng(1 at tribal office and 1 at Moshitwa) require paypoints. |
| Ward 12 | 1.Paypoints needs structures and toilets,water and chairs(Dept of Health to check old people blood pressure ect. 2.Paypoint required at Matseding |
| Ward 13 | 1.Need for Dropping Centre @ Morarela and Mbuzini.2.Need for Orphanage and Old Age Centre @ Morarela and Mbuzini 3.Upgrading of Elandskraal Lethabong Centre.4.Upgrading of Eandskraal Disable Centre. |
| Ward 14 | Old age home and disability centre required at Regae |

The challenges in respect of the above is to provide  facilities for the pensioners at the pay points.

7.3	HIV/AIDS

The municipality implemented the decentralised response to HIV & AIDS, having joined the CMRA support project in June 2007 as the 7th pilot site. The objectives of the municipality project were: (a) to establish an Interdepartmental Forum (IDF) on HIV & AIDS with a clear objective, mandate and responsibility, coordination body and budget (earmarked from the various departments) and well embedded in the IDP in order to increase the service delivery to the community related to HIV & AIDS issues and (b) to advise the municipality in how to establish and/strengthen the Local Aids Council (LAC) – the multisectoral municipal HIV & AIDS platform involving all stakeholders (governmental and non-governmental) in the field of HIV & AIDS to address the problem of HIV & AIDS from the local level in a coordinated and effective way, broaden the scope of the spin off and avoid unnecessary overlaps.

The IDF members have been identified. Preparation of departmental action plans on HIV & AIDS has been compiled. There is a good understanding among IDF members about the role of the IDF. The LAC had been established.

The project has already contributed significantly to raising awareness in the municipality with regard to mainstreaming of HIV & AIDS.

HIV & AIDS are rife, with a prevalence rate of 16.7% in 2006. Limited access to basic services, unemployment, poverty and lack of access to primary health care due to the vastness and rural nature of the Municipality are some of the risk factors that affect the spread of HIV & AIDS.

It is crucial that an HIV & AIDS Coordinator be appointed who will anchor the programme within the municipality and champion the work of the IDF and LAC. The CMRA Project Coordinator should be working hand-in-hand with this person to impart valuable skills and experience to ensure sustainability. Resources (material and human) should be made available to support the activities of the LAC.

The challenges for the above is to allocate budget for programs

Community needs :

| Ward 4 | 1. Hospice facilities required and funds be allocated by the district 2..Funds required for HIV/AIDS program 3.Office required for Home Based Care |
| --- | --- |

7.4	Safety and Security

The following table indicates the facilities available in respect of police stations in the municipality.					Police and Magisterial Services Rendered

| Ward | Former TLC | Location | #### Facility |
| --- | --- | --- | --- |
| 1,2,3 & 5 | Moutsé 1 |  | No Police station (Main PS in Dennilton and satellite in Matlerekeng) |
| 4 | Moutsé 1 | Matlerekeng | Satellite Police Station with 16 personnel |
| 6 | Marble Hall | Marble Hall | Police Station with cells and courtroom.6 Private Security Services. |
| 7 | Moganyaka/Leeuwfontein | Moganyaka/Leeuwfontein | No formal and local services. |
| 8 | Moganyaka/Leeuwfontein | Manapyane/Moganyaka | No formal and local services. |
| 9 | Hlogotlou/Lepelle |  | No formal and local services. |
| 10 | Hlogotlou/Lepelle |  | No formal and local services. |
| 11 | Hlogotlou/Lepelle/Nebo |  | Satelite Police Station at Rakgwadi |
| 12 | Hlogotlou/Lepelle |  | No local Police Station |
| 13 | Middle Lepelle | Elandskraal | Police Station at Elandskraal |
| 14 | Middle Lepelle |  | No formal local services. |

7.4.1	Backlog – Ward visits : August 2010

| Ward 1 | No need indicated |
| --- | --- |
| Ward 2 | Bareki Police station |
| Ward 3 | No need indicated |
| Ward 4 | 1. Require fully fledged police station that operate 24 hours.2.Traffic signs required i.e.stop etc. 3.Satelite traffic/court required at Matlerekeng 4.Traffic signs required at schools for pedestrian crossing and speed humps and scholar patrols(traffic dept.be requested to assist ) |
| Ward 5 | 1.CPF to be launched 2.Security from SAPS or security institutions required to patrol area. |
| Ward 6 | 1.The need for the urgent refurbishing of the existing fire fighting equipment including the fire tender as per the detailed document forwarded to the MEC for Provincial Treasury, a copy which is available on request. 2. Fire hydrants in Marble Hall town to be serviced/repaired where they have been knocked over, painted and recorded by GPS reading of their location 3. In view of the development of the Schuinsdraai Nature Reserve the need for land and water policing needs to be considered. |
| Ward 7 | Change police jurisdiction area from Motetema to Marble Hall |
| Ward 8 | Satelite police station required in the ward to fall under Marble Hall jurisdiction |
| Ward 9 | No need indicated |
| Ward 10 | Satelite police station required at Mabitsi B |
| Ward 11 | Form CPF for crime prevention |
| Ward 12 | Police station to be established at Matseding |
| Ward 13 | Need Upgrading of Elandsraal Police Station ( Councillor and IDP Manager must write letter to the M.E.C for safety find about the progress) |
| Ward 14 | No need indicated |

The challenges in respect of above is to move the Marble Hall police jurisdiction to include the area outside Marble Hall police 					jurisdiction.

7.5	Sports, Arts and Culture

1.Sports and recreation

The table below indicates the sports and recreation facilities available in the municipality as well as backlog

| Ward |  |  |  |
| --- | --- | --- | --- |
|  | Formal | Informal | General status |
| 1 | 1 | 3 | Sport & Recreational Facility for Malebitsa completed. |
| 2 | 0 | 4 | Informal Soccer and Netball fields.Poor quality fields. Insufficient number and variety of sport and recreational facilities. |
| 3 | 0 | 2 |  |
| 4 | 0 | 2 |  |
| 5 | 0 | 2 |  |
| 6 | 4 | 0 | Mining Sport Club.Golf course.Tennis Courts.Sport fields at Primary School |
| 7 | 0 | 3 | 1 soccer field.1 softball field.1 netball field.1 boxing club.1 music club |
| 8 | 0 | 13 | 6 soccer fields.7 netball fields |
| 9 | 0 | 7 | 7 soccer fields.Netball fields at schools |
| 10 | 0 | 10 | No formal sport grounds exist |
| 11 | 0 | 5 | 5 Soccer fields.No specific information |
| 12 | 1 | 12 | 11 soccer fields & netball field |
| 13 | 1 | 3 | New formal facility completed |
| 14 | 0 | 4 | 3 soccer fields & netball field |
| Total | 4 | 67 |  |

7.5.1	Backlog – Ward visits : August 2010

| Ward 1 | Malebitsa stadium phase 3 |
| --- | --- |
| Ward 2 | Sports ground outside Mokgwaneng community hall |
| Ward 3 | Sports/Recreation centre required on the land available between Keerom and Uitvlugt |
| Ward 4 | 1.Indoor sports centre required at Rathoke.2.Sport facility required at MPCC at Matlerekeng |
| Ward 5 | Grading of sports grounds |
| Ward 6 | 1.The need for existing parks, and playgrounds to be upgraded and beautified made serviceable and safe. New parks need to be considered and develop.2.The repair and maintenance of the existing tennis courts is in need of attention.3.With the purpose of maintaining the health of the committee the consideration should be given to the design of a cycle track through town and suburban areas.4.Repair the damaged brick flower beds in government square so as to be able to take new plants. |
| Ward 7 | Multi purpose recreational facility with sports fields required |
| Ward 8 | 1.Mini staduim required for the ward.2.Need upgrade of all sports fields,fencing,facilities for indigenous games and base ball 3.Establishment of museum to be considered(Look at possibility to establish at Schuinsdraai nature reserve) |
| Ward 9 | 1.Mini stadium required at Mabitsi A.2.Maintenance of sports fields in all villages and schools required |
| Ward 10 | Grading of sports fields required |
| Ward 11 | Grading of sports fields required |
| Ward 12 | 1.Every village requires sports fields and upgrading of soccer fields plus associated equipment.2.Sports centre required at Matseding |
| Ward 13 | 1.Security needed at Elandskraal Stadium.2.Need for Third Phase of Stadium Upgrading Need for toilets proper, design of pitch lights and additional high mast light @ all pitch grounds.Need for creating grand stand for other sports codes and lights.3.Grading of all COMMUNITY SPORTS GROUNDS (Mbuzini,Morarela and Elandskraal) 4.Need for Elandskraal Recreation Centre |
| Ward 14 | 1.School sports grounds to be graded 2.Grader required for soccer fields.3.Staduim and Multi purpose sports centre required at Regae.4.Facilities required for all codes in all villages |

The challenges for the above is the lack of capacity to maintain sports and recreation facilities

2. Community centers

The table below indicates the community centers  available in the municipality as well as backlog

| Ward | Community hall | Multi purpose centre | Tribal hall |
| --- | --- | --- | --- |
| 1 | 1 | 0 | 0 |
| 2 | 2 | 0 | 0 |
| 3 | 0 | 0 | 0 |
| 4 | 0 | 0 | 1 |
| 5 | 1 | 0 | 1 |
| 6 | 1 | 0 | 0 |
| 7 | 1 | 1 | 0 |
| 8 | 1 | 0 | 1 |
| 9 | 0 | 0 | 0 |
| 10 | 0 | 0 | 0 |
| 11 | 0 | 0 | 1 |
| 12 | 0 | 1 | 0 |
| 13 | 0 | 1 | 0 |
| 14 | 1 | 0 | 1 |
| Total | 8 | 3 | 6 |

2.1	Backlog – Ward visits August 2010

| Ward 1 | Community hall Spitspunt |
| --- | --- |
| Ward 2 | 1.Mokgwaneng completion of Hall – running water, waterborne toilet and equipment 2.Klopper community hall |
| Ward 3 | Renovation of hall at Keerom |
| Ward 4 | No need indicated |
| Ward 5 | No need indicated |
| Ward 6 | No need indicated |
| Ward 7 | Caretaker and security guard required at Community hall |
| Ward 8 | 1.Manapyane Hall-fix roof leak(priority)need furniture urgently,change room,kitchen facilities,fix fence,fix roof leak,toilet upgrade,security, recreation facilities, electrical maintanence and cleaning of hall.Check social security for funding. 2.Community hall required at Moganyaka North |
| Ward 9 | No need indicated |
| Ward 10 | 1.Library/MPCC required for Mabitsi B.2.All villages with paypoints require Halls in following priority sequence: Selebaneng Serething,Vaalbank,Mmatwaneng, ,Greenside,Mabitsi A and,Ngwalemong-S.A.Social security agents be approached for funding. |
| Ward 11 | Community hall required in all villages |
| Ward 12 | 1.MPCC at Tsimanyane-2 of the 3 rooms do not have electricity(wiring to be checked!!!!)Need two more blocks-1 for hall and the other to house other departments.2. Halls required at Letebejane,Matseding and Phetwane. |
| Ward 13 | No need indicated |
| Ward 14 | 1.MPCC required for Regae which include Library.2. Regae community hall to be enlarged to build a stage and toilets to be upgraded(ceptic tank to small and VIP toilet not up to standard).3. The satellite office at Regae to be transferred to the municipality in order that cashiers can work twice a week to receive service fees from the community |

The challenges for the above is the lack of capacity to maintain the centers

7.6	Post Offices and communication

The table below indicates postal facilities available in the municipality as well as backlog

| Ward | Location | Facility/Service |
| --- | --- | --- |
| 1 | Driefontein Spitspunt Malebitsa | No Post Boxes. Collection Point with 800 Post boxes – 520 vacant. Post Office in Dennilton |
| 2 | Mmakola | Collection Point with 800 Post boxes – 421 vacant. .Post Office in Dennilton |
| 3 | Metsanangwana | Collection Point with 800 Post boxes – 220 vacant..Post Office in Dennilton |
| 4 | Rathoke | Postal Agent – Only boxes in Uitvlught.Post Office in Dennilton |
| 5 | Matlala | Collection Point with 800 Post boxes – 490 vacant.Post Office in Dennilton |
| 6 | Marble Hall | Main Post Office – service collection points in region.Private Courier services (2 locality stationed) |
| 7 | Moganyaka | Post office in Leeuwfontein |
| 8 | Manapyane | No local post office in Ward 8. Make use of service in Moganyaka. |
| 9 | Mamphokgo | Post Office.No postal service in other villages |
| 10 | Serithing Ngwalemong | Post Office boxes Post Office No postal service in other villages |
| 11 | Rakgwadi | Post Office.No postal services in other villages. |
| 12 | Tsimanyane | Posting service only.No postal service in other villages |
| 13 | Elandskraal/Hinlopen | Post Office. Mail Collection Point |
| 14 | Dicheoung | Mail Collection Point |

7.6.1	Backlog – Ward visits August 2010

| Ward 1 | Vodacom tower at Malebitsa |
| --- | --- |
| Ward 2 | No need indicated |
| Ward 3 | 1.Uitvlugt – increase post boxes and Keerom require post boxes(nothing at present).2.Vodacom tower at Keerom/Uitvlugt |
| Ward 4 | Post Office required at Matlerekeng |
| Ward 5 | No need indicated |
| Ward 6 | In view of the many queries by residence on various Municipal matters there is a need for a service desk to be installed at the Municipality both personal and phone contacts. |
| Ward 7 | No need indicated |
| Ward 8 | MTN/Cel C reception upgrade required for ward.2.Etv and SABC reception upgrade required at Moganyaka south and north. 3.Telekom landline connections required for schools and households in ward.4.Internet reception required 5.Post boxes required at Moganyaka North/South |
| Ward 9 | 1.Mamphokgo-post boxes required.2.Telkom connections required for schools and clinic-there is a main line leading to the hospital. |
| Ward 10 | 1.Telkom lines required in all villages for phones-Main line runs from Rakgwadi to Nebo .2.Post office required at Mabitsi B 3.Post boxes required in all villages accept Serithing and Ngwalemong “A” which have boxes. 4.Vodacom/MTN/Cel”C” reception is poor in all villages except Seretheng |
| Ward 11 | 1.Vodacom/MTN towers required in ward.2.TV antenna required in the ward.3.Post office required at Moomane 4.Post office required at Manotoloaneng |
| Ward 12 | 1.Tower required for vodacom/mtn/cell C at Tsimanyane and cordless telkom.2.House numbers to be placed at Letebejane |
| Ward 13 | Morarela and Mbuzini needs Telkom Public phones |
| Ward 14 | 1.3G required at Regae.2.MTN/Cel C poor reception and Telkom phones required at Dichoeung |

The challenges for the above is the lack of postal facilities and cel phone  reception

8.	INSTITUTIONAL ANALYSIS

The municipality has been organized in the following institutional components:

8.1	Council

1.Municipal  Council

The Council consist of 27 Councilors,14 ward councilors and 13 PR Councilors. The Council give political guidance to the municipality with regard to policy development

2.Office of the Speaker

Presiding at meetings of the Council

Performing the duties and exercises the powers delegated to the speaker in terms of section 32 of  the Structures Act No. 117 of 1998.

Ensuring that Council meets at least quaterly.

Maintaing order during meetings

Ensuring compliance in the Council and Council committees with the code of conduct set out in Schedule 5 of the Structures Act.

Ensuring that Council meetings are conducted in accordance with the rules and orders of the Council

3.Office of the Mayor

Presiding at meetings of Executive committee

Performing the duties, including any ceremonial functions,and exercises delegated to the Mayor by the municipal council or the executive committee.

8.2	Staff Component

The organogram has been completed, placements have been done, job descriptions is in place and appointment of key staff are being done as finances are available.

8.3	Human Resource Policies

Travelling and subsistence allowances policy and Cell phone policy was revised on 31 May 2010

8.4	Organisational Performance Management System(OPMS) and Performance Management System(PMS)

8.4.1	OPMS

Performance plan of the municipality for 2011/12

STRATEGIC THRUST 1: EFFECTIVE FINANCIAL MANAGEMENT

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 1.1Monitor and control the budget of the municipality so that expenditure is in line with Council’s requirements and availability of funds | End June 2012 | a)All spending occurs within the parameters of the budget. b)Sound financial management c)Highlight any irregularities to H.O D’s d) Provide a monthly overview of the budget for each department and the municipality and any issues that need to be taken into consideration |  |  |
| 1.2 Develop a medium term financial framework within which Council can operate. | End June 2012 | a)Develop a Five-year financial plan which should be approved by Council. b)Evidence to be provided that the financial plan is linked to the IDP. |  |  |

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 1.3 Develop and implement a budget process and system that allows for public participation and the alignment of the budget to community needs. | End May 2012 | a)Budget process plan approved by 31 August 2011. b)Prepare and submit draft budget to the Municipal Manager for discussion with management and thereafter the finance portfolio committee c)CFO should prepare the budget process as far as is practically possible in line with GAMAP principles. Prepare a plan that will show what needs to be in place in order to implement GAMAP by 2011/2012 . d)Budget process should be communicated and implemented. (Evidence to be provided on the implementation of the system). e) Ensure budget is adopted by end of May 2012. |  |  |

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 1.4 Manage and control budgeting and financial planning so that the strategic direction of Council is reflected in the budget and that the budget is adhered to. | 31 May 2012 | a)Evidence to provided of public participation (this will be arranged by finance portfolio committee, who will be guided by the development of the budget within timeframes that will lead to the adoption of the budget by 31 May 2012 b)Budget submitted to and approved by Council within required deadlines/format. c)Approved budget should be submitted to National Treasury within 14 days after adoption of the budget d)Preparation and submission of financial statements within required deadlines in the format required by the Auditor General |  |  |
| 1.5 Manage all assets and insurance of Council so that there is adequate cover. | 30 June 2012 | a)Asset risk management strategy should be developed. b)Develop an asset register |  |  |
| 1.6 Manage and control revenue so that Council receives all money owed to it. | 30 June 2012 | a)Plan developed ,approved and implemented to improve payment facilities/pay points in conjunction with other service providers. (Progress to be in line with plan). a)Indigents and Credit Control Policies developed and approved |  |  |
| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
|  |  | by Council. (Progress to be measured against policies). b)A Tariff Policy that differentiates various categories of consumers and areas based on services and affordability to be developed and approved by Council. c)Differentiated rates system to be developed and approved by Council. (Evidence of progress to be provided). |  |  |
| 1.7 Facilitate the process of building capacity in the Finance Department | 30 June 2012 | a)Appoint interns in consultation with the Manager Corporate Services b)Develop and implement a mentoring programme for the interns c)Appoint a Deputy Chief Financial Officer |  |  |
| 1.8 To identify other sources of revenue which will improve income received by the municipality | 30 June 2012 | Facilitate the compilation of a comprehensive valuation roll |  |  |

STRATEGIC THRUST 2 : INSTITUTIONAL TRANSFORMATION

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 2.1 Develop and implement an Employment Equity Plan for the Council and promote adherence to the plan in the Corporate Services Department | 30 June 2012 | a)Plan approved by Council. |  |  |
| 2.2 To promote and ensure that capacity is built within the institution and in the community | 30 June 2012 | a)Coordination of Internship/ volunteer/ mentorship programmes. b)Development of a skills development plan. c)Accessing of funds for skills development from LGWSETA d) Assisting other departments in facilitating access to training for members of the community i.e SETA’s and Dept. of Labour . |  |  |
| 2.3 To lead and direct the Human Resources Section so that the HR objectives of Council are achieved. | 30 June 2012 | a)Develop an institutional development business plan and facilitate its implementation. b)Develop HR policies and plans. c)Facilitate change management d)Develop a policy and programmes around the issue of HIV/AIDS in the workplace e) Purchasing of software that will assist in the management and |  |  |
| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
|  |  | administration of Human resource related information |  |  |
| 2.4 Lead and direct the Administration Section so that the administration objectives of Council are achieved | 30 June 2012 | Purchasing of software that will assist in the management, administration and distribution of information |  |  |
| 2.5 Lead and direct the Legal Service Section so that the objectives of Council in this area are achieved. | 30 June 2012 | Development and review of by-laws. |  |  |
| 2.6 Lead, direct and manage staff within Department so that they are able to meet their objectives. | 30 June 2012 | All subordinates to have job descriptions which are available for inspection and links to the overall strategic objectives of Department. |  |  |

STRATEGIC THRUST 3 : SUSTAINABLE DEVELOPMENT AND ENVIRONMENTAL MANAGEMENT

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 3.1 To promote a safe, clean sustainable and well managed environment in line with the Integrated Development Plan of the Municipality. | End of June 2012 | a)develop and implement policies and by-laws b)provide an efficient refuse removal service in Marble Hall and Leeuwfontein and develop a plan to extend the service to Elandskraal, Matlerekeng and other areas c)Proper disposal of collected waste at registered waste sites |  |  |

STRATEGIC THRUST 4 : SERVICE DELIVERY EXCELLENCE , CUSTOMER SERVICE AND BATHO PELE

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 4.1 To strive to provide services to the municipality’s customers in an effective and efficient manner | 30 June 2012 | a)Conduct customer survey to determine service and support satisfaction level : - Employees - Departments - Senior Management - Labour - Political Structures b)Training, awareness and implementation of BathoPele principles c)Establish suggestion boxes |  |  |

STRATEGIC THRUST 5 : ACCESS TO BASIC SERVICES

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 5.1 Prepare and facilitate the implementation of strategic plans for electricity that both inform and are aligned to the Integrated Development Plan | End June 2012 | a)Annual electricity plan developed and approved by Council. Plan should compliment plans for municipality’s growth b)Plan should be submitted to the District municipality and ESKOM for funding c)Facilitate the Provision of free basic electricity d)Facilitate the provision of electricity for the Marble Hall Loskop housing development project |  |  |
| 5.2 Prepare strategic plans for water and sewerage that both inform and are aligned to the Integrated Development Plan of the Municipality. | End June 2012 | a)Annual Water and Sanitation project Plan approved by Council and submitted to District municipality for implementation. Plan should compliment plans for the Municipality’s growth. b)Progress against plan provided – progress to be on track with approved plan. c) 5-year capital plan aligned to IDP, approved by Council and reviewed annually. |  |  |
| 5.3 Plan in liaison with the District municipality for services that are | End June 2012 | a)Facilitate a service level agreement with the District for the provision of water |  |  |
| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| within the powers and functions of the district municipality |  |  |  |  |
| 5.4 Prepare and implement strategic plans for roads and storm water that both inform and are aligned to the Integrated Development Plan of the Municipality. | End June 2012 | a)Annual roads and storm water plan approved by Council. Plan should compliment plans for the Municipality’s growth. - internal roads - Tarring of existing gravel roads - Progress against plan provided – progress to be on track with approved plan. b)5-year capital plan aligned to IDP, approved by Council and reviewed annually. |  |  |
| 5.5 Maintain the road assets so that the life cycle costs are optimized and the mobility/access needs of the population are met. | End June 2012 | Maintenance of internal tarred roads as part of the urban renewal plan |  |  |
| 5.6 Reduce the infrastructural backlogs to ensure efficient and effective provision of service for improved living conditions. | End June 2012 | a)100% of capital budget to be spent. b)Facilitate process of provision of housing and the implementation process |  |  |

STRATEGIC THRUST 6 : PUBLIC SAFETY AND BY-LAW ENFORCEMENT

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 6.1 Ensure the enforcement of by- laws and the prosecution of offenders. | End June 2012 | Control, regulate and monitor hawkers in town (traffic/health). Identify and allocate sites. Development of infrastructure c)Determination of tariffs and registration of hawkers Develop a database of hawkers info and a plan d)10% of informal traders trained and certified. e)Assessment of which by-laws are necessary to regulate activities in the department of community services |  |  |
| 6.2 To promote a safe and secure environment | End June 2012 | a) Undertake an assessment of the status quo in terms of police stations and the problems communities are encountering and the best mechanisms to deal with the problems. b)Facilitate and ensure that Community policing forums are established Develop a crime prevention strategy |  |  |
| 6.3 Regulate and manage traffic, enforce by-laws and educate the public so that safety on the | End June 2012 | a)Develop and implement targets for law enforcement to improve service delivery and increase income generated through this exercise for each official. |  |  |
| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| road is improved |  |  |  |  |
| 6.4 Oversee the management of the Licensing Section and Testing Stations so that efficient and effective license services and testing of vehicles takes place | End June 2012 | a)Perform an audit of establishing the testing stations compliance with SABS requirements. |  |  |
| 6.5 Oversee the management of disasters and safety of the residents | End June 2012 | a)Facilitate discussions with the District municipality for the development of a Disaster management centre in Marble Hall. b)Investigate the feasibility of establishing an ambulance service and develop a proposal |  |  |

STRATEGIC THRUST 7: HOUSING DELIVERY

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 7.1 Make provision for the improvement of service delivery of low income housing for low income communities. | End June 2012 | a) Evidence to be provided of housing provision for low-income communities. |  |  |

STRATEGIC THRUST 8 : TRANSPORTATION

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 8.1 To provide an effective and efficient transport system | End June 2012 | a)Identify areas where there is a need to develop taxi and bus ranks and make applications for funding. |  |  |

STRATEGIC THRUST 9 : ECONOMIC GROWTH AND DEVELOPMENT

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| . 9.1 To empower and build the capacity of entrepreneurs so that they are able to understand and have an impact on the economic development and growth of this Municipality. | End June 2012 | a)Develop a database of information on the economy, skills audit. b)Capacity building and training of entrepreneurs c)Empowerment of farmers through Emerging farmers development programme Evidence provided (in the form of a report) to show interaction with stakeholders i.e. names and positions of people, dates of meetings, meetings initiated by, issues discussed at meetings and outcome of meetings. |  |  |
| 9.2 Facilitate and foster the economic development through planning and increased economic activity in the municipal area | 30 June 2012 | a)Development of a unique tourism destination (mini national park, Flag Boshielo eco-tourism etc) e)Job creation through capital projects |  |  |
| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| 9.3 To preserve the heritage and culture of the municipality through promoting eco- tourism | 30 May 2012 | a)Heritage, culture, heritage sites and cultural sites preservation. b)Development of a cultural village. |  |  |

TRATEGIC THRUST10 : GOOD GOVERNANCE AND BUILDING DEMOCRACY

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 10.1 To promote effective and efficient communication both internally and externally | 30 June 2012 | a)Implementation of the communication strategy. |  |  |
| . 10.2 To ensure that there is effective and meaningful public participation by communities in Council programmes and activities | 30 June 2012 | a)Provide institutional support to ward committees b)Outreach programme by the Mayor |  |  |

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 10.3 Develop an IDP that ensures the activities of the municipality and its resource allocation are aligned to political priorities and community needs taking into account human resource and financial constraints | 30 June 2012 | Evidence to be provided of public participation and communication of the process to stakeholders e.g. publicity of information in the media, guidelines for councillors and staff, etc. |  |  |

STRATEGIC THRUST 11 : STRATEGIC MANAGEMENT

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 11.1 Develop an IDP that ensures the activities of the municipality and its resource allocation are aligned to political priorities and community needs taking into account human resource and financial constraints | 30 June 2012 | a)Planning process approved by Council. b)Evidence to be provided of education /support given to councilors and ward committee members during the planning process e.g. Councilors training programmes, etc. c)Development of Ward level IDP d)Facilitating the drafting of Annual municipal and Departmental business plans |  |  |

STRATEGIC THRUST 12 : FIGHTING POVERTY AND PROMOTING HUMAN DEVELOPMENT

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| 12.1 Lead and direct the Community Services for the Municipality so that the key strategic objectives in relation to Welfare are achieved. | End June 2012 | a)Initiate and facilitate food security projects in each ward. b)Facilitate the provision of shelter, sanitation, water and safety at pension pay points |  |  |

STRATEGIC THRUST 13 : HIV/AIDS PREVENTION AND MANAGEMENT

| OBJECTIVES | DATE | KEY PERFORMANCE INDICATOR | PERFORMANCE STATUS | REASON FOR DEVIATION |
| --- | --- | --- | --- | --- |
| .13.1 Lead and direct the Community services for the Municipality so that the key strategic objectives in relation to Health are achieved | End June 2012 | a)Develop and implement an HIV/AIDS strategy b)Coordinate the activities of NGO’s, CBO’s and other interest groups so that there is an integrated approach in dealing with HIV/AIDS and other social issues |  |  |

8.4.2	PMS

The Performance Management System (PMS) for the Municipality was reviewed and approved by Exco on 8 October 2010.The framework is in line with DPLG Local Government performance regulations published on 1 August 2006.

Performance agreements has been signed by managers for 2010/11.Performance agreements for 2011/12 will be approved by Council during June 2011.PMS evaluation panel has been established. Audit committee has been appointed on 26 November 2009 and quarterly review conducted during 2010/11.

8.5	Administrative Structure

1.Posts approved – 238

2.Vacancies – 18

3.Plans – Adverts for vacancies for critical posts placed during the year.

4.Challenges – The non-availability of funds for other vacancies.

8.6	Organogram

The following organogram was reviewed by council on 31 May 2010 and is aligned to the powers and functions of the municipality as 	set out under paragraph 10.1:

1.	Municipal Council

2.	Office of the Speaker

SPEAKER

Ward Councilors

Secretary   Budgeted

Driver

MUNICIPAL COUNCIL

Ward Liaison

Officers X2

Divisional Manager: Council Support Services

Reports to Unit

Manager

Corporate Services

3.		Office of the Mayor

MAYOR

Secretary Budgeted

Driver Budgeted

MUNICIPAL COUNCIL

Children, Aged, Gender & Disability Officers x2

Divisional Manager: Council

Support Services

Reports to Unit

Manager

Corporate Services

Communications

Officer

Public Relation

Officer Budgeted

4.	Organisational structure for Administration

5.	Office of the Municipal Manager

MUNICIPAL MANAGER Budgeted

Personal

Assistant Budgeted

Divisional Manager:

IDP M&E Budgeted

Divisional Manager: LED & Tourism

IDP M&E

Coordinator X 1

LED & Tourism

Officer X 1

Techniocians

X2

Admin

Office r X 1

Admin

Officer X 1

Manager

Strategic Planning

Internal Audit Budgeted

Data Capture

X2

Manager: PMU

6.	Corporate Services Business Unit

Human Resource

Division

MUNICIPAL MANAGER

SECRETARY Budgeted

UNIT MANAGER:

CORPORATE SERVICES Budgeted

Legal & Admin

Division

Supervisor: Information

Communication

& Technology

Council Support

Services Division

Div. Man

Council Support

Supervisor: Security

Services

Secretary to Mayor X 1

Secretary to

Speaker X1

Communication

Officer X 1

Mayoral Driver

X1

Ward Liaison Officer X 3

Committee Clerks

X2

Messengers

X2

Children, Aged, Gender & Disability Officer X1

6.1	Information Communication and Technology Division

Technician  Budgeted

Supervisor:

Information Communication

& Technology

MUNICIPAL MANAGER

UNIT MANAGER:

CORPORATE SERVICES

6.2	Human Resource Division

Divisional Manager:

Human Resource Budgeted

Labour

Relations

Officer Budgeted

Organisational

Development

Officer Budgeted

MUNICIPAL MANAGER

UNIT MANAGER:

CORPORATE SERVICES

HR Officer Budgeted

Personnel

Clerks x 2 (1 budgeted)

Occupational Health

& Safety Officer Budgeted

PMS Officer

6.3		Legal and Administration

r

Chief Admin Officer Records

Record Clerk

X (2)  budgeted

Legal Officer

Legal Admin

Clerk

Administration

Officer budgeted

Messenger/

Drivers x 1)

Cleaners /Kitchen

Attendant x 7 (8)

Divisional Manager:

Legal & Admin Budgeted

MUNICIPAL MANAGER

UNIT MANAGER:

CORPORATE SERVICES

Receptionist /Typist budgeted

7.	Technical Services Business Unit

Civil Services

Divisional Manager budgeted

MUNICIPAL MANAGER

UNIT MANAGER:

TECHNICAL SERVICES budgeted

Electro

-

Technical Services

Water & Sanitation

Roads & Storm water

Electrical

Technical

SECRETARY budged

Town Planning

Divisional Manager

Town Planner

Building Control

Divisional Manager budgeted

Divisional Manager

Water & Sanitation

7.1		Water and Sanitation Division

Divisional Manager:

Water & Sanitation

MUNICIPAL MANAGER

UNIT MANAGER:

TECHNICAL SERVICES

Technician

X2

Artisan: Water &

Sanitation X (2)

Water

-

Truck

Drivers X (4)

Labourers  X

(8)

Water

Operators X (4)

Sewer

Operators X (4)

7.2		Roads and Storm water division

Divisional Manager:

Roads & Storm Water

MUNICIPAL MANAGER

UNIT MANAGER:

TECHNICAL SERVICES

Technician

Roads & Storm water X2

Artisans

x 2

Compactor

Operator x 1

Labourers

X 8

TLB Operator

x 4

Grader

Operator x 4

Truck

Drivers x 4

7.3	Town Planning Division

Divisional Manager:

Town Planning

MUNICIPAL MANAGER

UNIT MANAGER:

TECHNICAL SERVICES

Town Planner budgeted

Handyman

X 2

Caretaker

X 1

Building

Inspector X 2 (1 budgeted)

Building Controller

Land Use Management

Services Officer X1

7.4	Electro-technical  Services Division

Divisional Manager:

Electro

-

Technical Services budgeted

MUNICIPAL MANAGER

UNIT MANAGER:

TECHNICAL SERVICES

Technician Electrical Services

Electrician X (3)

Artisan

Assistants (3)

Labourers X (3) budgeted

Artisan X (3)

Senior Mechanical Officer budgeted

Mechanic X (2) (1 budgeted)

Artisan

Assistants (2)

General

Worker (2)

Budgeted

8.	Financial Services Business Unit

Budget & Treasury

Division

MUNICIPAL MANAGER

UNIT MANAGER:

FINANCIAL SERVICES budgeted

Supply Chain Management

Division budgeted

SECRETARY budgeted

Revenue

Expenditure

Budget Control

Supply Chain Management

Unit

Customer Care Unit

8.1	Budget and Treasury : Revenue

Divisional Manager:

Budget & Treasury

MUNICIPAL MANAGER

UNIT MANAGER:

FINANCIAL SERVICES

Accountant Revenue budgeted

Senior Clerk Revenue budged

Clerk Revenue

X (2)

Meter

Readers (2)

Cashiers X (4) (2 budgeted)

8.2	Budget and Treasury : Expenditure

Divisional Manager:

Budget & Treasury

MUNICIPAL MANAGER

UNIT MANAGER:

FINANCIAL SERVICES

Accountant Expenditure budgeted

Snr Clerk

Expenditure

X (1) budgeted

Clerk

Expenditure

X (1) Budgeted

Snr Clerk

Salaries X (1) budgeted

Clerk

Salaries  X (1)

8.3	Budget and Treasury : Budget Control Division

Divisional Manager:

Budget & Treasury

MUNICIPAL MANAGER

UNIT MANAGER:

FINANCIAL SERVICES

Accountant Budget Control

Asset Control

Officer X (1)

8.4	Financial Management : Customer Care Management Unit

Divisional Manager:

Budget & Treasury

MUNICIPAL MANAGER

UNIT MANAGER:

FINANCIAL SERVICES

Senior Admin Officer:

Credit Control &

Indigent Support X (1)

Admin Officer:

Credit Control &

Indigent Support X (1 budgeted)

Consumer Account

Enquiry

Clerks X (2)

Customer Care Unit

8.5	Supply Chain Management Unit

Divisional Manager:

Supply Chain Management budgeted

MUNICIPAL MANAGER

UNIT MANAGER:

FINANCIAL SERVICES

Assistant Logistics/

Stores Officer X (1) budgeted

Acquisition & Tendering

Officer X (2) budgeted

Logistics / Stores

Officer X (1) budgeted

9.	Community Services Business Unit

Health, Education,

Library & Environment

Division

MUNICIPAL MANAGER

UNIT MANAGER:

COMMUNITY SERVICES budgeted

Traffic, Protection &

Emergency Services

Division

SECRETARY budgeted

Library Services

Parks & Cemeteries

Solid Waste

HIV / AIDS

Environmental Management

Traffic Services

Licensing

Sports, Youth, Arts, Heritage & Culture Officers (2)

9.1	Health, Library, Education and Environment Division

Divisional Manager:

Health, Library, Education

& Environment budgeted

MUNICIPAL MANAGER

UNIT MANAGER:

COMMUNITY SERVICES

Senior

Librarian (1)

Librarian (1) budget

Library

Attendant (1) budget

Artisan

Parks & Cemetery (1)

Cemetery

Labourers  X (4)

Horticulturist

X (1)

Labourers

X (15)

HIV / AIDS

Coordinator

Tractor Drivers

X (4)

Environmental Management Officer (1)

Solid Waste

9.2	Solid Waste

Divisional Manager: Health, Library, Education & Environment

MUNICIPAL MANAGER

UNIT MANAGER:

COMMUNITY SERVICES

Supervisor: Solid Waste

Truck  Driver

X (3)

TLB Operator

X (1)

Foreman

Tractor Driver

X (3)

Labourers

X (8)

Street Cleaners

X (10)

9.3	Traffic, Protection and Emergency Services Division

Divisional Manager: Traffic, Protection & emergency Services

MUNICIPAL MANAGER

UNIT MANAGER:

COMMUNITY SERVICES

Chief Traffic officer

Law Enforcement

Chief Licensing

Officer: Registration

Authority

Superintendent

X (2)

PIT Assistant

x 1

Senior License

Officer X (1)

Superintendent

Testing Centre x 1

Traffic Officer

X (16)

Cashier:

Licensing

X (4)

Vehicle

Examiner

X 2

Drivers Licenses

Examiner X 6

Business Licenses Officer

Customer Care Clerk x 1

Filing Clerk x 1

Cleaners (2)

10	Administrative/Satelite Offices

Zamenkomst Satellite Office

CORPORATE SERVICES

Admin Officer

Cleaner

TECHNICAL SERVICES

Water & Sanitation Team

FINANCIAL SERVICES

COMMUNITY SERVICES

Cashier

Messenger / Driver

Receptionist/ Typist

Roads & Storm-water Team

Parks & Cemetery Team

Traffic, Protection & Emergency Team

General Worker (6)

Artisan

Artisan

Artisan

General Worker (4)

General Worker (4)

Traffic Officers (2)

Leeuwfontein Satellite Office

CORPORATE SERVICES

Admin Officer

Cleaner

TECHNICAL SERVICES

Water & Sanitation Team

FINANCIAL SERVICES

COMMUNITY SERVICES

Cashier

Messenger / Driver

Receptionist/ Typist

Roads & Storm-water Team

Parks & Cemetery Team

Traffic, Protection & Emergency Team

General Worker (6)

Artisan

Artisan

Artisan

General Worker (4)

General Worker (4)

Traffic Officers (2)

Elandskraal Satellite Office

CORPORATE SERVICES

Admin Officer

Cleaner

TECHNICAL SERVICES

Water & Sanitation Team

FINANCIAL SERVICES

COMMUNITY SERVICES

Cashier

Messenger / Driver

Receptionist/ Typist

Roads & Storm-water Team

Parks & Cemetery Team

Traffic, Protection & Emergency Team

General Worker (6)

Artisan

Artisan

Artisan

General Worker (4)

General Worker (4)

Traffic Officers (2)

8.7         Employment equity

Employment equity plan has been compiled and the challenges is to attract suitable, qualified and competent staff  in line with the 			              plan.

8.8        Skills needs

The skills needs are covered in the skills development plan.

9.	FINANCIAL VIABILITY AND  MANAGEMENT

9.1	Grants and Subsidies

The allocation for 2010/11 is MIG R 14 800 000 ,Equitable Share R52 272 000, FMG R1 000 000, Organic farming (DTI) R15 159 850 			and MSIG R750 000 and  was utilized for the following projects:

| Section Responsible | IDP Link | Projects | Ward Number | Funding Source | Budget 2010/2011 |
| --- | --- | --- | --- | --- | --- |
| Technical services | Roads and stormwater | Tar R29 from Matlerekeng to Rathoke | 4 | Council/MIG Vote 850/305060 | 5 200 000 |
| Technical services | Roads and stormwater | Rehabilitation of Leeufontein Internal Roads Phase 1 | 7l | Council/MIG Vote 850/305056 | 4 694 920 |
| Technical services | Roads and stormwater | Mathukuthela Bridge | 11 | Council/MIG Vote 850/305061 | 850 000 |
| Technical services | Roads and stormwater | Manotolwaneng Bridge | 11 | Council/MIG Vote 850/305062 | 554 245 |
| Technical services | Roads and stormwater | Marble Hall Bulk Stormwater |  | Council/MIG | 640 000 |

| Section Responsible | IDP Link | Projects | Ward Number | Funding Source | Budget 2010/2011 |
| --- | --- | --- | --- | --- | --- |
| Technical services | Roads and stormwater | Malebitsa internal roads | 1 | Council/MIG Vote 850/305075 | 640 000 |
| Technical services | Roads and stormwater | Keerom/Uitvlug road | 2 | Council/MIG Vote 850/305065 | 640 000 |
| Technical services | Roads and stormwater | Moganyaka access road | 8 | Council/MIG Vote 850/305064 | 640 000 |
| Technical services | Roads and stormwater | Vaalbank internal road | 10 | Council/MIG Vote 850/305076 | 600 000 |
| Technical services |  |  |  |  |  |

| Section Responsible | IDP Link | Projects | Ward Number | Funding Source | Budget 2010/2011 |
| --- | --- | --- | --- | --- | --- |
| Strategic Planning | LED & Job creation | Organic farming | All | DTI Vote760/260154 | 15 159 850 |
| Financial services | Financial management | Financial viability special projects | All | Council MSIG Vote775/260115 | 150 000 |
| Financial Services | Financial management | MFMA reporting and AFS audit action plans | All | Council MSIG Vote775/260780 | 350 000 |
| Corporate Services | Good Governance and public participation | Functioning of ward committee | All | Council MSIG Vote505/260641 | 250 000(MSIG) |

9.2	Credit and Debt Control

Credit control and Debt collection policy reviewed by the council on 31 May 2010.

The purpose of this policy is to ensure that credit control forms part of the Municipality’s financial system and 						to disclose the intention of Council to standardise procedures for each individual case.

Service accounts that are not paid by the 25th of the month are being placed on a cut-off list and handed to the parties liable for the 				disconnection of services, on the first day of each week and the services of all accounts highlighted for disconnection are disconnected 				before the end of the third working day of the first week.This action occur without any prior notice. Reconnection fees are payable  in 				terms of council’s tariff of  charges on payment of outstanding account is paid.

9.3	Investments

Investment policy was adopted by council.

The Chief Financial Officer is responsible for investing the surplus funds of the Municipality. These investments are managed in 				consultation with the Mayor or chairperson of the Portfolio Committee on Finance.

On a quarterly basis the Chief Financial Officer  submit to council a report reflecting information on the council’s investment portfolio, including the type of investment, interest rates, period of investment and a summary of the exposures to particular financial institutions. The CFO must submit once a year a certificate of compliance that no gifts, commission or other consideration was received for investments made.

The CFO must  keep a investment register for all investments made

9.4	Audits

Audits are made by the staff of the Auditor General as soon as the financial statements have been compiled at the end of August of 				each year.

The audit on the financial statements for 2009/10 has been completed and an unqualified opinion was received from the Auditor 				General for the previous year.

9.5	Budget and Treasury

1.Cash flow budget has been compiled and form part of the budget for 2010/11.

2.Objectives of 2010/11 budget was to divide budget into following programs:

1.1	Operational – R127 813 744

1.2	Capital – R16 399 000

1.3	MIG – R14 800 000

1.4	Grants – R68 881 000

1.5	Rates and Taxes – R9 902 500

3.Figures on the above for 2009/10  is:

1.1	Operational – R108 471 796

1.2	Capital – R 16 443 900

1.3	MIG – R12 000

1.4	Grants – R42 737 000

1.5	Rates and Taxes – R7 800 000

9.6	Revenue Management

Revenue enhancement  project included in the SDBIP of the CFO has been implemented by the appointment of service provider for 				strategy development .

9.7	Supply Chain Management

Supply chain management division established and SCM policy reviewed on 31 May 2010.

In terms of policy three Bid committees has been established namely, Bid specification committee, Bid evaluation 					committee and Bid adjudication committee.

9.8	Asset Management

Asset management policy adopted by council on 31 May 2010.

The fixed asset register converted  to GAMAP/GRAP format.

10.	GOOD GOVERNANCE AND PUBLIC PARTICIPATION

The following arrangements and structures are in place to assist with local governance:

10.1	Powers and Functions

| Function | Municipal Authority | District Authority | Remarks |
| --- | --- | --- | --- |
| 1.Air Polution | Yes |  |  |
| 2.Building regulations | Yes |  |  |
| 3.Child care facilities | Yes |  |  |
| 4.Electricity reticulation | Yes for Marble Hall town |  | Eskom reticulate rest of municipality |
| 5.Fire fighting | No(see remarks) | Yes | Provide function on behalf of district |
| 6.Local tourism | Yes |  |  |
| 7.Municipal airport | Yes |  |  |
| 8.Municipal planning | Yes |  |  |
| 9.Municipal Health Service | No(see remarks) |  | Provide function on behalf of GSDM |
| 10.Municipal Public Transport | Yes |  | Bus & Taxi rank in private ownership |
| 11.Pontoons & Ferries | Yes |  |  |
| 12.Storm water | Yes |  |  |
| 13.Trading regulations | Yes |  |  |
| 14.Water (potable) | No(see remarks) | Yes | Provide function on behalf of District for Marble Hall town,Leeuwfontein and Zamenkomst |
| 15.Sanitation | No(see remarks) | Yes | Provide function on behalf of District for Marble Hall town,Leeuwfontein and Zamenkomst |
| 16.Beaches and amusement facilities | Yes |  |  |
| 17.Billboards and the display of advertisements in public places | Yes |  |  |
| 18.Cemetries,funeral parlours and crematoria | Yes |  |  |
| 19.Cleansing | Yes |  |  |
| 20.Control of public nuisance | Yes |  |  |
| 21.Control of undertakings that sell liquor to the public | Yes |  |  |
| 22.Facilities for the accommodation,care and burial of animals | Yes |  |  |
| 23.Fencing and fences | Yes |  |  |
| 24.Licensing of dogs | Yes |  |  |
| 25.Licensing and control of undertakings that sell food to the public | Yes |  |  |
| 26.Local amenities | Yes |  |  |
| 27.Local sports facilities | Yes |  |  |
| 28.Markets | Yes |  |  |
| 29.Municipal Abattoirs | Yes |  |  |
| 30.Municipal parks and recreation | Yes |  |  |
| 31.Municipal roads | Yes |  |  |
| 32.Noise pollution | Yes |  |  |
| 33.Pounds | Yes |  |  |
| 34.Public places | Yes |  |  |
| 35.Refuse removal refuse dumps and solid waste disposal | Yes |  |  |
| 36.Street trading | Yes |  |  |
| 37.Street lighting | Yes |  |  |
| 38.Traffic and parking | Yes |  |  |
| 39.Registration authority | Yes |  |  |

10.2	Communication

Newsletters  are published on a quarterly basis  in terms of one of the projects which are included in the SDBIP of Corporate services 				manager , the key objective being to promote, market and  inform constituencies about activities within the Municipality.

10.3	Ward Committees

Fourteen ward committees have been established and support is given by the municipality in the form of sitting fee which are  paid to 				members for attending ward committee meetings.After municipal election two additional ward committees to be established as number 				of wards have been increased to sixteen in terms of demarcation board ward delimitations.

Ward committees consist of 10 members each and each member have a specific portfolio i.e. water, roads, IDP,LED etc. The ward 				committees participate in the meetings when the wards are visited when reviewing the IDP to give input on community isues.

10.4	Community Development Workers

Seventeen community development workers have been deployed to the 14 wards of the municipality and report to the Speakers office

10.5	Traditional Leadership

There are five traditional leaders within the municipal area .

The traditional leaders are consulted in regard to all local governance matters and are invited to all Council and IDP representative 				meetings.

The relationship between the council and the traditional leaders are sound.

10.6	Intergovernmental Relations

Good relationship has been established with the District municipality in that various forums have been formed namely, District Mayors 				Forum ,District Municipal Managers forum, District IDP Managers forum, District IDP Representative Forum District Planning forum 				District PMS forum ,District Technical  forum and District  Health forum.

Sector departments are part of the District IDP representative forum where their plans and programs for the IDP’s  of  the District and 				municipalities within the district are given.

10.7	Audit,anti-corruption and risk management

The challenges in respect of audit, anti- corruption and risk management is that  action plans are not always implemented within set 				deadlines .

10.8	Special focus groups

Disabillity,Youth and Gender desk has been established in the municipality and there programs are coordinated through the Mayor’s 		office. Reading facilities have been established for the blind at the Marble Hall library.

The   needs of these groups include disability centre and recreation facilities for the youth.

11.	SWOT ANALYSIS

KPA 1 Service delivery and infrastructure development

| Department | Issues/ Services Delivery | Strength | Weakness | Opportunity | Threats |
| --- | --- | --- | --- | --- | --- |
| Technical services | Provision of water & purification services | Water works upgraded | Ageing infrastructure. Process of transferring staff to GSDM too slow. | District is currently developing bulk services studies in Montse area. SDM in the process of replacing the asbestos pipes in town. Plans for transferring of staff already in place.the process will be completed by the 30th June 2010. | Different water tariffs -Water authority lies with Greater Sikhukhune district municipality and limited decision making at local level. |

|  | Water works |  | Marble Hall water works needs to be refurbished and new reservoir and dams not commissioned | District in process of upgrading Marble Hall water purification works |  |
| --- | --- | --- | --- | --- | --- |
|  | Provision of roads & maintenance |  | Insufficient & old plant equipment then render them insufficient | Un-economic equipment to be auctioned | On-going roads deterioration of the municipality |
|  | Provision of sewerage |  |  | GSDM appointed the consultant to upgrade the Marble Hall sewerage plant and sewerage ponds at Leeuwfontein | Water authority lies with GSDM |
| Community Services | Environmental services | Environment plan/strategy & implementation plan in place | Environment plan implementation not being monitored .Environmental management is a district function, not clear how to be implemented to fit the district plan. Staff inadequate Devolution of services not yet complete pending district function | DEAT willing to allocate budget and assist | Control over service process not finished |
|  | Traffic services and Law enforcement | Committed few staff and learnership opportunities New vehicles and equipment | Need extra warm bodies and office space | Ongoing training by provincial department | Non-alignment of boundaries as per magistrate and South African Police Services |
|  | Sport & creation, arts& culture and heritage sites | Heritage project in place and sport programmes | Lack of office equipment | On-going training and assistance by provincial department | No mandate or control and budget |
|  | Cleaning services | Licensed refuse tip site in place and collection of refuse in Marble Hall, Leeuwfontien and Elandskraal and hope to extend to other areas | Non payment by community Old fleet and no fleet management Lack of operational and warm bodies | Funding from GSDM | Programmes from national not aligned or implemented at local level. |
|  | Registration Authority | Adequate equipment | Lack of capacity and warm bodies | Provincial assistance | Closure by SABS vehicle inspectors for non-compliance |
|  | Disaster and Emergency services | Approved disaster management plan | District manage disaster management. Lack of warm bodies and inadequate budget and office space. Poor monitoring of the service No SLA between municipality and GSDM | District assistance | Fragmented service Lack of control |
|  | Youth, gender& disability programmes | Internship programmes in place. | Lack of warm bodies, office space and budget |  | No control or mandate |
|  | Library services | Recruitment plan of staff in place and well resourced library | Insufficient of tertiary institution books, budget and staff |  |  |
|  | Security services | Private security company has been appointed for high risk areas | Lack of good security management, plan, poor access control and locking of offices after hours Inadequate control of alarm system and supervision |  | No control |
|  | Parks and recreational facilities | Landscape in place | Lack of warm bodies No budget to extend service to other areas of EPMLM |  | No control |
|  | Hawkers and business trading licences | Hawkers management plan in place. Formal stalls build and database of beneficiaries and associates in place | No supervision and not designated as trading licence authority | Support of the stakeholders | No control |

KPA 2 Local economic development

| Department | Issues/ Services Delivery | Strength | Weakness | Opportunity | Threats |
| --- | --- | --- | --- | --- | --- |
| Strategic Planning | Plan manage and manage the implementation of LED | Organic farming cluster funded by DTI for 3 years amounting to R25m | Lack of monitoring of implementation of LED. Lack of staff | Employment and Funding future growth of LED projects | Unemployment and collapse of existing projects |

KPA 3 Municipal financial viability

| Department | Issues/ Services Delivery | Strength | Weakness | Opportunity | Threats |
| --- | --- | --- | --- | --- | --- |
| Finance | Revenue enhancement | Implementation of credit control policy in place | Most people in the rural communities are not paying their rates accounts . | Councilors should embark on awareness campaigns during their meetings with community members and encourage them to pay as part of their community work. Revenue enhancement strategy implementation | Some instances community members have been sighted saying that their councilor told them not to pay and this contributes to the non recovery of debts regardless of efforts made by administration. Lack of support from councilors persuade communities to pay for rates and services |
|  | Financial management and budget control | Compliance with MFMA budget regulations | Lack of staff in key positions | Good financial management | Revenue are not collected from entire municipality Interference in the filling of positions from politicians Lack of proper delegation of authority to unit managers on recruitment |

KPA 4 Municipal transformation & Institutional development

| Department | Issues/ Services Delivery | Strength | Weakness | Opportunity | Threats |
| --- | --- | --- | --- | --- | --- |
| Corporate Services |  |  |  |  |  |
|  | Human Resources and Development Administration personnel related issues. Industrial relations | Organogram reviewed on 29 May 2009 | Training plans for individual staff not in place,inadequate personnel, lack of coordination of training,inadequate implementation of policies(no monitoring).In service training policy. | Good Governance, Local Economic Development (LED) , Services Delivery | Foreign organisation to absorb them |
|  | Manage occupational health & safety matters | Labour officer arranging committees | No OHS committee,budget not used | Safety committee in place |  |
|  | Manage & provision of IT service | IT system upgraded,backup information kept(downloaded daily from network).Draft IT policy in place.IT officer appointed. | Monitoring of backup(backup register),remote backup. | Web site designed |  |
|  | Manage PMS i.r.o.employees | System is in place | Lack of individual employee workplan,lack of official responsible for monitoring of PMS-employee | GSDM appointed service provider to review framework and cascade PMS to post levels 1 & 2 | Unproductive staff |

KPA 5 Good governance

| Department | Issues/ Services Delivery | Strength | Weakness | Opportunity | Threats |
| --- | --- | --- | --- | --- | --- |
| Corporate Services | Legal advisory and corporate governance | Legal advisory firms appointed(2),draft bylaws in place. With new database will | Lack of legal services advisory panel, lack of contract management system, uncoordinated management of requests for legal service by departments | Identification of competent legal firm | Lawsuit |
|  | Provision logistic & administration support services | Ward committees established,budget available for ward committee operations,extra person in PRO’s office to assist with ward committee co-ordination, communication strategy, newsletter and draft public participation policy in place,electronic administration in place(filing)and staff trained to use system,Council agenda’s compiled. Council programme in place(portfolio,Exco & Council) | Ineffective local labour forum,lack of council resolution register,late submission of items for agenda,insufficient utilization of drivers,ineffective portfolio committees, |  |  |

KPA6 Spatial Rationale

| Department | Issues/ Services Delivery | Strength | Weakness | Opportunity | Threats |
| --- | --- | --- | --- | --- | --- |
| Technical Services | Ensure lawful security of tenure | Land use management system drafted | Lack of applicable legislation to approve Land Use Management System | To implement LUMS ounce in place | Uncoordinated and haphazard development |
|  | Develop, gain approval for and implement a spatial development framework | No Nodal points have been identified in SDF. SDF approved by Council on 25 June 2008. | No capacity to implement SDF | Compilation of master plans for the development of nodal points | Lack of approved Land Use Management System |

CHAPTER 3 – STRATEGIES PHASE

12.	DEVELOPMENT  STRATEGIES

## 12.1	Municipality Vision

The vision was amended at a strategic planning workshop on 8-9 February 2011 as follows:

Viable and sustainable municipality that provides quality services and enhance economic growth.

## 12.2	Municipality Mission

The mission was amended at a strategic planning exercise on 8-9 February 2011 as follows:

To involve all sectors of the community in the economic and social development whilst improving service delivery thereby  becoming a 				prominent agricultural, business, and mega industrial growth point in Sekhukhune District for the benefit of the residents and province

12.3	Core values of the municipality

1.Transparency, High Quality Service Delivery, Accountability

2.Service Communities with Integrity, Efficiency, Professionalism

3.Commitment, Teamwork, Communication

12.4	Strategies

12.4.1	 MUNICIPAL TURN AROUND STRATEGY

The following turn around strategy was developed during a meeting held on 29 and 30 March 2010 					with Councilors, Unit Managers, Divisional Managers, Staff from COGTA and DLGH and various sector 				departments:

## Quarterly progress report for period ending 31 December 2010

| PRIORITY AREA | BASELINE | INDICATORS | TARGETS | PROGRESS ACHIEVED | BLOCKAGES | CORRECTIVE MEASURES | SUPPORT NEEDED IN TERMS OF UNBLOCKING |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Access to basic (or higher) water | Out of 32304 households,290830 have access, and the backlog is 11474. | Nr of households with access to basic (or higher) levels of water | Engage District to return the WSA status by 30 June 2010. District to fast track the completion of retention dam and reservoir by December 2010 . District to improve the quality at the reservour by 30 April 2010. Municipality to improve the quality at the households by 30 April 2010. Expedite the retention of the water service providers by end of Arpil 2010 | District to report |  |  | District to complete uncompleted infrastructure projects in Mashimong, Makgtle (Ten) by December 2010. Engage the district in the supply of water for Ward 1-4 by 30 April 2010. Expedite the retention of the water service providers by end of Arpil 2010 |
| Access to basic (or higher) sanitation | Out of 32304, backlog is 25482. | Nr of households with access to basic (or higher) sanitation | District to formalise the participation of municipality in the planning, implementation, and M&E by 01 July 2010. District to establish a new sewerage system to cater for the new extension 6 and 1 new school by 2011 District to Maintain plants in marble hall town, eilandskraal, leuwfontein by 01 July 2010 | District to report |  |  | District to formalise the participation of municipality in the planning, implementation, and M&E by 01 July 2010. District to establish a new sewerage system to cater for the new extension 6 and 1 new school by 2011 |
| Access to basic (or higher) Electricity | Out of 32304, 30556 are connected and 1620 is the backlog | Nr of households with access to basic (or higher) electricity | DoE to increase the allocation from 400 to 600 units per year by 01 July | - Backlog now 1620 and Eskom plan to complete all project s that was on list before end of May 2011 except two (Mamphokgo and Matlerekeng) who will be completed before end of June 2011. There will be additional post connections. - Provision was made in budget for transformer maintenance. Oil testing was done. Tender must be advertised. - 2 Positions was advertised but no appointments. Struggle to get suitable instruments for quality recording in villages | - Incorrect data from Councillors. - Poor ESKOM performance - No progress in HR. - SCM very slow. Availability of independent remote metering of QOS. | - Include only name list verified by Councillor in IDP - Continues pressure on ESKOM. - Request HR to speed up process. - Request SCM to speed up process. - Request SCM to re-stock stores and update items needed. - Advertisements in Sowetan deliver poor results. - Update data-base and ensure notification of registered suppliers –tenders & quotes. Invitations for specialised work. | - Support from Councillors and IDP manager. - Pressure from MM on ESKOM and DoE at forum. - Engage Eskom to look at quality of supply by 2011. - Technical advise requested on QOS system. - MM to give direction to HR and SCM to improve. |
| Access to basic (or higher) refuse removal and solid waste disposal | Out of 32304, 2345 are serviced and the backlog is 29959. | Nr of households with access to basic (or higher) refuse removal | DLGH to assist the municipality in sourcing funds for operation and maintenance of landfill site by 01 July 2010. DLGH and LEDET to assist in Education and Awareness campaign on refuse removal by 30 May 2010. | Leeufontein is serviced 2 new vehicles delivered October 2010. None from DLGH AND LEDET |  |  | District and LEDET to return the environmental health function to the municipality by 2011. |
| Access to municipal roads | The total KM of roads is 451km, 63km tarred, and gravel is 388 km | Km of new municipal roads constructed | Engage District, DLGH and DoRT to assist in funding the development of the Integrated Road Master Plan by 30 December 2010. Approach OTP, DLGH and DoRT to assist with the maintenance of N11road by September 2010 . Municipality to look at alternative ways of maintaining gravel roads (DoRT) by 30 June 2010. | The engagement process started before end of October 2010.Have already emailed the TOR to the coordinator at the Department of local Government and Housing waiting for response Contacted Mr Issa from NRA in Pretoria ,indicated that at the moment they do not have any money or reserves but we should start again towards the end of the financial year maybe we will succeed to something when they start with their budgeting process The DoRT has also started an initiative called the Community home based routine maintenance programme .This pilot project has started with our Tsimanyane cost centre ,it is progressing well | NONE | NONE | Engage District, DLGH and DoRT to assist in funding the development of the Integrated Road Master Plan by 30 December 2010. Approach OTP, DLGH and DoRT to assist with the maintenance of N11road by September 2010 The Dort or DLGH to help the Municipality with funding to purchase more and better equipment |
| Access to free basic water | 13973 | Nr of households with access to free basic water | 13973 | 13973 |  |  |  |
| Access to free basic electricity | 2095 | Nr of households with access to free basic electricity | 2095 configured | 1450 collecting |  |  |  |
| Housing (Formalisation of informal settlement) | 2830houses built, Waiting list is at 200, | Nr of houses built | DLGH to fast track the finalisation of uncompleted houses by 30 April 2010. Municipality to engage Traditional Leaders on the proper management of land. Engage Moganyaka traditional authority on land invasion at Leeuwfontein by end of May 2010 | 484 houses completed |  |  |  |
|  |  | Nr of households in informal settlements provided with water | N/A |  |  |  |  |
|  |  | Nr of households in informal settlements provided with sanitation | N/A |  |  |  |  |
|  |  | Nr of households in informal settlements provided with electricity | N/A |  |  |  |  |
| Disaster Management |  | Number of disasters prevented, mitigated and preparedness | N/A |  |  |  |  |
| Repairs and maintenance |  | Service delivery Interruptions per type of service (time per month) and nr of households affected | District to report |  |  |  |  |
| Revenue management | Revenue enhancement strategy adopted in 2005 to be reviewed | Monthly collection rate on billings | 99 % in town Advertisement for the appointment of the service provider April 2010 Appoint service provider by May 2010 Development of the review of revenue enhancement strategy August 2010 | 80% collection rate in town |  |  |  |
|  |  | Percentage growth in revenue collected by the municipality as a % of projected revenue target. | 10% | 0-increase this quarter due to December holidays. |  |  |  |
|  |  | % of budgeted revenue for property rates collected (Implementation of the Municipal Property Rates Act, 2004 (Act no. 6 of 2004)) | Revenue budget is R127 813 744 Rates budget is R9 652 500 which is 7.6% of budgeted revenue | R944,257 collected which is 10% of budgeted rates revenue |  |  |  |
|  |  | Grants as a % of revenue received | Revenue budget is R127 813 744 Grants is R68 881 000 which is 54% of budgeted revenue | R19,700,975 received which is 15% of budgeted revenue |  |  |  |
| Debt management |  | R debtors outstanding as a % of own revenue | 50% reduction on outstanding debtors | 8% collected |  |  |  |
|  |  | % of debt over 90 days | 80% collection of recoverable handed over debts from the debtors’ book. | 30% collected |  |  |  |
|  |  | Debt collected as a percentage of money owed to the municipality | 80% collection of recoverable handed over debts from the debtors’ book. | 30% collected |  |  |  |
| Expenditure Management |  | Monthly operational expenditure as a percentage of planned expenditure | Budget expenditure for 3 months is R31 796 856 | Actual expenditure for 3 months is R29,016,246 |  |  |  |
|  |  | Monthly capital expenditure as a % of planned capital expenditure | Budget R20 226 000 | Spent R8,436,326 |  |  |  |
|  |  | % of operational budget spent on repairs and maintenance | 5% of operational Budget is for repairs and maintenance (R6 622 675 of R127 187 425) | 2% Spent R 144,245 of R6 622 675 budget |  |  |  |
|  |  | Monthly Repairs and maintenance expenditure (Rands) | Budget R6 622 675 | R144,245 spent |  |  |  |
|  |  | MIG expenditure a % of annual allocation | Annual allocation is R14 800 000 | 45% spent (R7,564,558) |  |  |  |
| Unqualified audit |  | Audit opinion | Unqualified | AG audit in process |  |  |  |
| Integrated development planning |  | Timeous adoption of IDP | Approve by 31 May 2011 | Analysis phase completed and approved by IDP representative forum on 30 November 2010 |  |  |  |
|  |  | Timeous adoption of budget | Approve by 31 May 2011 | Process plan approved on 25 November 2010 |  |  |  |
|  |  | Timeous adoption of SDBIP | Approve by 31 May 2011 | Process plan approved on 25 November 2010 |  |  |  |
|  |  | Reliable and credible IDPs | Compile reliable and credible IDP | Process plan approved on 25 November 2010 |  |  |  |
| Administration |  | Timeous submission of annual financial statements | Compile annual final statements by 31 August 2010 | Annual financial statements compiled and submitted to AG on 31 August 2010 |  |  |  |
|  |  | Timeous submission of annual reports | To submit annual report to council by 31 January 2011 | Draft annual performance info included in financial statements handed to AG on 31 August 2010 |  |  |  |
|  |  | Updated and credible asset register | Quarterly assets verification reports 75% disposal of obsolete stock | -Quarterly assets verification done. -Auction procurement |  |  |  |
|  |  | Functional OPMS | Review PMS framework | Reviewed PMS approved on 25 November 2010 |  |  |  |
| Administration |  | Updated and credible indigent registers | Updated indigent register | 9 wards registered |  |  |  |
|  |  | Financial controls applied to ensure usage is monitored / limited to indigent policy | To ensure accessibility of free basic services to the community | 2095 configured for FBE 1450 Collecting |  |  |  |
| Reduced corruption |  | Functional supply chain management system | A transparent municipal supply chain management system | Policy reviewed on 31 May 10 |  |  |  |
|  |  | Anti-corruption strategy implemented by target date | Anti-corruption strategy compiled by July 2010 | Strategy drafted to be submitted to Council during October 2010 for approval |  |  |  |
| Labour relations |  | % of critical posts filled | To fill 238 approved posts | 218 posts filled 17 posts advertised on 31 Aug 10 |  |  |  |
|  |  | % of critical posts with signed performance agreements | 100 % of section 57 mangers to sign performance agreements |  |  |  |  |
|  |  | Level of functionality of Local Labour Forum (LLF) | To have sound relations between management, unions and staff n by number of LLF meetings held | One meeting held |  |  |  |
| Public Participation |  | % of functional ward committees in terms of the new model | To ensure functionality of ward committees | Ward committees meet monthly and submit reports to Speakers office |  |  |  |
|  |  | Number of ward committee management meetings held and percentage attendance by members | To hold 12 ward committee meetings in the 14 wards | 6 ward committee meetings held in each of the 14 wards |  |  |  |
|  |  | Number of community meetings held | To hold 1 meeting every month for each of the 14 wards | 6 meetings held per 14 wards |  |  |  |
| Enabling environment for growth and development |  | Nr of job opportunities created through the CWP | To create 750 temporary jobs through labor intensive projects | 100 temporary jobs created |  |  |  |
|  |  | Number of wards per municipality implementing the CWP | To implement CWP in 7 wards | Implemented in 3 wards |  |  |  |
|  |  | Nr of cooperatives established and still functional in wards where the CWP is implemented | 24 cooperatives established | Cooperatives functional in 6 wards |  |  |  |
|  |  | LED strategy adopted | To adopt reviewed LED | LED strategy reviewed in 2008.Attended meeting at Phalaborwa on 10-15 October 2010 with Provincial LED office to review strategies |  |  |  |
| Enabling environment for growth and development |  | LED strategy and plans are aligned with PGDS | To align LED strategy with PGDS | Reviewed LED aligned to PGDS |  |  |  |

12.4.2	SUMMARY OF TURN AROUND STRATEGY

| Commision | Problem Statement | Strategic Objectives | INTERVENTIONS BY SECTOR DEPARTMENTS |
| --- | --- | --- | --- |
| Institutional transformation and good governance | Inadequate corporate/institutional capacity impedes the objectives of the IDP. Insufficient reflection of community needs impacts on the credibility of the IDP. Ineffective functioning of IGR structures impacts on good governance. | To improve corporate/institutional capacity to maximise institutional performance. To strengthen IGR structures to attain good governance and accountability. | Review of service level agreement of traffic function by department of Roads and Transport. Review of service level of CDWs by DLGH. Monitoring of sector department on IDP processes by Office of the Premier. |
| Service Delivery and Infrastructure Planning | The current powers and functions limits effective water and sanitation management, revenue enhancement, and accountability. The current institutional capacity limits maximum infrastructure development and service delivery. | To acquire WSA for improved basic service delivery. To strengthen institutional capacity for infrastructure development. | Engage District to return the WSA status by 30 June 2010 . District to fast track the completion of retention dam and reservoir by December 2010 . District to improve the quality at the reservoir by 30 April 2010. District to complete uncompleted infrastructure projects in Mashimong, Makgtle (Ten) by December 2010. Engage the district in the supply of water for Ward 1-4 by 30 April 2010 District to formalise the participation of municipality in the planning, implementation, and M&E by 01 July 2010. District to upgrade sewerage works in Marble Hall to cater for the new extension 6 and 1 new school by 2011. District to Maintain sewerage plants in marble hall town, Elandskraal, Leeuwfontein by 01 July 2010. DLGH review housing project management model to include role of municipality in Planning, implementation, and M&E of projects by 2011. DLGH to fast track the finalisation of uncompleted houses by 30 April 2010. DoE to increase the allocation of electricity connections from 400 to 600 units per year by 01 July 2010. Engage Eskom to improve quality of supply by 2011. Engage District, DLGH and DoRT to assist in funding the development of the Integrated Road Master Plan by 30 December 2010. Approach OTP, DLGH and DoRT to assist with the maintenance of N11road by September 2010 . DLGH to assist the municipality in sourcing funds for operation and maintenance of landfill site by 01 July 2010. DLGH and LEDET to assist in Education and Awareness campaign on refuse removal by 30 May 2010. District and LEDET to return the environmental health function to the municipality by 2011. Engage DoRT on the review of the shares of revenue by 2011 i.r.o. Traffic services Engage DoRT on the review of the possibility of getting shares per driver liscence card issued by 2011. DSAC to establish Libraries in three satelite offices: elandkral, zemenkop,and leuwfontein by December 2010. Municipality and DSAC to provide Education and awareness on the use of library by December 2010. DSAC Update the material in the library in town : Reference books, in all languages, and for disabled by December 2010. Engage SAPS to align police station boundaries with those of the municipality by August 2010. |
| FINANCIAL VIABILITY | Revenue enhancement strategy to be reviewed.(adopted in 2005) In adequate municipal capacity in order to implement IDP (staff) Inefficient financial systems. No Risk unit management in place. | To review and implement revenue enhancement strategy to enhance revenue collection. To upgrade the server of current financial system for optimal utilization. To establish Risk management unit for good governance and financial accountabillity. | Payment of assessment rate by the relevant sector departments on time. Clear reporting lines and formats by Provincial Treasury. Clear service level agreements for Water between the Municipality and SDM. DLGH to assist with the replacement of the financial system. |

| LED & PLANNING | Lack of capacity in the planning and LED unit. Lack of access of land for development. Lack of SMME and Cooperative Strategy. | To capacitate the planning unit in order to ensure its maximum functionality. To acquire strategic land for economic development. To capacitate and support SMMEs and Cooperatives in order for self sustainability. | Deployment of Town Planner by DLGH/DBSA. Assistance by TIL on the development of Marketing and Investment strategy. Intervention by the Department of Rural Development to unlock community land for development. |
| --- | --- | --- | --- |

12.4.3 	Following strategies have been developed to meet the municipality’s development challenges and are arranged in Key Performance areas(KPA’s) starting with Service delivery and infrastructure development :

KPA 1 Service delivery and infrastructure development

| High level strategic objectives | Key development priorities | Strategies to achieve objectives |
| --- | --- | --- |
| Adequate quality and quantity of affordable water available to all consumers in the municipal area | Provision of potable water at Marble Hall, Leeuwfontein and Zamenkomst | 1.Engage GSDM to sign Service level agreement for provision of water. 2.Undertake to improve access to sustainable and affordable water. 3.Undertake to maintain, extend and upgrade municipal water assets. 4.Undertake to provide cost-effective and sustainable water. 5.Undertake to provide free basic water to indingent households. 6.Ensure that all households have water by 2012 subject to funds being provided by GSDM . |
| Provide an adequate and appropriate sewer systems/systems for the urban part of the municipality as well as appropriate measures for the rural conditions | Provision of sanitation at Marble Hall, Leeuwfontein and Zamenkomst | 1.Engage GSDM to sign Service level agreement for provision of sanitation 2.Undertake to improve access to sustainable and affordable sanitation. 3.Undertake to maintain, extend and upgrade municipal sanitation assets. 4.Undertake to provide cost-effective and sustainable water. 5.Undertake to provide free basic sanitation to indigent households. 6.Ensure that all households have sanitation by 2012 subject to funds being provided by GSDM . |

| Provide affordable and reliable electricity to urban and rural areas in the municipality | 1.Provision of Bulk Electricity supply & Increase of capacity 2.Electricity Ring fencing 3.Mabitsa High Mast lights(1) 4.Matlerekeng and Rathoke Public lights(4) 5.Matla Ramoshebo high mast lights(5) 6.Marble Hall high mast lighting cluster(6) 7.Moganyaka South High Mast Lights(8) 8.Mohlalaotwane high mast lights(11) 9.Dichoeung high mast lights(14) | 1. Undertake Increasing electricity in Marble Hall town 2. Undertake separation electrical services from municipal services 3.Undertake Construction of high mast lights. 4.Engage with ESKOM to connect 697 housholds with electricity in 24 villages 4.Undertake to provide cost-effective and sustainable electricity infrastructure. 5.Undertake to improve access to sustainable and affordable electricity services. 3.Undertake to maintain, extend and upgrade municipal electricity assets. 4.Ensure that all households have access to electricity by 2012 subject to provision of funds by ESKOM. |
| --- | --- | --- |
| Ensure that the sports and recreation need of people in the municipal area is met | 1.Spitspunt community hall(1) 2.Doornlaagte community hall(2) 3.Mokgoaneng community hall refurbishment(2) 4.Keerom community hall(3) 5.Leeuwfontein sports field(7) 6.Phetwane community hall(12) 7.Letebejane community hall(12) 8.Morarela community hall(13) 9.Regae MPCC(14) | Undertake construction of community halls, sports field and MPCC |

| Provide safe and appropriate road and storm water networks in the municipal areas | 1.Uitvlugt internal roads(3) 2.Rathoke internal roads(4) 3.MatlalaRamoshebo to Matswayaneng low level bridge(5) 4.Leeuwfontein internal roads(7) 5.Moganyaka internal roads(8) 6.Moeding A internal roads(9) 7.Makgatle internal roads(9) 8.Mabitsi A internal roads(10) 9.Vaalbank internal roads(10) 11.Mohlalaotwane internal roads(11) 12.Elandskraal internal roads(13) | 1.Undertake construction of paved roads bridges,and bulk storm water. 2.Undertake to provide cost-effective and sustainable municipal roads and stormwater. 3.Undertake to improve access to viable and sustainable municipal roads and stormwater. 4.Undertake to extend and upgrade the municipal roads and stormwater. 5.Undertake to promote environmental sound practices and employment creation in the provision of storm water infrastructure. |
| --- | --- | --- |
| To promote a safe, clean sustainable and well managed environment in line with the Waste Management plan, Integrated Development Plan and Environmental Management plan of the Municipality. | Compliance of council with NEMA and council’s Integrated environmental plan | 1.Undertake development and implemention policies and by-laws 2.Undertake to provide an efficient refuse removal service in Marble Hall and Leeuwfontein and develop a plan to extend the service to Elandskraal, Matlerekeng and other areas 3.Proper disposal of collected waste at registered waste sites |
| Lead and direct the Community services for the Municipality so that the key strategic objectives in relation to Health are achieved | Provide programmes on HIV/AIDS prevention | 1.Undertake to develop and implement an HIV/AIDS strategy 2.Coordinate the activities of NGO’s, CBO’s and other interest groups so that there is an integrated approach in dealing with HIV/AIDS and other social issues |
| To develop a SLA with Sekhukhune district municipality in respect of disasters | Develop SLA | Engage GSDM to develop SLA for approval be Council |
| To promote a safe sustainable and well managed public transport system with the Integrated Development Plan of the Municipality. | Compliance of council with Land Transport Act | 1.Engage GSDM to develop public transport plan. 2.Engage with private owner of taxi rank in marble hall for council to take over facility. 3.Undertake process to establish taxi rank at Leeuwfontein |

KPA 2 Local economic development

| High level objectives | Key development priorities | Strategies to achieve objectives |
| --- | --- | --- |
| Facilitate and foster the economic development through planning and increased economic activity in the municipal area | 1.Development of a unique tourism destination (mini national park, Flag Boshielo eco-tourism etc) 2.Job creation through capital projects | 1.Engage stakeholders who have interest in development together for business expansion and retention 2.Undertake development of business plan 3.Undertake sourcing funds - involvement of tourism/parks boards required 4.Ensure to include capital projects that can be labour intensive - 5.Ensure that the designs of contracts are labour - intensive and monitoring of number of jobs - created 6. Negotiate with the District to use municipal terms of reference in relation to Labour intensive projects 7.Promote PPP and community partnership in building the community 8.Enhance cluster sector competiveness 9. Promote inter-governmental dialogue to agree on shared priorities and collective economic interventions and attract the private sector and non-governmental sector with incentives 10.Undertake compilation of marketing investment strategy 11.Align municipal LED efforts with the district, provincial and national LED objectives on infrastructure and skills development, |

KPA 3 Municipal financial viability

| High level objectives | Key development priorities | Strategies to achieve objectives |
| --- | --- | --- |
| Maximize revenue collection in all areas outside Marble Hall | Revenue collection outside Marble Hall | 1.Undertake Implementation of revenue enhancement strategy 2.Raise awareness concerning payment for services 3.Ensure proper financial management and investment of council resources |
| Develop and implement a budget process and system that allows for public participation and the alignment of the budget to community needs. | 1.Approved budget timetable 2.Accurate, credible and approved multi year budget 3.Monthly budget reports in accordance with legislation 4.Efficient management of approved budget and timeous identification of red lights | 1.Undertake to prepare budget process plan for approval by 31 August 2010. 2.Undertake to prepare and submit draft budget to the Municipal Manager for discussion with management and thereafter the finance portfolio committee 3.CFO undertake to prepare the budget process in line with GAMAP principles. 4.Budget process be communicated and implemented. e) Ensure budget is adopted by end of May 2011. |
| Manage procurement in order to ensure effective and efficient service delivery to the community | Capacitate local contractors on tender procedures and staff and councilors on SCM | 1.Undertake to facilitate of workshop with staff ,councilors and contractors 2.Undertake to hold SCM committee meetings within 3 weeks of closure date of tender 3.Include subcontracting clause in established company’s appointment letter . 4.Undertke to register of all local contractors on data base |
| To ensure sustainability of clean audit report | Sustain clean audit report | 1Undertake to compile all financial reports as prescribed by MFMA 2.Include progress on implementation of audit action plan in all monthly management meetings. |

KPA 4 Municipal transformation & Institutional development

| High level objectives | Key development priorities | Strategies to achieve objectives |
| --- | --- | --- |
| Develop and implement an Employment Equity Plan for the Council and promote adherence to the plan in the Corporate Services Department | Entrench employment equity through gender, disability and youth programmes streamlining within the workplace | Undertake to prepare plan in compliance with labour legislation Undertake to draw programmes and methods through which the objectives can be attained |
| Human Resources and Development Administration personnel related issues. Industrial relations | Ensure compliance with legislation on Hr issues and all policies | 1.Undertake to develop an institutional development business plan and facilitate its implementation. 2.Undertake to develop HR policies and plans. 3.Undertake to facilitate change management 4.Undertake to develop a policy and programmes around the issue of HIV/AIDS in the workplace 5. Undertake the purchasing of software that will assist in the management and administration of Human resource related information |

KPA 5 Good governance

| High level objectives | Key development priorities | Strategies to achieve objectives |
| --- | --- | --- |
| To ensure that all priority projects in the IDP are implemented for each financial year (for which funds have been allocated) | Annual IDP Review | 1. Undertake to draft process plan 2. Undertake the draft mini ward level IDP for the 14 wards 3. Public participation in IDP process (process plan 4.Undertake to prepare document for approval by 29 May 2010 |
| To ensure skills development for all staff | Implement skills development program | Undertake to have all employees undergo job-related training |
| To ensure compliance with EE act | Implement EE act | Undertake compliance with EE act to introduce Gender, Disability & Race Equity in all staff categories |
| To promote effective and efficient communication both internally and externally | 1.Ensure publication of Municipal events and community news from various wards within the municipality 2.Create opportunities for local citizenry in the issuing of comments, letters and other means of information sharing 3.Promote healthy and sound media relations between the Municipality and the public | 1.Undertake to publish and circulate quarterly newsletter 2.Undertake to Implement communication strategy which include good governance,public participation and strategies of the municipality with other spheres of government. 3.Undertake to mobilise public confidence in the understanding of the Municipality’s role in the community |
| Coordinate performance of the institution and management in line with powers and functions | To implement the PMS framework | 1.Undertake compilation PMS review framework 2.Undertake compilation of organizational performance plan in line with powers and functions 3.Undertake compilation of performance agreements and plans for unit managers 4.Ensure submission of organizational performance reports 5Undertake visiting projects to verify performance evidence 6.Ensure submission of performance reports to evaluation panel and Audit committee for evaluation. 7,Ensure coordination of compilation of annual report for submission to council 8.Ensure submission of annual report to oversight committee and council |

KPA6 Spatial Rationale

| High level objectives | Key development priorities | Strategies to achieve objectives |
| --- | --- | --- |
| Ensure lawful security of tenure | Land use management | Undertake drafting of land use management system |
| Develop, gain approval for and implement a spatial development framework | Review of SDF | 1.Ensure to engage service provider to review SDF. 2.Undertake drafting in liaison with community. 3.Ensure draft is approved by Council l. |

CHAPTER  4 – PROJECTS PHASE

13.	MUNICIPAL PROJECTS

13.1 Following are a summary of the identified projects of the community:

| PRIORITY ISSUE | COMMUNITY NEED |
| --- | --- |
| Water | 16576 RDP level |
| Sanitation | 29169 VIP toilets |
| Electricity | 1608 connections |
| Housing | 8195 RDP houses |
| Roads and storm water | 404km internal roads to be graded including provision of stormwater, 40km roads to be paved and 21 bridges to be build |
| Clinic | Malebitsa,Mokgwaneng,Doornlaagte,Mamphogko,Magatle,Matilu, Ngwalemong”A” ,Greenside,Gareagapola,Matsedeng,Mogalatsane and Dichoeung |
| Schools | 4 Secondary,8 Primary,11 Admin blocks,23 block class rooms,8 Pre-schools, 10 creches, 25 schools - toilets,7 schools- renovation and 14 schools – Libraries/laboritries |
| Local Economic Development | Investment and Marketing strategy Tourism - Eco Tourism Flag Boshielo and conservancy and educational tourism Meat – Productivity improvements in livestock Horticulture – Marketing ,emerging farming development and Logistic Hub Informal economy – Establishment of support system |
| Spatial planning | LUMS implementation |

MIG PROJECTS APPROVED BUDGET FOR 2011/12

| Item No | PROJECT | MIG APPROVED BUDGET | REQUIRED BUDGET |
| --- | --- | --- | --- |
| 1 | Mathukuthela Low Bridge | R 2,500,000.00 | R 2,300,587.00 |
| 2 | Manotolwaneng Low Bridge | R 2,500,000.00 | R 2,288,987.50 |
| 3 | Mokgwaneng Community Hall | R 400,000.00 | R 400,000.00 |
| 4 | Vaalbank Access Road | R 7,000,000.00 | R 588,000.00 |
| 5 | Moganyaka access road | R 21,000,000.00 | R 1,764,000.00 |
| 6 | Malebitsa Internal Roads | R 14,000,000.00 | R 1,176,000.00 |
| 7 | Klopper Community Hall | R 4,500,000.00 | R 4,500,000.00 |
| 8 | Marblehall Stormwater Phase II. | R 4,000,000.00 | R 4,000,000.00 |
| 9 | Rathoke Internal Roads | R 30,030,839.21 | R - |
| 10 | Leeuwfontein Internal Roads | R 18,500,000.00 | R - |
| 11 | Project Management Unit | R 726,683.27 | R 726,683.27 |
| TOTAL |  |  | R 17,744,257.77 |

13.2 	Following are the projects for which funds have been obtained:

| Priority Issue/Programme 1: Water Infrastructure |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Adequate quality and quantity of affordable water available to all consumers in the municipal area in terms of the Water Sector Plan |  |  |  |  |  | Target for the Year: 20% of the total households in the municipal area |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 2075 | Water | - Marble Hall Leeuwfontein - Matlerekeng | Marble Hall Leeuwfontein Matlerekeng | To provide water services as per SLA | Free access to potable water facilities |  | 2011/12 | SDM | SDM | SDM |
| 2074 | Water services network maintenance | - Marble Hall Leeuwfontein - Matlerekeng | Marble Hall Leeuwfontein Matlerekeng | To ensure systematic provision of maintenance services | To maintain infrastructure |  | 2011/12 | SDM | SDM | SDM |
| 2006 | Moutse Bulk water supply & cost recovery | - Moutse | Moutse | To compile the water feasibility study such that the water source, storage, supply and distribution can be determined | To provide potable water to minimum of basic level of service and plan for intermediate and full services |  | 2011/12 | 5 000 000 | SDM | SDM |
| 2076 | Cost Recovery ( WDM Project) Flag-Boshielo Scheme | - EPMLM | EPMLM | To supply water | To supply water |  | 2011/12 | 5 625 631 | SDM | SDM |
| 2077 | Installation of flow control valves at 91 Reservoirs (WCM) and Extension of Flag Boshielo WTW to 25Ml/d | - EPMLM | EPMLM | To supply water | To supply water |  | 2011/12 | 5,460,000 | SDM | SDM |
| 2078 | Flag Boshielo WTW Package Plant | - EPMLM | EPMLM | To supply water | To supply water |  | 2011/12 | 7,000,000 | SDM | SDM |

| Priority Issue/Programme 2: Sanitation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Provide an adequate and appropriate sewer system/systems for the urban part of the municipality as well as appropriate measures for the rural conditions |  |  |  |  |  | Target for the Year: 30% of the total households in the municipal area |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 3030 | Sanitation | - Marble Hall Leeuwfontein - Matlerekeng | Marble Hall Leeuwfontein Matlerekeng | To provide sanitation services as per SLA | Free access to potable sanitation facilities |  | 2011/12 | SDM | SDM | SDM |
| 3029 | Sanitation services network maintenance | - Marble Hall - Leeuwfontein - Matlerekeng | Marble Hall Leeuwfontein Matlerekeng | To ensure systematic provision of maintenance services | To maintain infrastructure |  | 2011/12 | SDM | SDM | SDM |
| 3031 | Sanitation Moutse (Rathoke, Matlala-Ramoshebo & Uitvlugte) | - Moutse (Rathoke, Matlala-Ramoshebo & Uitvlugte) | Moutse (Rathoke, Matlala-Ramoshebo & Uitvlugte) | To supply sanitation to basic level of service | To supply sanitation to basic level of service |  | 2011/12 | 5 400 000 | SDM | SDM |

| Priority Issue/Programme 3: Electricity |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Provide affordable and reliable electricity to urban and rural areas in the municipality |  |  |  |  |  | Target for the Year: 30% of total households with electricity in the municipal area |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 4072 | Free basic electricity | - Marble Hall | EPMLM community | To provide FBE to beneficiary as mandated by Government | To supply FBE to indigent customers that apply and is registered and approved as beneficiaries 1.Registration 2.Revise policy 3.Submit to ESKOM 4.Public awareness |  | 2011/12 | 1 750 000 | EPMLM Vote 260260245 | EPMLM |
| 4008 | Machinery and equipment | - Marble Hall | Marble Hall | To prolong life of equipment and increase safety & reliability according to NERSA license conditions | Compliance with NERSA license. Compliance with Insurance Reliable service Prolonged life Increased value of asset. |  | 2011/12 | 35 000 | EPMLM Vote 260/235090 | EPMLM |
| 4011 | Bulk supply to EXT 6 | - Marble Hall | Marble Hall | To ensure reliable and safe supply by installing a ring feed to Ext 6 phase 3 and upgrading of Ext 2 LT | Number of ring main feed to be installed |  | 2011/12 | 300 000 | EPMLM Vote 260/235110 | EPMLM |
| 4012 | Network maintenance Public lighting | - GMHM | GMHM | To supply effective and sufficient electricity to the areas with public lighting | Well managed and maintained facilities |  | 2011/12 | 500 000 | EPMLM Vote 260/235150 | EPMLM |

| 4014 | Machinery & equipment | - EPMLM | EPMLM | Machinery & equipment | Machinery & equipment | 2011/12 | 53 000 | EPMLM Vote 260/235090 | EPMLM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 4006 | Mamphokgo | - Mamphokgo | Mamphokgo community | To install bulk electricity supply and network | To connect 111 households and energize | 2011/2012 | 1 443 000 | Eskom | EPMLM ESKOM |
| 4052 | Matlerekeng | - Matlerekeng | Matlerekeng community | To install bulk electricity supply and network | To connect 160 households and energize | 2011/2012 | 1 422 468 | Eskom | EPMLM ESKOM |
| 4073 | Makgatle A | Makgatle A | Makgatle A | To install bulk electricity supply and network | To provide 87 house connections | 2011/2012 | 1,444,878 | Eskom | EPMLM ESKOM |
| 4074 | Malebitsa | Malebitsa | Malebitsa | To install bulk electricity supply and network | To provide 121 house connections | 2011/2012 | 1,090,590 | Eskom | EPMLM ESKOM |
| 4075 | Matlala -A-Ramoshebo | Matlala -A-Ramoshebo | Matlala -A-Ramoshebo | To install bulk electricity supply and network | To provide 22 house connections | 2011/2012 | 330,000 | Eskom | EPMLM ESKOM |
| 4076 | Arial platform | Marble Hall | EPMLM | To purchase aerial platform | Aerial platform | 2011/12 | 570 000 | EPMLM Capital Vote 260/305010 | EPMLM |
| 4077 | Remote metering | Marble Hall | EPMLM | To purchase remote metering | Remote metering | 2011/12 | 200 000 | EPMLM Capital Vote 260/305 | EPMLM |

| Priority Issue/Programme 4: Roads and Stormwater |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Provide safe and appropriate road and storm water networks in the municipal areas |  |  |  |  |  | Target for the Year: 1500KMs of safe road and storm water network |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 5027 | Tar R29 from Matlerekeng to Rathoke | - Matlerekeng - Rathoke | Matlerekeng Rathoke community | To tar R29 from Matlerekeng to Rathoke | To tar R29 from Matlerekeng to Rathoke |  | 30 June 2012 | 12,500,000 | SDM | SDM |
| 5082 | Mathukuthela Bridge | Mathukuthela | Mathukuthela | To improve accessibility of other portion of the area | Complete and functional low level bridge |  | 30 June 2012 | 2,300,587 | Council/MIG Vote 850/305061 | EPMLM |
| 5083 | Manotolwaneng Bridge | - Manotolwaneng | Manotolwaneng | To improve accessibility of other portion of the area | Complete and functional low level bridge |  | 30 June 2012 | 2,288,987 | Council/MIG Vote 850/305062 | EPMLM |
| 5084 | Marble Hall Bulk Stormwater Phase 2 | - Marble Hall Marble Hall | Marble Hall | To control the stormwater drainage efficiently | Complete and functional stormwater drainage |  | 30 June 2012 | 4,000,000 | Council/MIG | EPMLM |
| 5080 | Tompi Seleka / Kromdraai to Mogaladi D4370 | Ward 12 | Ward 12 community | Upgrading of road from gravel to tar | To tar 25km road |  | 30 June 2012 | 66 000 000 | Road agency Limpopo | RAL |
| 5019 | Malebitsa internal roads | Malebitsa | Malebitsa | Upgrading of internal roads | To upgrade internal roads |  | 30 June 2012 | 1,176,000 | Council/MIG Vote 850/305075 | EPMLM |
| 5074 | Keerom/Uitvlug road | Keerom Uitvlugt | Keerom Uitvlugt | Upgrading of road from gravel to tar | To tar link road |  | 30 June 2012 | RAL | RAL | RAL |
| 5018 | Moganyaka access road | Moganyaka | Moganyaka | Upgrading of access road | To upgrade access road |  | 30 June 2012 | 1,764,000 | Council/MIG Vote 850/305064 | EPMLM |
| 5047 | Vaalbank internal road | Vaalbank | Vaalbank | Upgrading of access road | To upgrade access road |  | 30 June 2012 | 588,000 | Council/MIG Vote 850/305076 | EPMLM |
| 5086 | D2535-Road Rehabilitation (Including Widening) |  | EPMLM | D2535 - Road Rehabilitation (Including Widening) -LDRT | To rehabilitate and widen D2535 road |  | 30 June 2012 | 7 500 000 | RAL | RAL |
| 5087 | D4285 -Ga-Matlala / Ragaphela to Tsimanyane to Kromdraai | Ward 10,11 & 12 | Ward 10,11 & 12 | D4285 - Upgrading (gravel to bituminous / tar surface) | To upgrade road from gravel to tar |  | 30 June 2012 | 48 900 000 | RAL | RAL |
| 5088 | D2900 to Zamerkost to Uitvlugt to Doornlaagte to Tshikanosi (Leeuwkuil) | Ward 2& 3 | Ward 2& 3 | D2664, D2919, D2922, D2919 - Upgrading (gravel to tar) | To upgrade road from gravel to tar |  | 30 June 2012 | 21 500 000 | RAL | RAL |
| 5089 | Malebitsa to Driefontein access road | Malebitsa Driefontein | Malebitsa Driefontein | To provide improved mobility and accessibility | To provide improved mobility and accessibility |  | 30 June 2012 | 15,000,000 | SDM | SDM |
| 5090 | Tshikanoshi to Malebitsa Access Road | Tshikanoshi Malebitsa | Tshikanoshi tMalebitsa | To provide improved mobility and accessibility | To provide improved mobility and accessibility |  | 30 June 2012 | 20,000,000 | SDM | SDM |
| 5091 | Purchasing of the TLB | EPMLM | EPMLM | Purchasing of the TLB | Number of TLB to be purchased |  | 30 June 2012 | 780 000 | EPMLM Capital vote 650/305070 | EPMLM |
| 5092 | Purchasing of the Bomag roller(Construction) | EPMLM | EPMLM | Purchasing of the Bomag roller(Construction) | Number of Bomag roller to be purchased |  | 30 June 2012 | 1 000 000 | EPMLM Capital vote 650/305070 | EPMLM |
| 5093 | Purchasing of the Low bed truck | EPMLM | EPMLM | Purchasing of the Low bed truck | Number of trucks to be purchased |  | 30 June 2012 | 1 800 000 | EPMLM Capital vote 650/305070 | EPMLM |
| 5094 | Purchasing of a 2 Tipper truck | EPMLM | EPMLM | Purchasing of a 2 Tipper truck | Number of Tipper Truck to be purchased |  | 30 June 2012 | 1 400 000 | EPMLM Capital vote 650/305070 | EPMLM |
| 5095 | Purchasing of 1 number of LDV’S | EPMLM | EPMLM | Purchasing of 1 number of LDV’S | Number of vehicle to be purchased |  | 30 June 2012 | 300 000 | EPMLM Capital vote 650/305070 | EPMLM |

| Priority Issue/Programme 5: Waste Management and Refuse Disposal |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Provide a safe, effective and economical waste management and refuse disposal system |  |  |  |  |  | Target for the Year: 10% increase in the households satisfaction index |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 1269 | To install street refuse bins in Marble Hall | - Marble Hall | EPMLM | To ensure efficient waste management systems by implementing the solid waste implementation plan and to continuously improve the systems | Effective facilities for dumping of collected waste and littering of waste in streets |  | 30 June 2012 | 150 000 | EPMLM Capital vote 360/305070 | EPMLM |
| 1270 | Solid waste | - Marble Hall | Leeufontein RDP , Mokganyaka | Expand refuse removal services to Leeufontein RDP , Mokganyaka | Serviced areas of Leeufontein RDP, Mokganyaka |  | 30 June 2012 | 250 000 | EPMLM Capital Vote 360/305071 | EPMLM |

| Priority Issue/Programme 6: Transportation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Promote an effective and affordable transport system to cater for the whole of the municipal area |  |  |  |  |  | Target for the Year: 1 transport infrastructure and system project |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 5085 | Weighbridge | Marble Hall | EPMLM | Rathoke Construction of weighbridge - LDRT | To construct weighbridge |  | 30 June 2012 | 4 100 000 | LDRT | LDRT |

| Priority Issue/Programme 7: Housing |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Ensure that the housing need of people in the municipal area is met |  |  |  |  |  | Target for the Year: 15 000 households with housing |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 8001 |  |  |  | To build 60 RDP houses |  |  | 30 June 2012 | DLGH | DLGH | DLGH |
| 8002 |  |  |  | To build 50 RDP houses |  |  | 30 June 2012 | DLGH | DLGH | DLGH |
| 8003 |  |  |  | To build 175 RDP houses |  |  | 30 June 2012 | DLGH | DLGH | DLGH |

| Priority Issue/Programme 8: Cemeteries |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Provide safe, appropriate and accessible burial space/cemetery space in the municipal area |  |  |  |  |  | Target for the Year: < 1 family with a complaint |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 9001 | Fencing of cemeteries | EPMLM | EPMLM Community | To fence two cemeteries | Two cemeteries fenced |  | 30 June 2012 | 550 000 | EPMLM vote 425/260799 | EPMLM ` |
| `9002 | New cemetery in Marble Hall town | - Marble Hall | EPMLM Community | To establish new cemetery in Marble Hall town | New cemetery |  | 30 June 2012 | 1 000 000 | EPMLM Capital vote 425/305111 | EPMLM |

| Priority Issue/Programme 9: Posts and Telecommunications |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: To ensure that a basic communication infrastructure is within reach of all the inhabitants in the municipal area |  |  |  |  |  | Target for the Year: 2 Communication infrastructure projects |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |

| Priority Issue/Programme 10: Land Ownership and Land Use Management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Ensure lawful security of tenure |  |  |  |  |  | Target for the Year: 100% compliance of land tenure legislation |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 1242 | Annual update and revision of IDP(2010/11) | - GMHM | EPMLM communities | To compile IDP revision for 2009/10 | Compilation of IDP revision |  | 31 May 2012 | 100 000 | EPMLM Vote 760/260025 | EPMLM |

| Priority Issue/Programme 11: Local Economic Development and Job Creation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Ensure economic growth in all sectors of the economy in order to curb unemployment and related negative issues |  |  |  |  |  | Target for the Year: 3% GDP for the area |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 12107 | Moganyaka grape | Moganyaka | Moganyaka community | Construction of a Pack house | To construct pack house |  | 2011/12 | 1 500 000 | LDA | LDA |
| 12041 | Special Projects | EPMLM | EPMLM communities | To Implement projects eminating from EU LED/Urban renewal strategies | Implementing projects eminating from LED/Urban renewal strategies.EU funded projects |  | 30 June 2012 | 200 000 | EPMLM Vote 760/260150 | EPMLM |
| 1308 | Schuinsdraai Nature Reserve Development | Schuinsdraai | EPMLM communities | Develop tourist accommodation | To develop tourist accommodation |  | 30 June 2012 | 19 178 000 | DEAT | DEAT |

| 12110 | Tompi Seleka Rehabilitation of Bulk water supply | Tompi Seleka | Tompi Seleka | Rehabilitation of bulk water supply | To rehabilitate bulk water supply | 2011/12 | 100 000 | LDA | LDA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12112 | Roodewal Rehabilitation of irrigation Scheme | Roodewal | Roodewal | Rehabilitation of irrigation Scheme | To rehabilitate irrigation scheme | 2011/12 | 400 000 | LDA | LDA |
| 12111 | Organic farming cluster | EPMLM | EPMLM | Create 15 organic farms | To create 15 organic farms | 2011/12 | 5 579 150 | DTI | EPMLM |
| 12112 | Kopano Disable | EPMLM | EPMLM | Sprinkler and centre pivot irrigation for 26,7 ha | Sprinkler and centre pivot irrigation for 26,7 ha | 2011/12 | 2,000,000 | LDA | LDA |
| 12113 | Sekhukhune Poultry Projects | EPMLM | EPMLM | Fetakgomo/ Ephraim Mogale 9x1000 capacity broiler houses | Fetakgomo/ Ephraim Mogale 9x1000 capacity broiler houses | 2011/12 | 1,500,000 | LDA | LDA |
| 12114 | Mabodibeng | EPMLM | EPMLM | Fencing. Borehole drilling & equipping. Cold room. Pasturizing unit. | Fencing. Borehole drilling & equipping. Cold room. Pasturizing unit. | 2011/12 | 450,000 | LDA | LDA |
| 12115 | Cattle handling facilities | EPMLM | EPMLM | Construction of a basic cattle handling facility | Construction of a basic cattle handling facility | 2011/12 | 60,000 | LDA | LDA |
| 12116 | Cattle handling facilities | EPMLM | EPMLM | Construction of a basic cattle handling facility | Construction of a basic cattle handling facility | 2011/12 | 60,000 | LDA | LDA |
| 12117 | Cattle handling facilities | EPMLM | EPMLM | Construction of a basic cattle handling facility | Construction of a basic cattle handling facility | 2011/12 | 60,000 | LDA | LDA |
| 12118 | Elandskraal Block C & E | Elandskraal | Elandskraal | Rehabilitation of irrigation Scheme | Rehabilitation of irrigation Scheme | 2011/12 | 2 375 000 | LDA | LDA |
| 12119 | Tompi Seleka Bio-diesel | EPMLM | Tompi Seleka | Bio-diesel plant | Bio-diesel plant | 2011/12 | 7 600 000 | LDA | LDA |
| 12120 | Marketing and Investment strategy | EPMLM | EPMLM | To entice investors to Marble Hall and Industrial investors retention | To entice investors to Marble Hall and Industrial investors retention | 2011/12 | NIL | EPMLM | EPMLM |
| 12121 | Eco tourism Flag Boshielo dam nature reserve development | EPMLM | EPMLM | Develop a unique eco-tourism destination | Develop a unique eco-tourism destination | 2011/12 | NIL | EPMLM | EPMLM |
| 12122 | Horticulture cluster | EPMLM | EPMLM | To improve the competitiveness of horticulture cluster by obtaining funds to assist viable emerging businesses | To improve the competitiveness of horticulture cluster by obtaining funds to assist viable emerging businesses | 2011/12 | NIL | EPMLM | EPMLM |
| 12123 | Red meat cluster | EPMLM | EPMLM | To improve the competitiveness of red meat cluster by obtaining funds to assist emerging businesses | To improve the competitiveness of red meat cluster by obtaining funds to assist emerging businesses | 2011/12 | NIL | EPMLM | EPMLM |
| 12124 | Tourism cluster | EPMLM | EPMLM | Promote economic growth in the tourism industry by establishing information centre | Promote economic growth in the tourism industry by establishing information centre | 2011/12 | NIL | EPMLM | EPMLM |

| 12125 | Informal economic cluster | EPMLM | EPMLM | Promote economic growth in the informal industry by training traders | Promote economic growth in the informal industry by training traders | 2011/12 | 10 000 | EPMLM 760/260150 | EPMLM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12126 | Logistic Hub | EPMLM | EPMLM | Establish logistic hub | Establish logistic hub | 2011/12 |  |  |  |
| 12127 | Marble Hall festival | EPMLM | EPMLM | Develop tourism in the municipality by attracting tourists and possible investors to the area by showcasing our natural resources and products | Develop tourism in the municipality by attracting tourists and possible investors to the area by showcasing our natural resources and products | 2011/12 | 20 000 | EPMLM 760/260150 | EPMLM |
| 12128 | Coordinate effective use of the local business support center | EPMLM | EPMLM | Access to information, advice and assistance regarding LED related matters | Access to information, advice and assistance regarding LED related matters | 2011/12 | NIL | EPMLM | EPMLM |
| 12129 | Fundraising | EPMLM | EPMLM | Increase available funds by 5% for implementation of projects | Increase available funds by 5% for implementation of projects | 2011/12 | NIL | EPMLM | EPMLM |
| 12130 | Coordination of the drafting of sector plans | EPMLM | EPMLM | Review SDF and LED strategy | Review SDF and LED strategy | 2011/12 | NIL | EPMLM | EPMLM |
| 12131 | Urban renewal strategy | EPMLM | EPMLM | Promote economic growth by market linkages | Promote economic growth by market linkages | 2011/12 | NIL | EPMLM | EPMLM |
| 12132 | Review LED strategy | EPMLM | EPMLM | To review LED strategy | Number of strategy review | 2011/12 | NIL | EPMLM | EPMLM |

| Priority Issue/Programme 12: Health |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Promote the development of a healthy community and an effective healthcare environment |  |  |  |  |  | Target for the Year: < 15 cases a month |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 13019 | Occupational Health Safety | EPMLM | GMHM community | To ensure the compliance of the workplace to the OH&SA and regulations | OHS compliant facilities,trained officials and working committees,safer workplace and monitoring reporting |  | 30 June 2012 |  | EPMLM Vote 510/260730 | EPMLM |
| 13022 | Provide programmes on HIV/AIDS | EPMLM | GMHM | To provide programmes on HIV/AIDS | Successful campaigns, Interaction with affected people and provision of support |  | 30 June 2012 |  | EPMLM Vote 375/260560 | EPMLM |
| 13023 | Matlala EMS | Tsimanyane | EPMLM | Ambulance base | Ambulance base |  | 30 June 2012 | 5 100 000 | DOH | SAKHIWO HS |
| 13024 | Matlala Boiler Replacement | Tsimanyane | EPMLM | Hospital – District | Hospital – District |  | 30 June 2012 | 500 000 | DOH | SAKHIWO HS |
| 13035 | Matlala Hospital | Tsimanyane | EPMLM | Accommodation | Accommodation |  | 30 June 2012 | 307 000 | DOH | SAKHIWO HS |

| Priority Issue/Programme 13: Social Welfare |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Ensure improved living standards and promote humane living conditions for every member of society |  |  |  |  |  | Target for the Year: 10% increase in the household satisfaction index |  |  |  |  |
| Project ID | Project Name | Project Location Project Beneficiaries |  | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 14019 | Bakone Disabled Care centre | Serething | Serething | Establish disabled care centre | To establish disabled care centre |  | 30 June 2012 | Lottery fund | Lottery | Lottery |

| Priority Issue/Programme 14: Education |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Promote the provision of effective education to all learners and equip people to lead a meaningful life |  |  |  |  |  | Target for the Year: 350 Learners and 700 scholars |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 15002 | Marble Hall Secondary School | - Marble Hall | Marble Hall community | New Secondary School - Public ordinary schools | New Secondary School - Public ordinary schools |  | 2011-12 | 10 805 000 | DOE | DPW |

| Priority Issue/Programme 15: Safety and Security |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Ensure a safe, secure and humane environment for inhabitants of the municipality |  |  |  |  |  | Target for the Year: 10% reduction |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |

| Priority Issue/Programme 16: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Ensure accessibility to Sport and Recreation facilities for all the inhabitants of the municipal area |  |  |  |  |  | Target for the Year: 30000 inhabitants attending major sporting and recreational events |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 17010 | Purchace equipment for maintenance of parks and sports fields | EPMLM | EPMLM communities | To ensure the development of new facilities and the maintenance of existing parks/grounds and the beautification of the town | Purchase and distribution of equipment and proper maintained parks,open spaces and sports grounds |  | 30 June 2011 | 21 200 | EPMLM Vote 425/260170 | EPMLM |
| 17012 | Parks | EPMLM | EPMLM communities | Greening of the municipality – biodiversity conservation | 250 trees planted |  | 30 June 2012 | 150 000 | EPMLM Capital Vote 425/305070 | EPMLM |

| Priority Issue/Programme 19: Environmental Management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Ensure that the general environment is protected and promoted in a sustainable and ongoing way |  |  |  |  |  | Target for the Year: 30% target achievement |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |

| Priority Issue/Programme 20: Training and Skills Development |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Improve employee skills and competencies |  |  |  |  |  | Target for the Year: 25% of employees |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 21004 | Bursary fund staff | EPMLM | EPMLM community | To provide bursaries to staff | To provide bursaries to staff |  | 30 June 2012 |  | Council Vote | EPMLM |
| 21005 | Bursary fund COMMUNITY | EPMLM | EPMLM community | To provide bursaries to community | To provide bursaries to community |  | 30 June 2012 |  | Council Vote | EPMLM |

| Priority Issue/Programme 21: Staff Component and Appointments |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Appoint employees to all vacant posts |  |  |  |  |  | Target for the Year: 15 employees at management level |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 22000 | Appointments of new staff in accordance with vacancies on oganigram | Marble Hall | GMHM communities | To fil vacancies on oganigram | Filling of vacancies on oganigram |  | 30 June 2012 |  | EPMLM | EPMLM |

| Priority Issue/Programme 22: Organisational Infrastructure and Assets |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Institutional arrangements and office space |  |  |  |  |  | Target for the Year: 98% uptime and running of the systems |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 23003 | Office Furniture & equipment | Marble Hall | EPMLM communities | To purchase furniture & equipment | Purchasing of furniture & equipoment |  | 30 June 2012 | 800 000 | EPMLM Capital Vote 500/ 305050 | EPMLM |
| 23005 | Municipal buildings | Marble Hall | EPMLM communities | To extend offices | To extend offices |  | 30 June 2012 | 880 000 | EPMLM Capital vote 625/305054 | EPMLM |
| 23009 | Maintenance of all municipal buildings and facilities | Marble Hall | EPMLM communities | To improve conditions of municipal buildings | Sustainable municipal buildings |  | 30 June 2012 | R350 000 | EPMLM Vote 625/235030 | EPMLM |
| 23006 | Programing | Marble Hall | EPMLM communities | Check licensing and agreements on ICT | Fully functional ICT work environment Digital and electronic record keeping and archives |  | 30 June 2012 |  | EPMLM Vote 500/260430 | EPMLM |
| 23011 | Vehicle corporate services | Marble Hall | EPMLM communities | To purchase new vehicle | Purchasing of new vehicle |  | 30 June 2012 |  | EPMLM Capital Vote 450/305001 | EPMLM |
| 23012 | Vehicle Finance services | Marble Hall | EPMLM communities | To purchase new vehicle | Purchasing of new vehicle |  | 30 June 2012 |  | EPMLM Capital Vote 775/305071 | EPMLM |
| 23013 | Vehicle Traffic services | Marble Hall | EPMLM communities | To purchase new vehicle | Purchasing of new vehicle |  | 30 June 2012 |  | EPMLM Capital Vote 225/305903 | EPMLM |
| 23014 | Airconditioners | Marble Hall | EPMLM communities | To purchase air conditioners | Purchasing of air conditioners |  | 30 June 2012 |  | EPMLM Capital Vote 625/305067 | EPMLM |
| 23015 | Project Management Unit | Marble Hall | EPMLM communities |  |  |  | 30 June 2012 |  | EPMLM Vote 625/305067 | EPMLM |
| 23016 | Rehabilitation of admin block | Marble Hall | EPMLM communities | To rehabilitate admin block | To rehabilitate admin block |  | 30 June 2012 | 600 000 | EPMLM Capital Vote 625/305 | EPMLM |
| 23017 | Rehabilitation of municipal hall | Marble Hall | EPMLM communities | To rehabilitate municipal hall | To rehabilitate municipal hall |  | 30 June 2012 | 400 000 | EPMLM Capital Vote 625/305 | EPMLM |
| 23018 | Traffic guard house | Marble Hall | EPMLM communities | To build guard house | To build guard house |  | 30 June 2012 | 150 000 | EPMLM Capital Vote 220/305022 | EPMLM |
| 23019 | Upgrading of hawker stalls | Marble Hall | EPMLM communities | To upgrade hawker stalls | To upgrade hawker stalls |  | 30 June 2012 | 350 000 | EPMLM Capital Vote 225/305 | EPMLM |
| 23020 | Doornlaagte /Klopper community hall | - Doornlaagte | Doornlaagte community | To build community hall | To build community hall |  | 30 June 2012 | 3 500 000 | EPMLM Capital vote/MIG Vote 625/305077 | EPMLM |
| 23021 | Mokgwaneng Community Hall | - Mokgwaneng | Mokgwaneng community | Renovate community hall | To renovate community hall |  | 30 June 2012 | 550 000 | EPMLM Capital/MIG Vote 625/305051 | EPMLM |

| Priority Issue/Programme 24: Service Delivery Standards (Batho Pele) |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Implementation of the Batho Pele Principles |  |  |  |  |  | Target for the Year: 100% compliance and customer satisfaction |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 24000 | Batho Pele | Marble Hall | EPMLM community | Promote public awareness on customer Care relations | Implementable Service Standards |  | 30 June 2012 |  | EPMLM 510/260472 | EPMLM |
| 24001 | Corporate newsletter and related publications | Marble Hall | EPMLM community | Ensure publication of Municipal events and community news from various wards within the municipality Create opportunities for local citizenry in the issuing of comments, letters and other means of information sharing Promote healthy and sound media relations between the Municipality and the public | Number of newsletters issued |  | 30 June 2012 |  | EPMLM Vote 450/260021 | EPMLM |
| 24002 | Internal Communication | Marble Hall | EPMLM community | To optimize public’s access to Council information through the remote electronic media platforms | To optimize public’s access to Council information through the remote electronic media platforms |  | 30 June 2012 | NIL | EPMLM | EPMLM |

| 24003 | Development of Administrative Services | Marble Hall | EPMLM community | To optimize coordination and coherence of Council messages | To optimize coordination and coherence of Council messages | 30 June 2012 | NIL | EPMLM | EPMLM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | To enhance accessibility of Council information through se of relevant indigenous languages | To enhance accessibility of Council information through se of relevant indigenous languages | 30 June 2012 | NIL | EPMLM | EPMLM |
|  |  |  |  | Develop an effective and efficient event management strategy | Develop an effective and efficient event management strategy | 30 June 2012 | NIL | EPMLM | EPMLM |

| Priority Issue/Programme 25: Performance Management System |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Develop appropriate key performance indicators |  |  |  |  |  | Target for the Year: According to prescribed and set standards |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |

| 25001 | PMS | EPMLM | EPMLM communities | Cascade PMS to other staff | PMS cascaded to other staff | 30 June 2012 |  | EPMLM Vote 750/260146 | EPMLM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

| Priority Issue/Programme 26: Financial Management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Improve debtor collection |  |  |  |  |  | Target for the Year: 2% and below 8% |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 26001 | Revenue enhancement strategy implementation | EPMLM | EPMLM communities | To maximize the collection of revenue | % increase in revenue collected. |  | 30 June 2012 | 300 000 | EPMLM Vote 775/260714 | EPMLM |
| 26002 | Programming | EPMLM | EPMLM communities | Programming | Programming |  | 30 June 2012 | 920 000 | EPMLM Vote 775/260430 | EPMLM |
| 26004 | Compile GRAP compliant asset register | EPMLM | EPMLM communities | To ensure compliance with GRAP standards | % GRAP compliant asset register compiled |  | 30 June 2012 | 1 800 000 | EPMLM Vote 775/260780 | EPMLM |
| 26005 | Review indigent register | EPMLM | EPMLM communities | To ensure accessibility of free basic services to the community | % review of indigent register |  | 30 June 2012 | 50 000 | EPMLM Vote 775/260713 | EPMLM |
| 26006 | Appoint finance interns | EPMLM | EPMLM communities | To ensure compliance with National Treasury’s budget reforms | Number of interns appointed |  | 30 June 2012 | 500 000 | EPMLM Vote 775/ | EPMLM |
| 26007 | Conduct feasibility study on new financial system | EPMLM | EPMLM communities | To ensure proper accounting of transactions | % feasibility study conducted on new financial system |  | 30 June 2012 | 300 000 | EPMLM Vote 775/ | EPMLM |
| 26008 | Conduct half yearly asset verifications | EPMLM | EPMLM communities | To improve the management of Assets | Number of assets verifications conducted |  | 30 June 2012 | 500 000 | EPMLM Vote 775/ | EPMLM |
| 26009 | Compilation of general valuation and supplementary valuation roll. | EPMLM | EPMLM communities | To compile a supplementary valuation roll in compliance with the MPRA | % of Supplementary valuation roll compiled. |  | 30 June 2012 | 1 279 860 | EPMLM Vote 775/ | EPMLM |
| 26010 | Compile financial statements in terms of Gamap/Grap format. | EPMLM | EPMLM communities | To ensure compliance with GRAP standards | % compilation of GRAP compliant 2010/2011 Annual Financial Statements |  | 30 June 2012 | 700 000 | EPMLM Vote 775/ | EPMLM |
| 26011 | Clear audit queries | EPMLM | EPMLM communities | To improve compliance with financial management regulations | % development and implementation of audit Action plan to address audit queries for 2010/2011. |  | 30 June 2012 | 50 000 | EPMLM Vote 775/ | EPMLM |
| 26012 | Compile budget for 2012/2013 MTREF | EPMLM | EPMLM communities | To comply with the MFMA with regards to budget and reporting requirements. | Number of budget Community participation programmes conducted. |  | 30 June 2012 | 217 300 | EPMLM Vote 775/ | EPMLM |

| Priority Issue/Programme 27: Fleet Management |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Improve vehicle management |  |  |  |  |  | Target for the Year: 5% vehicle replacement |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 27001 | Vehicle tracking and control | Marble Hall | EPMLM communities | To manage and control utilization of municipal vehicle fleet | Effective use of vehicles and reduce abuse |  | 30 June 2012 |  | EPMLM Vote 640/260816 | EPMLM |

| Priority Issue/Programme 28: Internal Audit |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Improve internal controls |  |  |  |  |  | Target for the Year: 5% vehicle replacement |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 28001 | Quarterly Internal Audit Engagements | Marble Hall | EPMLM communities | To provide an independent objective assurance | To provide an independent objective assurance |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 28002 | Quarterly SDBIP Performance Reports and AC Progress reports | Marble Hall | EPMLM communities | To ensure accountability | To ensure accountability |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 28003 | 2011/2012 Internal Audit Charter | Marble Hall | EPMLM communities | Define and set out the nature, role purpose and responsibilities and authority of IA within EMLM | Define and set out the nature, role purpose and responsibilities and authority of IA within EMLM |  | 30 June 2012 | nil | EPMLM | EPMLM |

| 28004 | To facilitate risk assessment and review : - Risk management Strategy - Risk management policy - Fraud Prevention Plan - Fraud Response Plan - Whistle-blowing policy | Marble Hall | EPMLM communities | To help management to prioritise the identified risks. This enables management to spend more time, effort and resources to manage risks of higher priority than risks with a lower priority. | To help management to prioritise the identified risks. This enables management to spend more time, effort and resources to manage risks of higher priority than risks with a lower priority. | 30 June 2012 | nil | EPMLM | EPMLM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 28005 | Reporting to Audit Committee quarterly. | Marble Hall | EPMLM communities | To report to Audit Committee on Activities of Internal Audit. | To report to Audit Committee on Activities of Internal Audit. | 30 June 2012 | 50 000 | EPMLM | EPMLM |
| 28006 | Appoint internal auditor | Marble Hall | EPMLM communities | To increase the scope of internal audit through appointment of competent staff | To increase the scope of internal audit through appointment of competent staff | 30 June 2012 | 167 000 | EPMLM | EPMLM |

| Priority Issue/Programme 29:Special focus groups and Special programs |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Improve development of special programs |  |  |  |  |  | Target for the Year: 5% vehicle replacement |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 29001 | Development programme and advocacy for the disables. | Marble Hall | EPMLM communities | To develop and implement Disability Development Programmes | To develop and implement Disability Development Programmes |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 29002 | Training programme for people with disability e.g. approach towards business. | Marble Hall | EPMLM communities | To develop and empower disability people with business skills programmes offered by Libsa (Forum) | To develop and empower disability people with business skills programmes offered by Libsa (Forum) |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 29003 | Aged Development Programme and advocacy | Marble Hall | EPMLM communities | To develop and implement development programmes for he Aged which help to give meaning for the aged life. | To develop and implement development programmes for he Aged which help to give meaning for the aged life. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 29004 | Youth development program and Advocacy | Marble Hall | EPMLM communities | To develop and implement Youth development programs | To develop and implement Youth development programs |  | 30 June 2012 | nil | EPMLM | EPMLM |

| 29005 | Woman and Gender development program and advocacy | Marble Hall | EPMLM communities | To develop and implement Woman and Gender development programme | To develop and implement Woman and Gender development programme | 30 June 2012 | nil | EPMLM | EPMLM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 29006 | Childrens development program and advocacy | Marble Hall | EPMLM communities | To develop and implement Childrens development program | To develop and implement Childrens development program | 30 June 2012 | nil | EPMLM | EPMLM |
| 29007 | Geographic name change program | Marble Hall | EPMLM communities | To develop and implement program for geographic name change | To develop and implement program for geographic name change | 30 June 2012 | nil | EPMLM | EPMLM |
| 29008 | Ward committee program | Marble Hall | EPMLM communities | To develop and implement program for ward committees | To develop and implement program for ward committees | 30 June 2012 | nil | EPMLM | EPMLM |
| 29009 | Traditional leaders support | Marble Hall | EPMLM communities | To develop and implement program for Traditional leaders | To develop and implement program for Traditional leaders | 30 June 2012 | nil | EPMLM | EPMLM |
| 29010 | Civic Courtesey | Marble Hall | EPMLM communities | To successfully host Mayoral guests | To successfully host Mayoral guests | 30 June 2012 | nil | EPMLM | EPMLM |

| Priority Issue/Programme 30:Council support |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme Objective: Improve development of special programs |  |  |  |  |  | Target for the Year: 5% vehicle replacement |  |  |  |  |
| Project ID | Project Name | Project Location | Project Beneficiaries | Project Objective | Key Performance Indicator |  | Period | Budget Allocation | Source of Funding | Implementing Agency |
| 30000 | Intergovernmental relations | Marble Hall | EPMLM communities | To have good relations with other government bodies. | Number of meetings held with such bodies, Established revived local IGR forum. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 30001 | Public Participation | Marble Hall | EPMLM communities | To afford the community with an opportunity of taking part in municipal programmes and giving inputs. | Number of consultative meetings held, Number of mayoral outreach programmes held, Number of ward & Ward Committee meetings held. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 30002 | Communication, Media Relations and Reporting. | Marble Hall | EPMLM communities | To have a well coordinated communication and good relations with the public. | Approved revised Communication policy, Number of reports developed. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 30003 | Handling Presidential Hotline queries | Marble Hall | EPMLM communities | To expedite service delivery and enhance customer care. | Number of community members assisted, Number of queries handled. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 30004 | Record of articles and press releases. | Marble Hall | EPMLM communities | To keep record of articles & press releases pertaining to the municipality for future references. | Number of articles & press releases kept in record, Number of record files opened. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 30005 | Reviewal of Delegation of Powers between political and administration functionality | Marble Hall | EPMLM communities | To ensure optimum functionality of Council, its committees and staff | Approved reviewed Delegation of Powers document. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 30006 | Revival of HIV/AIDS Council | Marble Hall | EPMLM communities | To give special attention to HIV/AIDS programmes in order to alleviate the pandemic’s impact on communities. | Number of meetings held by the council, Number of awareness campaigns conducted. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 30007 | Revival of the Aged & Disability council | Marble Hall | EPMLM communities | To give special attention to disabillity programmes in order to alleviate the pandemic’s impact on communities. | Number of meetings held by the council. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 30008 | Revival of Youth, Sport & Recreation council | Marble Hall | EPMLM communities | To give special attention to youth,sports & recreation programmes in order to alleviate the pandemic’s impact on communities. | Number of meetings held by the council. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 20009 | Traditional Leaders | Marble Hall | EPMLM communities | To enhance municipal relations with Traditional leaders & to encourage their participation in municipal programmes. | Number of consultative meetings held with them, Number of council meetings they attended |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 20010 | Traditional Healers | Marble Hall | EPMLM communities | To enhance municipal relations with Traditional healers & to encourage their participation in municipal programmes. | Number of consultative meetings held with them. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 20011 | Early Child Development (ECD) | Marble Hall | EPMLM communities | To afford children & stakeholders with an opportunity for developing children from early stages. | Number of consultative meetings held, Number of children taking part in the programme, Number of established ECD centres. |  | 30 June 2012 | nil | EPMLM | EPMLM |
| 20012 | Gender-based programmes & Moral Regeneration | Marble Hall | EPMLM communities | To develop a Framework & to discourage gender-based conflicts & violence, and to establish a committee. | Number of consultative meetings held, Approved Framework, |  | 30 June 2012 | nil | EPMLM | EPMLM |

14.	DISTRICT PROJECTS

14.1	DEPARTMENT OF WATER AFFAIRS : WATER AND SANITATION

| No. | Project name | Project discription | Overall budget (Rm) | Planning and design | Period of implementation |  |  | Budget |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 2011/2012 | 2012/2013 | 2012/2013 |  |
| 301 | Moutse West BWS & Reticulation & Cost Recovery: (MIG/LP0346/w/05/07) | SDM 41 - Moutse West BWS & Reticulation & Cost Recovery: (MIG/LP0346/w/05/07 | 10.0 | Feasibillity | 5.0 |  |  |  |

14.2	SEKHUKHUNE INFRASTRUCTURE AND WATER SERVICES

| KPA | PROGRAMME | PROJECT NO | PROJECTS | STATUS | TOTAL BUDGET | BUDGET 2011/12 | BUDGET 2012/13 | BUDGET 2013/14 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Water Infrastructure | MIG and District Infrastructure Development Programme | IWS053/11-12 | Cost Recovery ( WDM Project) Flag-Boshielo Scheme | New | R 20,000, 000.00 | R 5 625 631 | R 14 374 369 | 0.00 |
|  |  | IWS013/11-12 | Installation of flow control valves at 91 Reservoirs (WCM) and Extension of Flag Boshielo WTW to 25Ml/d | New | R46,260,000.00 | R 5,460,000.00 | R 40,800,000.00 | 0.00 |
|  |  | IWS015/11-12 | Flag Boshielo WTW Package Plant | New | R7,000,000.00 | R 7,000,000.00 | 0.00 | 0.00 |
| Sanitation | MIG and District Infrastructure Development Programme | IWS001/11-12 | Moutse (Rathoke, Matlala-Ramoshebo & Uitvlugte) | Design | R 10,400, 000.00 | R 5,400,000.00 | R5,000,000.00 | 0.00 |
| Roads | MIG and District Infrastructure Development Programme | IWS010/11-12 | Matlelerekeng to Rathoke Road (Phase3) | Ongoing | R22,500,000.00 | R 12,500,000.00 | R10,000,00.00 | 0.00 |
| Roads | MIG and District Infrastructure Development Programme | IWS011/11-12 | Malebitsa to Driefontein access road | Ongoing | R32,500,000.00 | R 15,000,000.00 | R17,500,000.00 | 0.00 |
|  | MIG and District Infrastructure Development Programm | IWS012/11-12 | Tshikanoshi to Malebitsa Access Road | Ongoing | R50,000,000.00 | R 20,000,000.00 | R 20,000,000.00 | R 10,000,000.00 |

15.	SECTOR DEPARTMENT PROJECTS

15.1	DEPARTMENT OF ROADS AND TRANSPORT – INFRASTRUCTURE PROJECTS

| No | Project Name | Project description | Planning & Design F/Y |  | Overall Budget | Implementing period and budget |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | F/Y | Budget |  | 2011/12 | 2012/13 | 2013/14 |
| 5 | Weighbridge | Rathoke Construction of weighbridge - LDRT |  |  | R16m | R4.1m |  |  |
| 22 | Road Rehabilitation (Including Widening) | D2535 - Road Rehabilitation (Including Widening) -LDRT | 2011/2012 | R7.5m | R75.5m |  | R31 725 000 | R35 775 000 |
| 23 | Ga-Matlala / Ragaphela to Tsimanyane to Kromdraai | D4285 - Upgrading (gravel to bituminous / tar surface) - RAL |  |  | R48.9m | R48.9m |  |  |
| 29 | D2900 to Zamerkost to Uitvlugt to Doornlaagte to Tshikanosi (Leeuwkuil) | D2664, D2919, D2922, D2919 - Upgrading (gravel to tar) |  |  | R57.5m | R21.5m | R36m |  |
| 34 | Tompi Seleka / Kromdraai to Mogaladi | Makhuduthamaga / Ephraim Mogale - D4370 Upgrading (Gravel to tar) RAL |  |  | R83m | R66m | R17m |  |

15.2	Limpopo Department of Agriculture – Infrastructure projects 2011/12

| No. | Project Name | Project description/type of structure | Overall Budget | Planning and Design |  | Implementation period and Budget R thousand |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | FY | Budget | 2011/12 | 2012/13 | 2013/14 |  |
| 5 | Kopano Disable | Sprinkler and centre pivot irrigation for 26,7 ha | 2,000,000 |  |  | 2,000,000 |  |  |  |
| 6 | Sekhukhune Poultry Projects | Fetakgomo/ Ephraim Mogale 9x1000 capacity broiler houses | 1,500,000 |  |  | 1,500,000 |  |  |  |
| 9 | Rahlagane Table Grapes | Construction of a Pack house | 1,500,000 |  |  | 1,500,000 |  |  |  |
| 16 | Mabodibeng | Fencing. Borehole drilling & equipping. Cold room. Pasturizing unit. | 450,000 |  |  | 450,000 |  |  |  |
| 31 | Cattle handling facilities | Construction of a basic cattle handling facility | 60,000 |  |  | 60,000 |  |  |  |
| 32 | Cattle handling facilities | Construction of a basic cattle handling facility | 60,000 |  |  | 60,000 |  |  |  |
| 33 | Cattle handling facilities | Construction of a basic cattle handling facility | 60,000 |  |  | 60,000 |  |  |  |
| 46 | Tompi Seleka | Rehabilitation of Bulk water supply | 2,000,000 |  |  | 100,000 |  |  |  |
| 47 | Roodewal | Rehabilitation of irrigation Scheme | 4,400,000 | 2011/12 | 400,000 |  |  |  |  |
| 48 | Elandskraal Block C & E | Rehabilitation of irrigation Scheme | 2,750,000 |  |  | 2,375,000 | 125,000 |  |  |
| 52 | Tompi Seleka Bio-diesel | Bio-diesel plant | 8,800,000 |  |  | 7,600,000 | 400,000 |  |  |

15.3	Department of education infrastructure plan mtef budget v22a

| No. | Project name | Project description | Total project cost | Planning and design |  | MTEF Forward estimates |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | F/Y | Budget | 2011/12 | 2012/13 | 2013/14 | 2014/15 | 2015/16 |
|  | Marble Hall Secondary School | New Secondary School - Public ordinary schools | 41,630,000 |  |  | 10,805,000 |  |  |  |  |

15.4	Health Infrastructure Projects

| No | Project name | Project description | Implementing agent | Total project cost | Plan & design |  | Implementation period and budget |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | F/y | Budget | 2011/12 |  |  |
|  | Matlala EMS | Ambulance base | SAKHIWO HS | 5,700 |  |  | 5,100 |  |  |
|  | Matlala Boiler Replacement | Hospital – District | SAKHIWO HS | 10,340 |  |  | 500 |  |  |
|  | Matlala Hospital | Accommodation | SAKHIWO HS | 6,532 |  |  | 307 |  |  |

15.5	Housing – Sekhukhune District Municipality

| Local Municipality | Allocation |
| --- | --- |
| Ephraim Mogale | 60 |
| Ephraim Mogale | 50 |
| Ephraim Mogale | 175 |

16.	PARASTATELS AND STATE OWNED ENTERPRISES PROJECTS

16.1	ESKOM Electrification Plan 2011/12

| Project Name | TOTAL Planned CAPEX | TOTAL Planned Connections |
| --- | --- | --- |
| Mamphokgo | R1 443 000.00 | 111 |
| Matlerekeng | R1 422 468.00 | 160 |
| Makgatle A | R1,444,878.00 | 87 |
| Malebitsa | R1,090,590.00 | 121 |
| Matlala -A-Ramoshebo | R330,000.00 | 22 |

16.2	DTI

| PROJECT | BUDGET 2010/11 | BUDGET 2011/12 | BUDGET 2012/13 |
| --- | --- | --- | --- |
| Organic farming cluster | 15 159 850 | 5 579 150 | 4 301 000 |

16.3	LEDET

| PROJECT | BUDGET | IMPLEMENTER | Responsible Person |
| --- | --- | --- | --- |
| Schuinsdraai Nature Reserve | R25 million | LEDET & LTP | Moses Ngobeni And Fixon Hlungwane |

CHAPTER 5 – INTEGRATION PHASE

17.	INTEGRATION

The following plans have been adopted by the council in order to carry out its mandate set out in the constitution:

17.1	Organisational Performance Management System

The Performance Management System (PMS) for the Municipality was compiled and approved by Council on 28 October 2004.Service provider has been appointed by GSDM in October 2009 to review the framework and to cascade PMS to post levels 2 & 3.

Performance agreements has been signed by managers for 2009/10 and agreements for 2010/11 will be approved by Council during June 2010.Internal audit plan for 2010/11 will be compiled during June 2010and will be approved by Audit committee thereafter which will include audit of performance review.

17.2	Integrated Spatial Development Framework

The spatial development principles relevant to the Greater Marble Hall Spatial Development Framework, which was adopted by Council on  25 June 2007 and not reviewed, are:

- Correction of historically distorted spatial patterns;

- Spatial integration;

- Densification (compact towns and cities);

- Sustainable land development practices;

- Spatially co-ordinated sectoral activities;

- The discouragement of land invasions;

- Security of land tenure, and

- Equitable access to land

- Marble Hall Provincial Growth Point

Marble Hall has  been approved  as a Provincial Growth Point, as also identified in the Limpopo Spatial Rationale.

Leeuwfontein – Moganyaka Area Municipal Growth Point

The Leeuwfontein/Moganyaka Area  has been approved, as a Municipal Growth Point and infill development between Leeuwfontein, Manapyane, Moganyaka and Mamphokgo should take place, to enable the establishment of one cohesive development area, namely the Leeuwfontein Municipal Growth Point.

Elandskraal – Hinlopen area Municipal Growth Point

Because of the geographic locality and proximity to each other Elandskraal and Hinloopen has been approved as a single Municipal Growth Point for the Elandskraal area.

Regae – Dichoeung area Individual Municipal Growth Point

Regae and Dichoeng has been approved as an individual Municipal Growth Point with corridor development between Elandskraal and Dichoeng along road D3600.

- Rathoke-, Uitvlught-, Keerom-, Zamenkomst Area Municipal Growth Point

Rathoke/Uitvlught/Keerom/Zamenkomst Area has been approved as a Municipal Growth Point and infill development between the four towns, should take place to enable the establishment of one cohesive development area, namely the Rathoke/Uitvlught Municipal Growth Point

- Ditholong-, Letebejane, Tsimanyane Area Population Concentration Point

Ditholong-, Letebejane, Tsimanyane Area, as a result of the hospital situated in the area, locality adjacent to road D4285 (which is identified as a priority link road) and the relatively large population of approximately 6267, it has been approved as a Population Concentration Point.

This area is situated in close proximity to the Flag Boshielo Dam and a large area has been identified as conservation area. Eco Tourism can thus play an important role in the economic upliftment of this area.

It is proposed that infill development should take place between the settlements of Makgatle-A, Letebejane, Ditholong and Tsimanyane South to establish one nodal development area. Steep areas occur to the east of this proposed nodal point, which restricts development in this direction.

- Proposed Corridor Development

(1)	Zamenkomst – Rathoke – Malebitsa is seen as a future development corridor with the main growth point at Rathoke

(2)	In a north/south direction, the main development corridor of the Greater Marble Hall area, is from Marble Hall to be along the N1 in an eastern direction to Leeuwfontein and then in a northern direction along road D4100, to Matseding. Road D4358 and from there along Road D3600 to Elandskraal and ending at Dichoeung in the north.  It is thus important to expedite the upgrade of road D3600 between Elandskraal and Dichoeung, as development can only successfully take place if a sufficient transport system can be established for the transportation of consumers, goods and services. A road system can be regarded as the “life line” for the establishment of development areas.

(3)	The main proposed east/west development corridor along Road D4285 (Tsimanyane South, Ragaphela, Mmolwaneng) along a priority link road is proposed to link up with settlements (for example Maseremule Park) in the adjacent Greater Tubatse Municipality, as well as provide linkage with the north/south corridor.

5.6	Integrated LED Programme/Strategy

17.3	Local Economic Development

LED strategy and plan was approved on 25 June 2008 and proposals to improve the rate of economic development and the quality of life of the citizens of Marble Hall Municipality is Service  Delivery Improvements, Horticulture Cluster Promotion, Meat Cluster Promotion ,Tourism Cluster Development and Informal Economy Support.The strategy responds to economic constraints of the municipality and is aligned to key planning documents of the NSDP,PGDS etc.

EPWP is identified as a means to provide job opportunities and training along with various sectors for infrastructure development in respect of roads and storm water, electricity ,community development and LED development .

17.4	Integrated HIV/AIDS Programme

The municipality is implementing the decentralised response to HIV & AIDS, having joined the CMRA support project in June 2007 as the 7th pilot site. The objectives of the municipality project are: (a) to establish an Interdepartmental Forum (IDF) on HIV & AIDS with a clear objective, mandate and responsibility, coordination body and budget (earmarked from the various departments) and well embedded in the IDP in order to increase the service delivery to the community related to HIV & AIDS issues and (b) to advise the municipality in how to establish and/strengthen the Local Aids Council (LAC) – the multisectoral municipal HIV & AIDS platform involving all stakeholders (governmental and non-governmental) in the field of HIV & AIDS to address the problem of HIV & AIDS from the local level in a coordinated and effective way, broaden the scope of the spin off and avoid unnecessary overlaps.

The IDF committee has been established. Preparation of departmental action plans on HIV & AIDS has been compiled. LAC has been established.

The project has already contributed significantly to raising awareness in the municipality with regard to mainstreaming of HIV & AIDS and brochures for each ward has been compiled giving details of home based carers and the needs of the communities.

17.5	Integrated Poverty Reduction and Gender Equity Programme

To ensure a consistent set of measures to reduce poverty and to contribute to gender equity in the Municipality.

To strive to ensure that the needs of vulnerable and destitute households within the Municipalities area of jurisdiction are adequately and sustainably addressed.

Unemployment is high due to the following:

- Lack of job opportunities.

- High level of illiteracy.

- Lack of skills.

- Unsustainable projects.

- Lack of access to credit.

- Lack of and long distances to markets for products.

- Lack of economic diversification.

- Lack of investment.

The implications of this socio-economic status are that:

- Programmes should be targeted at women, aged, disabled, youth and those who cannot be accommodated into the formal economy:

- Projects and resources must be rurally based and should include food security projects.

- Programmes should focus on the upskilling of the people by introducing skills training programmes.

- Projects should address economic growth as an essential platform for employment creation.

The gender equity plan has been compiled

17.6	Disaster Management Plan

The purpose of a Disaster Management Plan is to enhance the capacity of the Municipality to prevent and to deal with disasters within the greater municipal area, and to avoid developments  and activities which are subject to high risk of disasters.

The plan was compiled and approved by Council on 26 September 2006.

The Greater Sekhukhune district municipality is responsible for disaster management and a SLA are being developed to act as agent for the district .

17.7	Water Services Development Plan

The Sekhukhune District Municipality compiled a Water Services Development Plan on behalf of the Greater Marble Hall Municipalities' area.    This information will be consolidated as a sector plan within the IDP.   Water and Sanitation are regarded as the highest priority needs within the municipality.  Strategies and Projects related to this sector is referred to in sections 3 and 4.

The municipality provide water services on behalf of GSDM for Marble Hall town,Leeuwfontein and Matlerekeng.Lephele North water and 			GSDM provide water services to other villages in the municipality.

17.8	Integrated Waste Management

The municipality have powers and functions for waste management.The  Integrated Waste Management Plan (IWMP) has in terms of the requirements stipulated in the White Paper on Integrated Pollution and Waste Management for SA. Strategies been compiled and approved by Council on 30 September 2003.

To ensure efficient waste management systems a solid waste implementation plan has been compiled to improve  waste disposal and the management of the waste disposal site.

17.9	Integrated Environmental Management Programme

Local government operates in a challenging set of circumstances in terms of ensuring environmental sustainability.The pressure for development can apply tremendous strain on the natural environment. To ensure that environmental sustainability considerations are taken into account during planning, development and implementation of projects, the  Integrated Environmental Programme was compiled and approved by Council on 29 March 2005.

17.10	Integrated Transport Plan

The municipality is a transport authority.The compilation of an Integrated Transport Plan was identified as a high priority project for the Public Transport sector.  This plan should be integrated with the provincial and district plans.  Financial and technical assistance need to be offered by the Department of Transport to compile this plan in the 2010/11 financial year.

17.11	Land Use Management System

GSDM appointed a service provider to compile a LUMS for the municipality.The draft has been compiled but not approved as yet due to lack of legislation to back the system.

17.12	Electricity – Energy master plan

The municipality is the electricity service provider for Marble Hall town and community lighting for the municipal area. ESKOM is the electricity service provider for the other villages in the municipality.

Energy master plan and energy saving policy has been compiled and complies with minimum required standard.

17.13	Roads master plan

Roads and storm water sector plan have been compiled which include investment plan for infrastructure. Roads master plan which include district ,provincial and national roads to be compiled in liaison with GSDM, Provincial and National roads departments in 2010/11 financial year.

17.14	Municipal infrastructure investment framework (MIIF)

Municipal infrastructure investment  framework is in place  and investment planning utilize the MIG grant over the next MTEF.

17.15	Public participation/Communication system

Public participation/communication system is in place as well as personnel, policy and strategy  which meet the minimum and required standard.

17.16	Risk management strategy and Anti-corruption strategy

Risk management and Anti-corruption strategies compiled .

17.7	Five year financial plan

Five year financial plan has been compiled and form part of the Budget document for 2011/12 compiled in terms of the MFMA which address the financial challenges highlighted and prioritised in the analysis phase and meet the minimum and required standard.

17.8	Audit action plan

The municipality received an unqualified audit report on the financial statements for 2008/9. Audit action plan has been compiled to address matters with emphasis. The comments from the Auditor – General are seriously addressed in the audit action plan.

17.9	Internal Audit Committee

Internal audit committee has been established on 26 November 2009 as per council resolution C2/15/2009

17.10	Institutional plan

Institutional plan developed in line with powers and functions which address the institutional challenges and prioritised in the analysis phase and meet the minimum and required standard.

17.11	HR strategy

HR strategy has been compiled and responds to the long-term goals as reflected in the IDP.

17.12	Workplace skills plan

Workplace skills plan has been compiled which addresses scares skills

17.13	Succession plan

Succession plan has been compiled for key positions

17.14	IGR structures

IGR structures in place are the IDP representative forum both on local and district level.

CHAPTER 6 - ADOPTION

18.	ADOPTION

IDP for 2011/12 – 15/16 was  adopted by Council on              by resolution number                       .