## Slide 1
EPHRAIM MOGALE LOCAL MUNICIPALITY
PERFORMANCE REVIEW
FIRST QUARTER
PERFORMANCE REPORT
2016/17
Date:
28 October 2016
Venue : KINGDOMS LODGE
Time: 08:00am

## Slide 2
ITEM | TIME | PRESENTER
OPENING & WELCOME: Mayor | 08h00 – 08h20 | Hon. CR KUPA
APOLOGIES 3. Progress on the Implementation on 3RD Quarter Lekgotla Resolutions | 08h20 -- 08h30 08h30 – 09h00 | Hon. CR KUPA
4. MUNICIPAL MANAGER’S OVERVIEW | 09h00 – 09h30 | Ms. MATHEBELA MM
PRESENTATIONS 5.1 Municipal Manager’s Office 5.2 Planning and Economic Development 5.3 Corporate Services Directorate Questions & Discussions TEA BREAK TEA BREAK TEA BREAK 5.4 Infrastructure Services Directorate 5.5 Community Services Directorate 5.6 Budget and Treasury Directorate |  | 
 | 09h30 - 10h00 10h00 –11h30 11h30 - 12h00 12h00 - 12h30 12h30- 13h00 13h00 - 13h30 13h30 - 14h00 14h00 – 14h30 | Ms. SELLO TEFFO Ms. KATLEGO SHONGWE Mr. REPLY MKWANAZI ALL ALL Mr. DURIE JOHAN Mr. CORRIE BADENHORST Ms. KHABO RAMOSIBI ALL
Questions & Discussions | 14h30- 15h00 | 
6.Closure | 15h15 | Hon. CR KUPA
7. Lunch Served |  | 
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE AGENDA

## Slide 3
Vision: “A viable and sustainable municipality that provide quality service and enhance socio-economic growth”
Mission: To involve all sectors of the community in the economic, environment and social development whilst improving service delivery thereby becoming a prominent agricultural, business and mega industrial growth point in the Sekhukhune District for the benefit of the residents and province.
MUNICIPAL MANAGER’S OVERVIEW
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
EPHRAIM MOGALE LOCAL MUNICIPALITY

## Slide 4
1st Quarter Job Creation:
Senior Management Posts:
No. of Positions: 266
Vacant Positions: 26
Filled Position : 240
1. New appointments: 04
2. Disciplinary Matters: 03
3. No. of suspensions for the Q1: 03
4. Dismissal: None
EPMLM 2016/2017 1st QUARTER EXCO LEKGOTLA AGENDA
MUNICIPAL MANAGER’S OVERVIEW
Number of Posts | Filled | Vacant | Vacancy rate
6 | 3 | 3 | 50%
MEN | WOMEN | YOUTH | DISABLED | TOTAL
121 | 929 | 475 | 0 | 1 525

## Slide 5
EPMLM 2016/2017 1st QUARTER EXCO LEKGOTLA AGENDA
MUNICIPAL MANAGER’S OVERVIEW
GRANT | TOTAL BUDGET | EXPENDITURE | % SPENT
MIG | R31 917 000.00 | R315 164.11 | 1%
FMG | R1 810 000.00 | R145 515.15 | 8%
EPWP | R1 258 000.00 | R0.00 | 0%
MSIG | R0.00 | R0.00 | 0%
TOTAL | R 34 985 000 | R460 679.26 | 1%

## Slide 6
PROGRESS ON AG MATTERS
EPMLM 2016/2017 1st QUARTER EXCO LEKGOTLA AGENDA
MUNICIPAL MANAGER’S OVERVIEW
NO OF ISSUES RAISED | NUMBER OF ISSUES RESOLVED
137 | 118

## Slide 7
KPA | Number of KPI’s | Achieved | Not Achieved | % Achieved | % Not Achieved
KPA 1: Spatial Rationale | 10 | 5 | 5 | 50.0% | 50.0%
KPA 2: Basic Service Delivery | 13 | 09 | 4 | 69.2% | 30.8%
KPA3: Local Economic Development | 5 | 3 | 2 | 60,0% | 40,0%
KPA 4: Municipal Transformation and Institutional Development | 13 | 09 | 4 | 69,2% | 30.8%
KPA 5: Financial Viability | 15 | 10 | 5 | 66.6% | 33.4%
KPA 6: Good governance and public participation | 22 | 12 | 10 | 54.5% | 45,5%
TOTAL | 78 | 48 | 30 | 61.5% | 38.5%
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
MUNICIPAL MANAGER’S OVERVEIW

## Slide 8
MUNICIPAL MANAGER’S OFFICE
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW

## Slide 9
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2 - Basic Service Delivery
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Improved community wellbeing through accelerated service delivery | SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (OMM) | FV 07 | Oper | New | 100% | 100% | 100% | Achieved Chief internal auditor appointed to member of the Evaluation committee for projects xx. | None | None

## Slide 10
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 4: Municipal Transformation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Plan for the future | Institutional Development | # of Quarterly institutional Performance Reports submitted to Council per quarter | MTDO 39 | 63,6 | 4 | 4 | 1 | 1 | Achieved Draft Annual Performance Report (4th Q performance report) served in council | None | None
 |  | # of formal performance reviews conducted with Section 56 employees (bi-annual) | MTDO 37 | 80 | 4 | 2 | N/A | N/A | N/A | N/A | N/A
 |  | % of KPIs attaining organisational targets by 30 Jun 2017 (Total organisation) | MTDO 38 | Oper | 78% | 100% | 75% | 57,1% | Not Achieved | Only 44 out of 77 KPI’s achieved set targets | 

## Slide 11
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance and Public Participation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Good Governance | # of Risk Management reports submitted to the Risk Management Committee per quarter | GG 10 | 350 | 4 | 14 | 2 | 1 | Not Achieved |  | 
 |  | # of Risk Management Committee meetings convened per quarter | GG 20 | 0 | 4 | 4 | 1 | 1 | Achieved | None | None
 |  | % execution of identified risk management plan within prescribed timeframes per quarter (OMM) | GG 16 | Oper | New | 100% | 100% | N/A | The actions on the risk register are targeted for second Quarter | None | None
 |  | % execution of identified risk management plan within prescribed timeframes per quarter (Total Organisation) | GG 16 | Oper | New | 100% | 100% | N/A | The actions on the risk register are targeted for second Quarter | None | None

## Slide 12
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance and Public Participation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Good Governance | Fraud / Corruption Risk Plan approved by Council by 30 Sept 2016 | GG 17 | 0 | 0 | 1 | 1 | 0 | Not Achieved | The plan is in place and has served in both the Risk Management and Audit Committee, however it is in between council meetings.(submitted to council support for agenda) | The plan to serve in the 1st ordinary council meeting to be held on the date yet to be confirmed
 |  | # of quarterly anti-fraud and corruption awareness campaigns held | GG 17/19 | 0 | 4 | 4 | 1 | 1 | Achieved | None | None
 |  | Strategic and Operational Risk Plan approved by Council by 30 Sept 2016 | GG 16 | 0 | 0 | 2 | 2 | 0 | Not Achieved | The plan is in place and has served in both the Risk Management and Audit Committee, however it is in between council meetings.(submitted to council support for agenda) | The plan to serve in the 1st ordinary council meeting to be held on the date yet to be confirmed
 |  | % of Auditor General matters resolved as per the approved audit action plan by 30 June 2017 (Total organisation) | GG 11/12/13 | 0 | New | 100% | N/A | N/A | N/A | 2015/16 AGSA audit still in progress | N/A

## Slide 13
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance and Public Participation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Good Governance | % of AG Management Letter findings resolved by 30 Jun 2017 (OMM) | GG 11/12/13 | 700 | New | 100% | N/A | N/A | N/A | 2015/16 AGSA audit still in progress | N/A
 |  | # of Internal Audit reports submitted to the Audit Committee per quarter | GG 14/15 | 0 | 4 | 4 | 1 | 1 | Achieved | None | None
 |  | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (OMM) | GG 14/15 | 0 | 4 | 100% | 100% | N/A | No Internal Audit conducted in the quarter under review | None | None
 |  | # of quarterly Performance Audit Committee meetings held | GG 15 | 700 | 4 | 4 | 1 | 1 | Achieved | None | None
 |  | Submission of Draft consolidated Annual Report to Council on or before 28 August 2016 | FV 10 | Oper | New | 1 | 1 | 1 | Achieved | None | None
 |  | Submission of Final audited consolidated Annual Report to Council on or before 28 January 2017 | FV 10 | Oper | New | 1 | N/A | N/A | N/A | N/A | N/A

## Slide 14
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance and Public Participation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Good Governance | Submission of AR Oversight Report to Council by the 30th March 2017 | FV 10 | Oper | New | 1 | N/A | N/A | N/A | N/A | N/A
 |  | % of Council meetings resolutions resolved within the prescribed timeframe (3 months) | GG 07 | Oper | New | 100% | 100% | 100% | Achieved | N/A | N/A
 |  | 2018/19 IDP review Process Plan approved by 30th June 2017 | MTOD 35 | Oper | New | 1 | N/A | N/A | N/A | N/A | N/A
 |  | Hosting of an annual Strategic Lekgotla to review the IDP by 30 Dec 2016 | MTOD 36 | 300 | 1 | 1 | N/A | N/A | N/A | N/A | N/A
 |  | Draft 2017/18 IDP/Budget tabled before Council for adoption by March 2017 | MTOD35 | Oper | New | 1 | N/A | N/A | N/A | N/A | N/A
 |  | Final IDP/Budget tabled and approved by Council by the 31st May 2017 | MTOD 35 | 300 | 1 | 1 | N/A | N/A | N/A | N/A | N/A

## Slide 15
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance and Public Participation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Good Governance | Obtain a Qualified Auditor General opinion for the 2015/16 financial year | GG 12 | Oper | Disclaimer | Disclaimer | N/A | N/A | N/A | N/A | N/A
 |  | Adjusted Budget and SDBIP approved by the Mayor by the 28th February 2017 | FV 05 | 0 | 1 | 1 | N/A | N/A | N/A | N/A | N/A
 |  | Final SDBIP approved by the Mayor within 28 days after approval of Budget | New | Oper | New | 1 | N/A | N/A | N/A | N/A | N/A

## Slide 16
OVERALL PERFORMANCE | 
TARGETS ACHIEVED | 08
TARGETS NOT ACHIEVED | 04
% ACHIEVEMENT FIRST QUARTER PERFORMANCE | 66.6%
BUDGET | R 0.00
EXPENDITURE | R 0.00
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
Overall Performance for MM’s Office

## Slide 17: PLANNING AND ECONOMIC DEVELOPMENT
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW

## Slide 18
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 1: Spatial Rationale
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
House the nation and build Integrated Human Settlement | Land use management | % of land use applications received and processed within 60 days as per the Town Planning and Township Ordinance Act 15 of 1986 | SR 01 | Oper | 20 | 100% | 30% | Not Achieved The newly formed district SPLUMA monthly working group meetings, assist in the discussion of received town planning applications. | The slow implementation of the Municipal Planning Tribunal, affects land developmental applications received and the timeframes associated with legislations. | Accept submitted applications and submit to council for decision, not to infringe on the legislated time-frames.
 |  | # of EPMLM Town Planning By-Laws developed and gazetted by Dec 2016 | SR 02 | Oper | 1 | N/A | N/A | 1 Draft EPMLM Town Planning By-Laws. The newly formed district SPLUMA monthly working group meetings, assist in the assessment of the Municipal By-Laws. | The by-laws not adapted by previous council, citing reasons that proof of the public participation was conducted. | Re-submit item to council with annexures of advert, attendance register for all 4 consultative public participation process conducted MARCH 2016

## Slide 19
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 1: Spatial Rationale
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
House the nation and build Integrated Human Settlement | Land use management | # of EPMLM Billboard and Advertising by-law developed and gazetted by Jun 2017 | SR 03 | Oper | New | N/A | N/A | By-Laws in draft phase. The By-Laws was done in the financial year 2013/14 and public participation conducted however needs to be insync with the town planning by-laws. | The By-Laws was done in the financial year 2013/14 and public participation conducted however needs to be insync with the town planning by-laws. | Ensure that by Q3 public participation
 |  | % of New Building Plans of less than 500 square meters assessed within 10 days of receipt of plans. | SR 04 | Oper | 50 | 100% | 100% | Achieved | None | None
 |  | % of New Building Plans of more than 500 square meters assessed within 28 days of receipt of plans. | SR 04 | Oper | New | 100% | 100% | Achieved | None | None

## Slide 20
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 1: Spatial Rationale
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
House the nation and build Integrated Human Settlement | Land use management | # of municipal buildings to be maintained as per the approved municipal maintenance plan by the 30 Jun 2017 | SR 06 | 572,3 | 35 | 5 | 0 | Not Achieved | 5 request made for the building maintenance | Supply chain department is attending to the request submitted.
 | Land use management | # of Land Use Awareness workshops to held with Magoshi by 30 June 2017 | SR 08 | Oper | 2 | 1 | 1 | Achieved | Conducted August 2016, received support from all traditional authorities, Cogshta and Salga | None
 | Housing | Develop a municipal building maintenance plan and submit to Council for approval by 30 Sept 2016 | SR 05 | Oper | New | 1 | 1 | Achieved | Municipal building have been assessed as on the maintenance plan and prioritised considering the funds available. | More Funds are required for the renovations of such as most of the Municipal Houses are very old.
 |  | Number of municipal houses to be maintained as per the approved municipal maintenance plan by the 30 Jun 2017 | SR 07 | Oper | New | 10 | 3 | Not Achieved | Requests for the general maintanance on 3 municipal houses are being done and still awaits SCM to invite service providers for inspections. | The waiting period from SCM department on request for goods is affecting us in terms of performance.

## Slide 21
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 1: Spatial Rationale
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
House the nation and build Integrated Human Settlement | SDF | Review EPMLM Spatial Development Framework and adopted by Council by 31 March 2017 | SR 10 | 106 | 0 | N/A | N/A | Terms of Reference, Specification and Advert done. | Municipal Budget for the project, no sufficient available | To seek funds from Coghsta as province indicated that they would support municipalities that have gazetted their Municipal Town Planning By-Laws. Ensure that By-Laws are approved by council to gazette.
 |  | Review EPMLM Town Planning Scheme by 31 March 2017 | SR 11 | Oper | 0 | N/A | N/A | Terms of Reference, Specification and Advert done. | N/A | N/A
 | Land use management | % of buildings; constructed with approved plans, inspected that comply with the National Building Regulations and Building Standards Amendments Act No 49 of 1995 | SR 04 | Oper | New | 100% | 100% | Achieved | N/A | N/A

## Slide 22
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2 - Basic Service Delivery
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
House the nation and build Integrated Human Settlement | Housing | # of reports in terms of new RDP Housing units provided by the CoGHSTA submitted to Council by 30 Jun 2017 | SR 13 /14 | Oper | 278 | 1 | 0 | Not Achieved | Developers are being appointed by Cohgsta recently and they still working on material issues | Meeting with the councillors for the appointments of labours
Improved community wellbeing through accelerated service delivery | SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (P&ED) | FV 07 | Oper | New | 100% | 66% | Not Achieved | Attended 2/3 | 

## Slide 23
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 3: Local Economic Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Grow the economy and provide livelihood support | LED | # of quarterly SMME's and Cooperatives capacity building skill workshops scheduled and held | LED 01 | 0 | 4 | 1 | 2 | Achieved | None | None
 |  | # of Coop's supported with respect to financial support by 30 Jun 2017 | LED 02 | 0 | 10 | 3 | 10 | Achieved | None | None
 |  | # of quarterly LED forum meetings held | LED 03 | 21,2 | 4 | 1 | 1 | Achieved | None | None
Develop partnerships |  | Hosting of a LED Summit by 30 Jun 2017 | LED 04 | 84,8 | 1 | N/A | N/A | N/A | N/A | N/A
 |  | Tourism Association established by Dec 2016 | LED 05 | 0 | 0 | N/A | N/A | N/A | N/A | N/A

## Slide 24
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 3: Local Economic Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Develop partnerships | LED | Hosting of a Businesses Tourism Indaba by 30 Jun 2017 | LED 09 | 0 | 2 | N/A | N/A | N/A | N/A | N/A
 |  | # of quarterly reports submitted to Council with respect to the implementation of Social Labour Plan (SLP) programmes of Mining Companies | New | Oper | New | 1 | 0 | Not Achieved | The LED unit could not succeed in meeting with the Mining houses due to unavailability of the managers | The LED should collaborate with the Community Services unit to persuade the Mining house to convene quarterly meetings
 |  | # of quarterly reports submitted to Council with respect to the Corporate Social Investment (CSI) programmes of both Business and Mining organisations | New | Oper | New | 1 | 0 | Not Achieved | The LED unit could not succeed in meeting with the Mining houses due to unavailability of the managers | The LED should collaborate with the Community Services unit to persuade the Mining house to convene quarterly meetings
Grow the economy and provide livelihood support |  | Review and update the cooperative database by 30 June 2017 | LED 06 | 0 | 1 | N/A | N/A | N/A | N/A | N/A

## Slide 25
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 4: Municipal Transformation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 31 March 2017 (P&ED) | MTOD 09 | Oper | 0 | N/A | N/A | N/A | N/A | N/A

## Slide 26
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (P&ED) | GG 14/15 | Oper | New | 100% | N/A | No Internal Audit conducted in the quarter under review | None | None
 |  | % of AG Management Letter findings resolved by 30 Jun 2017 (P&ED) | GG 11/12/13 | Oper | New | N/A | N/A | N/A | N/A | N/A
 |  | % execution of identified risk management plan within prescribed timeframes per quarter (P&ED) | GG 16 | Oper | New | 100% | N/A | The actions on the risk register are targeted for second Quarter | None | None

## Slide 27
OVERALL PERFORMANCE | 
TARGETS ACHIEVED | 8
TARGETS NOT ACHIEVED | 7
% ACHIEVEMENT FIRST QUARTER PERFORMANCE | 53.3%
BUDGET | R 1 255 084.00
EXPENDITURE | R 54 956.32
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
Overall Performance for PED Department

## Slide 28: CORPORATE SERVICE
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW

## Slide 29
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2 - Basic Service Delivery
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Improve community wellbeing through accelerated service delivery - | Institutional Development | # of quarterly Customer Complaint reports submitted to Council (inclusive of Presidential Hotline) | MTOD 19 | 0.5 |  | 4 | 1 | 1 | Achieved | None | None
 | SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (Corp) | FV 07 | Oper | New | 100% | 100% | 0% | Not Achieved | None | None

## Slide 30
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 4: Municipal Transformation
Strategic Objective | Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 30 Jun 2017 (Corp) | MTOD 09 | 3 000 | 0 | 12 | 3 | 0 | Not Achieved | No request received | None
 |  | % of Lease Agreements processed within the time frame of 30 days | MTOD 12 | Oper | New | 100% | 100% | 100% | Achieved | No submissions received | None
 |  | % of Service Level Agreements (SLA's) and Employment Contracts processed within the time frame of 30 days | MTOD 34 | Oper | New | 100% | 100% | 100% | Achieved | None | None
 |  | % of approved positions processed within three months of post being vacant (task 13 and above) | MTOD 02 | Oper | New | 100% | 100% | 100% | Achieved | None | None
 |  | % approved vacant positions (previously filled) processed within (3) months of post being vacant | MTOD 02 | Oper | New | 100% | 100% | 100% | Achieved | None | None

## Slide 31
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 4: Municipal Transformation
Strategic Objective | Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Develop and retain skilled capacitated workforce | Institutional Development | # of Job Descriptions developed by 30 Jun 2017 | MTOD 13 | 600 | 40 | 220 | 55 | 0 | Not Achieved | Job descriptions still to be signed | Fast track the signing thereof
 |  | % of employees from previously disadvantaged groups appointed in the three highest levels of management as per the approved EE plan by the 30 June 2017 (GKPI) | MTOD 01 | 75 | New | 100% | N/A | N/A | N/A | N/A | N/A
 |  | % of budget spent implementing the Workplace Skills Plan by the 30 Jun 2017 (GKPI) | MTOD 03 | Oper | New | 100% | N/A | N/A | N/A | N/A | N/A
 |  | % of beneficiaries trained as per target of Workplace Skill Plan (WSP) by 30 Jun 2017 | MTOD 03 | 318 | New | 100% | N/A | N/A | N/A | N/A | N/A
 |  | # of Councillors trained by 30 Jun 2017 | GG 08 | 220,9 | New | 21 | N/A | 28 | Achieved | Previously scheduled for 2nd Quarter implementation | None

## Slide 32
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 4: Municipal Transformation
Strategic Objective | Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Develop and retain skilled capacitated workforce | Institutional Development | # of beneficiaries of the Community Bursary scheme by the 30 Jun 2017 | MTOD 07/14 | 901 | 26 | 6 | N/A | N/A | N/A | N/A | N/A
 |  | Review organisational structure and align to the IDP and Budget by 30 June 2017 | MTOD 10/11 | Oper | New | 1 | N/A | N/A | N/A | N/A | N/A
Build effective and efficient Organization |  | # of quarterly ICT steering committee meetings held in terms of the implementation of the ICT governance strategy and policy | MTOD 23/24 25/26 27/28 | 1 860,7 | 4 | 4 | 1 | 0 | Not Achieved | No items submitted | Compilation of items for the committee
 |  | # of quarterly Local Labour Forum (LLF) meetings held as scheduled | MTOD 08 | 120 | 12 | 4 | 1 | 0 | Not Achieved | Parties to submit names of new representatives | Re-constitution of the Local Labour Forum
 |  | # of quarterly Workplace Health and Safety Forum meetings held as scheduled | MTOD 04 | 350 | 4 | 4 | 1 | 1 | Achieved | None | None
 |  | # of quarterly Employee Wellness Programs held | MTOD 05 | 400 | 2 | 4 | 1 | 1 | Achieved | None | None

## Slide 33
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance
Strategic Objective | Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Good Governance | Number of Council meeting held by June 2016 as per the Legislation | GG 07 | Oper | New | 4 | 1 | 4 | Achieved | None | None
 |  | Number of EXCO meetings held each month | GG 07 | Oper | New | 11 | 3 | 2 | Not achieved | Change of Council | Adherence to approved schedule
 |  | # of Section 79 Committee meetings held each quarter | GG 07 | Oper | New | 4 | 1 | 0 | Not achieved | None adherence to governance model | Adherence to governance model
 |  | # of quarterly reports submitted to Council in terms of the number of MPAC resolutions raised and resolved per quarter | GG 07 | Oper | New | 1 | 1 | 1 | Achieved | No items referred to MPAC | None

## Slide 34
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance
Strategic Objective | Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Effective and Efficient Community Involvement | Institutional Development | # of quarterly Community Workers local forum meetings held | LED 07 | Oper | 2 | 4 | 1 | 0 | Not Achieved |  | 
 |  | # of Public Participation meetings facilitated | GG 02 | 600 | New | 2 | N/A | N/A | N/A | N/A | N/A
Effective and Efficient Community Involvement | Institutional Development | # of quarterly reports submitted to Council in terms of scheduled ward committee meetings held | GG 03 | Oper | New | 4 | 1 | 0 | Not achieved | No ward committee meetings scheduled | Finalise the establishment of ward committees
 |  | # of Ward operational plan reports submitted to Council by the 30 Jun 2017 | GG 03 | Oper | New | 1 | N/A | N/A | N/A | N/A | N/A
 |  | # of quarterly community newsletters published and distributed | GG 05 | 275 | 4 | 4 | 1 | 0 | Not achieved | Compilation of information | Fast track compilation of information and publishing
 | Welfare Services | # of Transversal programmes implemented in terms of mainstreaming with respect to Gender, Disabled, Woman and Children Rights by the 30 Jun 2017 | GG 01 | 250 | New | 4 | 1 | 1 | Achieved | None | None
 | Youth | # of Youth programmes / initiatives implemented each quarter | GG 04 | 106 | New | 4 | 1 | 1 | Achieved | None | None

## Slide 35
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance
Strategic Objective | Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Effective and Efficient Community Involvement | Institutional Development | % hosting and management of the website by SITA | MTOD 29 | 75 | New | 100% | 100% | 100% | Achieved | None | None
Build effective and efficient Organization | Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (Corp) | GG 14/15 | Oper | New | 100% | 100% | N/A | No Internal Audit conducted in the quarter under review | None | None
 |  | % of AG Management Letter findings resolved by 30 Jun 2017 (Corp) | GG 11/12/13 | Oper | New | 100% | 100% | N/A | N/A | N/A | N/A
 |  | % execution of identified risk management plan within prescribed timeframes per quarter (Corp) | GG 16 | Oper | New | 100% | 100% | N/A | The actions on the risk register are targeted for second Quarter | None | None

## Slide 36
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
Overall Performance for Corporate Services
OVERALL PERFORMANCE | 
TARGETS ACHIEVED | 13
TARGETS NOT ACHIEVED | 10
% ACHIEVEMENT FIRST QUARTER PERFORMANCE | 56,5%
BUDGET | R 5 364 200.00
EXPENDITURE | R 480 526.00

## Slide 37: INFRASTRUCTURE
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW

## Slide 38
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2 - Basic Service
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Improved community wellbeing through accelerated service delivery | Roads and storm water | # of Kms of roads to be graded by 30 Jun 2017 | BS 89 | Oper 1 644 | 1 200km | 300km | 356.824 km | Achieved | None | None
 |  | Number of m2 of base and surface patches repaired by 30 Jun 2017 | BS 90 | Oper | 900 m2 | 300 m2 | 538.932m2 | Achieved | None | None
 |  | Review Roads Master plan and adopted by Council by 31 March 2017 | BS 59 | Oper | 1 | N/A | N/A | The 3rd draft document has been submitted. | N/A | N/A
 |  | # of Kms of gravel roads to be constructed in tar by 30 Jun 2017 | BS 48/50/52/53/54/70 | MIG 7 000 | 4,7kms | N/A | N/A | N/A | N/A | N/A
 |  | # of kms of Storm Water to be constructed in Ext 6 by 30 Jun 2017 | BS 45 | 6 000 | 400m | N/A | N/A | N/A | N/A | N/A
 |  | # of Kms of roads to be rehabilitated by 30 Jun 2017 | BS 71/84 | MIG 4 500 | New | N/A | N/A | N/A | N/A | N/A

## Slide 39
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2: Basic Service Delivery
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Improved community wellbeing through accelerated service delivery | Roads and storm water | Number of Km of roads to be constructed by 30 Jun 2017 (Industrial Road) | BS 57 | MIG 1 000 | 400m | N/A | 0km | Not Achieved | Tenders advertised and closed on the 09/09/2016, delays in convening BEC. | Its recommended that SCM must expedite the convening of BEC
 | Electricity | Number of high mast lights connected by 30 Jun 2017 | BS 17/32/38 | 200 | 10 | N/A | N/A | N/A | Waiting for ESKOM to install supply points, truck to transport TLB waiting for repairs for 1 year | Repair truck as soon as possible
 |  | # of Quarterly reports in terms of households with access to basic levels of electricity submitted to the MM (GKPI) | New | Oper | New | 1 | 1 | Achieved | None | None
 |  | Develop an Energy Master & OM plan and submit to Council for adoption by 31 March 2017 | BS 22 | 500 | New | N/A | N/A | N/A | Energy Master plan Inception report completed. O&M Plan specification submitted. SCM taking too long. 1 month and no BSC yet. | Request SCM to arrange BSC
 |  | # high mast lights upgraded to led fittings by 30 Jun 2017 | BS 10/25 | 430 | New | N/A | N/A | N/A | Tender closed 16/09/2016 | None
KPA 2 - Basic Service

## Slide 40
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2: Basic Service Delivery
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Improved community wellbeing through accelerated service delivery | Electricity | % of faulty streetlights fittings maintained within 90 days | BS 07/08 | Oper | 508 | 100% | 100% | Achieved | No stock in Stores >6 months. Specification submitted 18/07/2016. Not even BSC yet. | Request SCM to stock Stores and process submissions.
 |  | % of faulty Mast light fittings repaired within 90 days | BS 09/10 | Oper | 142 | 100% | 100% | Achieved | No stock in Stores >6 months. Specification submitted 18/07/2016. Not even BSC yet. | Request SCM to stock Stores and process submissions.
 |  | % of households with access to basic levels of electricity by the 30 June 2017 (GKPI) | New | INEP | 97,0% | N/A | N/A | N/A | First request only 3 partial submissions. Second request only 1 partial submission to date. | Encourage Councillors to submit backlogs
 | Project Management | % of new Capital projects started on time In terms of the appointment of consultants / contractors for EPMLM funded projects as per the Capital implementation plan | New | Oper | New | 50% | 0% | Not Achieved | Four tenders for appointment of Consultants closed on the 09/09/2016. 1 tender for construction closed on the 19/09/2016. | Its recommended that SCM must expedite the convening of BEC
KPA 2 - Basic Service

## Slide 41
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2: Basic Service Delivery
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Improved community wellbeing through accelerated service delivery | Project Management | % of new Capital projects completed in terms of agreed schedule for EPMLM funded projects by Jun 30 2017 | New | Oper | New | N/A | N/A | N/A | N/A delays in convening BEC. Four tenders for appointment of Consultants closed on the 09/09/2016. 1 tender for construction closed on the 19/09/2016. | N/A Its recommended that SCM must expedite the convening of BEC
 |  | % of Capital budget spend in terms of new IDP identified projects as per the Capital implementation plan by the 30 June 2017 (GKPI) | New | Oper | New | N/A | N/A | N/A | N/A delays in convening BEC. Four tenders for appointment of Consultants closed on the 09/09/2016. 1 tender for construction closed on the 19/09/2016 | N/A
 | Roads and storm water | % spending on MIG funding by the 30 June 2017 | New | Oper | New | N/A | N/A | N/A | N/A No appointments have been made to date. | N/A Appointment of service providers to be expedited.
 | SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (IS) | FV 07 | Oper | New | 100% | 100% | Achieved | None | None
 |  | # of quarterly reports submitted to Council in terms of compliance to the CoGHSTA Back to Basics reporting system | New | Oper | New | 1 | 1 | Achieved | None | None
KPA 2 - Basic Service

## Slide 42
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 3: Local Economic Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Grow the economy and provide livelihood support | LED | # of EPWP job opportunities provided through EPWP grant by 30 June 2017 (GKPI) | LED 03/08 | 601,2 | 253 | 50 | 0 | Not Achieved | Late appointments of EPWP participants and Service provider for supplying PPE'S | The Municipality should appoint EPWP participants as soon as possible so that we should start spending

## Slide 43
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 4: Municipal Transformation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 31 March 2017 (IS) | MTOD 09 | Oper | new | N/A | N/A | N/A | N/A | N/A

## Slide 44
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (IS) | GG 14/15 | Oper | New | 100% | N/A | No Internal Audit conducted in the quarter under review | None | None
 |  | % of AG Management Letter findings resolved by 30 Jun 2017 (IS) | GG 11/12/13 | Oper | New | 100% | N/A | N/A | N/A | N/A
 |  | % execution of identified risk management plan within prescribed timeframes per quarter (IS) | GG 16 | Oper | New | 100% | N/A | The actions on the risk register are targeted for second Quarter | None | None

## Slide 45
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
Overall Performance for Infrastructure
OVERALL PERFORMANCE | 
TARGETS ACHIEVED | 7
TARGETS NOT ACHIEVED | 3
% ACHIEVEMENT FIRST QUARTER PERFORMANCE | 70,0%
BUDGET | R 4 413 932.30
EXPENDITURE | R 632 011.77

## Slide 46: Community Services
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW

## Slide 47
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2 - Basic Service Delivery
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Improved community wellbeing through accelerated service delivery | Waste removal | % of households with access to a minimum level of basic waste removal by 30 June 2017 (once per week) (GKPI) | BS 94 | Oper | 17,4% | >17,4% | N/A | N/A | N/A | N/A | N/A
 |  | # of existing households in formal settlements provided with solid waste removal services by 30 Jun 2017 | BS 94 | Oper | 5619 | 5619 | N/A | N/A | N/A | N/A | N/A
 | SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (Social) | FV 07 | Oper | New | 100% | 100% | 100% | Achieved | No invite received from SCM | Outwith departments control, SCM convene meetings
 | Environmental management | External audit of the Landfill to comply with National Environmental Waste Act by 30 Jun 2017 | BS 98 | 90 | 1 | 1 | N/A | N/A | N/A | N/A | N/A

## Slide 48
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2 - Basic Service Delivery
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Effective and Efficient Community Involvement | Environmental management | # of landscaping and greening project implemented by 30 Jun 2017 | BS 102 | 1.2 | 1 | 1 | N/A | N/A | N/A | N/A | N/A
 | Community Facilities | # of Cultural and Heritage festivals held by 30 Jun 2017 | BS 116/117 | 210 | 2 | 2 | N/A | N/A | N/A | N/A | N/A
 |  | # of cemeteries fenced by 30 Jun 2017 | BS 109 | 690 | 7 | 6 | N/A | N/A | N/A | N/A | N/A
 |  | # of Mayor’s cup events held by 30 Jun 2017 | BS 114 | 65 | 1 | 1 | N/A | N/A | N/A | N/A | N/A
 |  | # of Mayors marathon events held by 31 Mar 2017 | BS 115 | 40 | 2 | 1 | N/A | N/A | N/A | N/A | N/A
 |  | # of Club Federations supported to promote sporting development by 30 Jun 2017 | BS 120 | 90 | New | 4 | 1 | 0 | Not achieved | SAC Officers suspended | Awaiting outcome of disciplinary process

## Slide 49
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2 - Basic Service Delivery
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Effective and Efficient Community Involvement | HIV & AIDS and other diseases | # of quarterly Local Aids Council forum meetings held | BS 112 | 64,5 | 4 | 4 | 1 | 1 | Achieved | N/A | N/A
 |  | # of quarterly HIV /AIDS awareness campaigns | BS 113 | 40,8 | 4 | 4 | 1 | 0 | Not Achieved | No Annual programme and decision on areas to cover | Annual programme to be drawn and implemented

## Slide 50
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 4: Municipal Transformation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 31 March 2017 (Social) | MTOD 09 | Oper | 3 | 3 | N/A | N/A | N/A | N/A | N/A

## Slide 51
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (SS) | GG 14/15 | Oper | New | 100% | 100% | N/A | No Internal Audit conducted in the quarter under review | None | None
 |  | % of AG Management Letter findings resolved by 30 Jun 2017 (SS) | GG 11/12/13 | Oper | New | 100% | N/A | N/A | N/A | N/A | N/A
 |  | % execution of identified risk management plan within prescribed timeframes per quarter (SS) | GG 16 | Oper | New | 100% | 100% | N/A | The actions on the risk register are targeted for second Quarter | None | None

## Slide 52
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
OVERALL PERFORMANCE | 
TARGETS ACHIEVED | 2
TARGETS NOT ACHIEVED | 2
% ACHIEVEMENT FIRST QUARTER PERFORMANCE | 50,0%
BUDGET | R 1 104 001.20
EXPENDITURE | R 0.00
Overall Performance for Community Services

## Slide 53: BUDGET AND TREASURY
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW

## Slide 54
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 2 - Basic Service Delivery
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Improved community wellbeing through accelerated service delivery | SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (BT) | FV 07 | Oper | New | 100% | 100% | 20% | Not Achieved | Lack of resources | to Fast-tract recruitment process and adherence to scheduled committee meetings
 |  | Average # of days elapsed on successful bids awarded as per the competitive bidding process for tenders over R200,000 | FV 07 | Oper | New | 60 | 60 | 100% | Achieved | none | none

## Slide 55
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 4: Municipal Transformation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 30 Jun 2017 (BT) | MTOD 09 | Oper | 0 | 1 | N/A | N/A | N/A | N/A | N/A

## Slide 56
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 5: Municipal Financial Viability
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Become Financially Viable | Financial Management | % of consumer quarterly payment level received as compared to that billed | FV 02 | Oper | 100% | >80,9% | >80,9% | 74% | Not Achieved | data integrity, non culture of payment for municipal services | continuous data cleansing and awareness's through media communication
 |  | % of approved (compliant) invoices paid within 30 days | FV 03 | Oper | 4 | 100% | 100% | 99% | Not Achieved | Invoice disputes | Request suppliers to send revised invoice as per date resolving the invoice queries
 |  | # of monthly section 66 MFMA reports submitted to Council with respect to staff remuneration | FV 06 | Oper | 12 | 12 | 3 | 3 | Achieved | None | None
 |  | Submission of MTRE Budget to Council for approval by the 31 May | FV 05 | Oper | 1 | 1 | N/A | N/A | N/A | N/A | N/A
 |  | # of monthly section 71 MFMA reports submitted to EXCO within legislative timeframes | FV 06 | Oper | 12 | 12 | 3 | 3 | Achieved | None | None

## Slide 57
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 5: Municipal Financial Viability
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Become Financially Viable | Financial Management | # of SCM quarterly reports submitted to Exco | FV 07 | Oper | 4 | 4 | 1 | 1 | Achieved | None | None
 |  | Annual submission of the asset verification report to the MM by 30 Sept 2016 | FV 08 | Oper | 1 | 1 | 1 | 1 | Achieved | None | None
 |  | Draft Annual Financial Statements (AFS) submitted on or before the 28 August 2016 | FV 10 | 3 210 | 1 | 1 | 1 | 1 | Achieved | None | None
 |  | % spend of the FMG funds by 30 Jun 2017 | FV 11 | FMG 1810 | 100% | 100% | 25% | 8% | Not Achieved | The invoice for the upgrade of financial system was received towards month end of the 1st quarter which ended up being paid in the 2nd Quarter | The municipality will fast-track spending, starting from the second quarter since we have paid an upgrade for financial system. This will also enable MUNSOFT consultant to be onsite to assist the municipality with the implementation of mSCOA.

## Slide 58
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 5: Municipal Financial Viability
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Become Financially Viable | Financial Management | # of quarterly section 52(d) MFMA reports submitted to Executive Mayor within legislative timeframes | FV 06 | Oper | New | 4 | 1 | 1 | Achieved | None | None
 |  | Section 72 (midyear) MFMA reports submitted to Executive Mayor within legislative timeframes | FV 06 | Oper | New | 1 | N/A | N/A | N/A | N/A | N/A
 |  | # of monthly SCM deviation reports submitted to the MM | FV 07 | Oper | New | 12 | 3 | 3 | Achieved | None | None
 |  | # of municipal fleet vehicle reports submitted each quarter | FV 09 | Oper | New | 4 | 1 | 1 | Achieved | None | None
 |  | # of MFMA checklists submitted per quarter as legislated | FV 06 | Oper | New | 12 | 3 | 3 | Achieved | None | None

## Slide 59
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 5: Municipal Financial Viability
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Become Financially Viable | Financial Management | % of (indigents) households with access to free basic electricity services by 30 Jun 2017 (GKPI | New | Oper | New | 100% | 100% | 0% | Not Achieved |  | 
 |  | Cost coverage ratio by the 30 June 2017 (GKPI) | New | Oper | 18,6 | 4,7 | N/A | N/A | N/A | N/A | N/A
 |  | % outstanding service debtors to revenue by the 30 June 2017 (GKPI) | New | Oper | 35,7% | 31,40% | N/A | N/A | N/A | N/A | N/A
 |  | % Debt coverage ratio by the 30 June 2017 (GKPI) | New | Oper | 12,3 | 18,8 | N/A | N/A | N/A | N/A | N/A

## Slide 60
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
KPA 6: Good Governance
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | Annual Target | 2016/17 1st Quarter |  |  |  | 
 |  |  |  |  |  |  | Target | Actual | Achievements | Challenges | Corrective Action
Build effective and efficient Organization | Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (BT) | GG 14/15 | Oper | New | 100% | 100% | N/A | No Internal Audit conducted in the quarter under review | None | None
 |  | % of AG Management Letter findings resolved by 30 Jun 2017 (BT) | GG 11/12/13 | Oper | New | 100% | N/A | N/A | N/A | N/A | N/A
 |  | % execution of identified risk management plan within prescribed timeframes per quarter (BT) | GG 16 | Oper | New | 100% | 100% | N/A | The actions on the risk register are targeted for second Quarter | None | None
 |  | Action Plan on issues raised by the Auditor General compiled and tabled to Council by January 2017 | GG 11 | Oper | New | 1 | N/A | N/A | N/A | N/A | N/A

## Slide 61
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW
Overall Performance for Budget & Treasury
OVERALL PERFORMANCE | 
TARGETS ACHIEVED | 10
TARGETS NOT ACHIEVED | 5
PERCENTAGE FOR ANNUAL PERFORMANCE | 66,7%
BUDGET | R 5 020 000
EXPENDITURE | R 3 223 227

## Slide 62
THANK YOU
EPMLM 2016/2017 FIRST QUARTER PERFORMANCE REVIEW