## PED
Planning & Economic Development
KPA 1: Spatial Rationale
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter
[6 empty] | Target | Actual | Achievements | Challenges | Corrective Action | POE
House the nation and build Integrated Human Settlement | Land use management | % of land use applications received and processed within 60 days as per the Town Planning and Township Ordinance Act 15 of 1986 | SR 01 | Oper | 20 | 100% | 30% | Not Achieved The newly formed district SPLUMA monthly working group meetings, assist in the discussion of received town planing applications. | The slow implementation of the Municipal Planning Tribunial, affects land devlopmental applications recived and the timeframes associated with legislations. | Accecpt submitted applications and submitt to council for decision, not to infringe on the legislated time-frames. | Land Use application register
|  | # of EPMLM Town Planning By-Laws developed and gazetted by Dec 2016 | SR 02 | Oper | 1 | N/A | N/A | 1 Draft EPMLM Town Planning By-Laws. The newly formed district SPLUMA monthly working group meetings, assist in the assessement of the Municipal By-Laws. | The by-laws not adpted by previous council, citing reasons that proof of the public participation was conducted. | Re-submitt item to council with annuxures of advert,attendance register for all 4 consulatative public partipation process conducted MARCH 2016 | Council Resolution, agenda and proof of Gazette
|  | # of EPMLM Billboard and Advertising by-law developed and gazetted by Jun 2017 | SR 03 | Oper | New | N/A | N/A | By-Lwas in draft phase.The By-Laws was done in the finacial year 2013/14 and public participation conducted however needs to be insync with the town planning by-laws. | The By-Laws was done in the finacial year 2013/14 and public participation conducted however needs to be insync with the town planning by-laws. | Ensure that by Q3 public participatiion | Council Resolution, agenda and proof of Gazette
|  | % of New Building Plans of less than 500 square meters assessed within 10 days of receipt of plans. | SR 04 | Oper | 50 | 100% | 100% | Achieved | N/A | N/A | Individual site inspection reports and the Building plan file register
House the nation and build Integrated Human Settlement | Land use management | % of New Building Plans of more than 500 square meters assessed within 28 days of receipt of plans. | SR 04 | Oper | New | 100% | 100% | Achieved No plans were submitted | N/A | N/A | Building Plan submission register
|  | # of municipal buildings to be maintained as per the approved municipal maintenance plan by the 30 Jun 2017 | SR 06 | 572.3 | 35 | 5 | 3 | Not Achieved 5 request made for the building maintenance | The waiting period from SCM department on request for goods is affecting us in terms of perfomance. | Supply chain department is attending to the requets submitted. | Section 72 financial report
|  | # of Land Use Awareness workshops to held with Magoshi by 30 June 2017 | SR 08 | Oper | 2 | 1 | 1 | Achieved | Conducted August 2016, received support from all traditional authorities, Cogshta and Salga | N/A | Attendance registers and reports
| Housing | Develop a municipal building maintenance plan and submit to Council for approval by 30 Sept 2016 | SR 05 | Oper | New | 1 | 1 | Achieved | Municipal building have been assessed as on the maintanance plan and prioritised considering the funds available as most of the Municipal Houses are very old. | More Funds are required for the renovations of such. | Inspection Reports
House the nation and build Integrated Human Settlement | Housing | Number of municipal houses to be maintained as per the approved municipal maintenance plan by the 30 Jun 2017 | SR 07 | Oper | New | 10 | 3 | Not Achieved | Requests for the general maintanance on 3 municipal houses are being done and still awaits SCM to invite service providers for inspections. | The waiting period from SCM department on request for goods is affecting us in terms of perfomance. | Approved Maintenance Plan
| SDF | Review EPMLM Spatial Development Framework and adopted by Council by 31 March 2017 | SR 10 | 106 | 0 | N/A | N/A | Terms of Refernce, Specification and Advert done. | Municpal Budget for the project, no sufficient available | To seek funds from Coghsta as province indicated that they would support municpalities that have gazzetted their Municipal Town Planning By-Laws. Ensure that By-Laws are approved by council to gazette. | Council Resolution and agenda
|  | Review EPMLM Town Planning Scheme by 31 March 2017 | SR 11 | Oper | 0 | N/A | N/A | Terms of Refernce, Specification and Advert done. | N/A | N/A | Council Resolution and agenda
| Land use management | % of buildings; constructed with approved plans, inspected that comply with the National Building Regulations and Building Standards Amendments Act No 49 of 1995 | SR 04 | Oper | New | 100% | 100% | Achieved | N/A | N/A | Individual site inspection reports and the Building plan file register
KPA 2 - Basic Service Delivery and Infrastructure Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter
[6 empty] | Target | Actual | Achievements | Challenges | Corrective Action | POE
House the nation and build Integrated Human Settlement | Housing | # of reports in terms of new RDP Housing units provided by the CoGHSTA submitted to Council by 30 Jun 2017 | SR 13 /14 | Oper | 278 | 1 | 0 | Not Achieved | Developers are beig appointed by Cohgsta recently and they still working on material issues and also meeting with the councillors for the appointments of labours |  | Annual RDP Housing report
| SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (P&ED) | FV 07 | Oper | New | 100% | 66% | Not Achieved | Attended 2/3 | To adhere to the Bid Committee Meetings Schedule | Attendance register
KPA 3: Local Economic Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter
[6 empty] | Target | Actual | Achievements | Challenges | Corrective Action | POE
Grow the economy and provide livelihood support | LED | # of quarterly SMME's and Cooperatives capacity building skill workshops scheduled and held | LED 01 | 0 | 4 | 1 |  |  |  |  | Attendance registers
|  | # of Coop's supported with respect to financial support by 30 Jun 2017 | LED 02 | 0 | 10 | 3 |  |  |  |  | Copies of completed funding application forms
|  | # of quarterly LED forum meetings held | LED 03 | 21.2 | 4 | 1 |  |  |  |  | Reports and Attendance Registers
Develop partnerships |  | Hosting of a LED Summit by 30 Jun 2017 | LED 04 | 84.8 | 1 | N/A |  |  |  |  | Reports and Attendance Register
|  | Tourism Association established by Dec 2016 | LED 05 | 0 | 0 | N/A |  |  |  |  | Reports and Attendance Register
Develop partnerships | LED | Hosting of a Businesses Tourism Indaba by 30 Jun 2017 | LED 09 | 0 | 2 | N/A |  |  |  |  | Reports and Attendance Register
|  | # of quarterly reports submitted to Council with respect to the implementation of Social Labour Plan (SLP) programmes of Mining Companies | New | Oper | New | 1 |  |  |  |  | Quarterly report and Council resolution
|  | # of quarterly reports submitted to Council with respect to the Corporate Social Investment (CSI) programmes of both Business and Mining organisations | New | Oper | New | 1 |  |  |  |  | Quarterly report and Council resolution
Grow the economy and provide livelihood support |  | Review and update the cooperative database by 30 June 2017 | LED 06 | 0 | 1 | N/A |  |  |  |  | Updated Cooperatives database
KPA 4: Municipal Transformation and Institutional Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter
[6 empty] | Target | Actual | Achievements | Challenges | Corrective Action | POE
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 31 March 2017 (P&ED) | MTOD 09 | Oper | 0 | N/A |  |  |  |  | Council Resolution and agenda
KPA 6: Good Governance and Public Participation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 2016/17 1st Quarter
[6 empty] | Target | Actual | Achievements | Challenges | Corrective Action | POE
Build effective and efficient Organization | Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (P&ED) | GG 14/15 | Oper | New | 100% |  |  |  |  | Quarterly IA status reports
|  | % of AG Management Letter findings resolved by 30 Jun 2017 (P&ED) | GG 11/12/13 | Oper | New | 100% |  |  |  |  | Quarterly AG Action Plan report
|  | % execution of identified risk management plan within prescribed timeframes per quarter (P&ED) | GG 16 | Oper | New | 100% |  |  |  |  | Quarterly Risk management committee reports
Note on B28: Alan Percy: Who will complete this section
Note on H25: Alan Percy: Target inadvertently reflected %
Note on I9: Alan Percy: N/A as target ia only applicable for 2nd Qtr
Note on I10: Alan Percy: N/A target only applicable for 4th Qtr
Note on I12: Alan Percy: Reflect as 100%
Note on I13: Alan Percy: Actual requires a number but it appears from the comments that no building were maintained therefore actual should reflect zero and comment "Not Achieved" 0
Note on I15: Alan Percy: Reflect as 1
Note on I16: Alan Percy: Needs to reflect actual achievement
Note on I17: Alan Percy: N/A added
Note on I19: Alan Percy: Needs to reflect actual achievement
Note on I26: Alan Percy: Actual revised to reflect meetings attended
Note on I46: Alan Percy: Please populate, as quarterly achievement needed
Note on I52: Alan Percy: Please populate, as quarterly achievement needed
Note on I53: Alan Percy: Please populate, as quarterly achievement needed
Note on I54: Alan Percy: Please populate, as quarterly achievement needed
Note on J11: Alan Percy: Coments revised
Note on J12: Alan Percy: Comments revised
Note on J14: Alan Percy: Comments revised
Note on J15: Alan Percy: Reflect as Achieved and comment moved to "Challenges"
Note on J25: Alan Percy: Not Achieved added and comment moved to "Challenges"
Note on J26: Alan Percy: Not Achieved added and comment moved to "Challenges"
Note on K18: Alan Percy: N/A added
Note on L46: Alan Percy: Refers to Sale/Disposal of Council