## Infras
Infrastructure Services
KPA 2 - Basic Service Delivery and Infrastructure Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Improved community wellbeing through accelerated service delivery | Roads and storm water | # of Kms of roads to be graded by 30 Jun 2017 | BS 89 | Oper 1 644 | 1 200km | 356.824 km | 300km | 454.313 | achieved | none | none | >1 200km | Inspection report
|  | Number of m2 of base and surface patches repaired by 30 Jun 2017 | BS 90 | Oper | 900 m2 | 538.932m2 | 300 m2 | 863.31 | achieved | none | none | <1200 m2 | Inspection report
|  | Review Roads Master plan and adopted by Council by 31 March 2017 | BS 59 | Oper | 1 | N/A | N/A | Assessment ;reviewing and closure | Not Achived | none | none | 1 | Council Resolution and agenda
|  | # of Kms of gravel roads to be constructed in tar by 30 Jun 2017 | BS 48/50/52/53/54/70 | MIG 7 000 | 4,7kms | N/A | N/A |  |  |  |  | 4km | Completion Certificate
|  | # of kms of Storm Water to be constructed in Ext 6 by 30 Jun 2017 | BS 45 | 6000 | 400m | N/A | N/A |  |  |  |  | 500m | Completion Certificate
|  | # of Kms of roads to be rehabilitated by 30 Jun 2017 | BS 71/84 | MIG 4 500 | New | N/A | N/A |  |  |  |  | 1km | Completion Certificate
Improved community wellbeing through accelerated service delivery | Roads and storm water | Number of Km of roads to be constructed by 30 Jun 2017 (Industrial Road) | BS 57 | MIG 1 000 | 400m | 0km | N/A |  |  |  |  | 250M | Completion Certificate
| Electricity | Number of high mast lights connected by 30 Jun 2017 | BS 17/32/38 | 5200 | 10 | N/A | N/A | N/A | ESKOM installed 6 of 16 supplies supplies. | ESKOM slow to install supply points. No transport for TLB. Waiting for material. Vacancies | Get truck licensed and roadworthy. Request SCM to source material. Request HR to fill vacancies | 17 | Certificate of compliance
|  | # of Quarterly reports in terms of households with access to basic levels of electricity submitted to the MM (GKPI) | New | Oper | New | 1 | 1 | 1 | 1 | ESKOM report for December 2016 only available mid January 2017. Only few backlog submissions from Councillors. | Request Councillors to submit baclog data. | 4 | Copy of Quarterly reports and Eskom monthly report
|  | Develop an Energy Master & OM plan and submit to Council for adoption by 31 March 2017 | BS 22 | 500 | New | N/A | N/A | N/A | Energy Master Plan: Recorders installed in all substations. OM Plan: Specification submitted 11/8/2016. Section 32 proposal submitted to Director. | Energy Master Plan: Concern about electrification backlog and public lighting. OM Plan: SCM did not process submission. Limited time left to complete. | Energy Master Plan: Follow-up with MISA about electrification backlog and public lighting. OM Plan: Follow section 32 appointment due to limited time left & cost saving. | 1 | Council Resolution and agenda
|  | # high mast lights upgraded to led fittings by 30 Jun 2017 | BS 10/25 | 400 | New | N/A | N/A | N/A | Service Provider appointed. | None | None | 30 | Completion Certificate
Improved community wellbeing through accelerated service delivery | Electricity | % of faulty streetlights fittings maintained within 90 days | BS 07/08 | Oper | 508 | 100% | 100% | 100% | 100% | No stock in SCM stores. Vacancies. Submission on 18/07/2016 for material not processed | Maintain stock levels. Fill vacancies. Process request for material. | 100% | Inspection/repair reports. Monthly reports.
|  | % of faulty Mast light fittings repaired within 90 days | BS 09/10 | Oper | 142 | 100% | 100% | 100% | 100% | No stock in SCM stores. Vacancies. Submission on 18/07/2016 for material not processed | Maintain stock levels. Fill vacancies. Process request for material. | 100% | Inspection/repair reports. Monthly reports.
|  | % of households with access to basic levels of electricity by the 30 June 2017 (GKPI) | New | Oper | 97% | N/A | N/A | N/A | ESKOM completed 21 connections | ESKOM deferred 5 projects. | Update backlog | >97% | Completion certificates provided by contracted consultants
| Project Management | % of new Capital projects started on time In terms of the appointment of consultants / contractors for EPMLM funded projects as per the Capital implementation plan | New | Oper | New | 0% | 100% |  |  |  |  | 100% | Individual project appointment letters in terms of consultants / contractors
Improved community wellbeing through accelerated service delivery | Project Management | % of new Capital projects completed in terms of agreed schedule for EPMLM funded projects by Jun 30 2017 | New | Oper | New | N/A | N/A |  |  |  |  | 100% | Individual project certificates of completion (COC)
|  | % of Capital budget spend in terms of new IDP identified projects as per the Capital implementation plan by the 30 June 2017 (GKPI) | New | Oper | New | N/A | 25% |  |  |  |  | 100% | Section 72 financial report
| Roads and storm water | % spending on MIG funding by the 30 June 2017 | New | Oper | New | N/A | 25% |  |  |  |  | 100% | Section 72 financial report
| SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (IS) | FV 07 | Oper | New | 100% | 100% |  |  |  |  | 100% | Attendance register
|  | # of quarterly reports submitted to Council in terms of compliance to the CoGHSTA Back to Basics reporting system | New | Oper | New | 1 | 1 |  |  |  |  | 400% | Copy of Quarterly report submitted to CoGHSTA
KPA 3: Local Economic Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Grow the economy and provide livelihood support | LED | # of EPWP job opportunities provided through EPWP grant by 30 June 2017 (GKPI) | LED 03/08 | 601.2 | 253 | 0 | 100 | 83 | Not achieved | Late appointment on Capital projects | The Municipality to appoint and project must commence with construction as soon as possible. | 305 | Quarterly reports submitted to the Department of Public Work
KPA 4: Municipal Transformation and Institutional Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 31 March 2017 (IS) | MTOD 09 | Oper | new | N/A | N/A |  |  |  |  | 2 | Council Resolution and agenda
KPA 6: Good Governance and Public Participation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Build effective and efficient Organization | Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (IS) | GG 14/15 | Oper | New | N/A | 100% |  |  |  |  | 100% | Quarterly IA status reports
|  | % of AG Management Letter findings resolved by 30 Jun 2017 (IS) | GG 11/12/13 | Oper | New | N/A | N/A |  |  |  |  | 100% | Quarterly AG Action Plan report
|  | % execution of identified risk management plan within prescribed timeframes per quarter (IS) | GG 16 | Oper | New | N/A | 100% |  |  |  |  | 100% | Quarterly Risk management committee reports
Note on G21: Alan Percy: based on backlog of 958 and h/h 32284