## PED
Planning & Economic Development
KPA 1: Spatial Rationale
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
House the nation and build Integrated Human Settlement | Land use management | % of land use applications received and processed within 60 days as per the Town Planning and Township Ordinance Act 15 of 1986 | SR 01 | Oper | 20 | 30% | 100% |  |  |  |  | 100% | Land Use application register
|  | # of EPMLM Town Planning By-Laws developed and gazetted by Dec 2016 | SR 02 | Oper | 1 | N/A | 1 |  |  |  |  | 1 | Council Resolution, agenda and proof of Gazette
|  | # of EPMLM Billboard and Advertising by-law developed and gazetted by Jun 2017 | SR 03 | Oper | New | N/A | N/A |  |  |  |  | 1 | Council Resolution, agenda and proof of Gazette
|  | % of New Building Plans of less than 500 square meters assessed within 10 days of receipt of plans. | SR 04 | Oper | 50 | 100% | 100% |  |  |  |  | 100% | Individual site inspection reports and the Building plan file register
House the nation and build Integrated Human Settlement | Land use management | % of New Building Plans of more than 500 square meters assessed within 28 days of receipt of plans. | SR 04 | Oper | New | 100% | 100% |  |  |  |  | 100% | Building Plan submission register
|  | # of municipal buildings to be maintained as per the approved municipal maintenance plan by the 30 Jun 2017 | SR 06 | 572.3 | 35 | 0 | 5 |  |  |  |  | 20 | Section 72 financial report
|  | # of Land Use Awareness workshops to held with Magoshi by 30 June 2017 | SR 08 | Oper | 2 | 1 | 1 |  |  |  |  | 4 | Attendance registers and reports
| Housing | Develop a municipal building maintenance plan and submit to Council for approval by 30 Sept 2016 | SR 05 | Oper | New | 1 | N/A |  |  |  |  | 1 | Inspection Reports
House the nation and build Integrated Human Settlement | Housing | Number of municipal houses to be maintained as per the approved municipal maintenance plan by the 30 Jun 2017 | SR 07 | Oper | New | 0 | 10 |  |  |  |  | 40 | Approved Maintenance Plan
| SDF | Review EPMLM Spatial Development Framework and adopted by Council by 31 March 2017 | SR 10 | 106 | 0 | N/A | N/A |  |  |  |  | 1 | Council Resolution and agenda
|  | Review EPMLM Town Planning Scheme by 31 March 2017 | SR 11 | Oper | 0 | N/A | N/A |  |  |  |  | 1 | Council Resolution and agenda
| Land use management | % of buildings; constructed with approved plans, inspected that comply with the National Building Regulations and Building Standards Amendments Act No 49 of 1995 | SR 04 | Oper | New | 0% | 100% |  |  |  |  | 100% | Individual site inspection reports and the Building plan file register
KPA 2 - Basic Service Delivery and Infrastructure Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
House the nation and build Integrated Human Settlement | Housing | # of reports in terms of new RDP Housing units provided by the CoGHSTA submitted to Council by 30 Jun 2017 | SR 13 /14 | Oper | 278 | 0 | 1 |  |  |  |  | 4 | Annual RDP Housing report
Improved community wellbeing through accelerated service delivery | SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (P&ED) | FV 07 | Oper | New | 66% | 100% |  |  |  |  | 100% | Attendance register
KPA 3: Local Economic Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Grow the economy and provide livelihood support | LED | # of quarterly SMME's and Cooperatives capacity building skill workshops scheduled and held | LED 01 | 0 | 4 | 2 | 2 | 4 | Achieved | NONE | NONE | 4 | Attendance registers
|  | # of Coop's supported with respect to financial support by 30 Jun 2017 | LED 02 | 0 | 10 | 10 | 6 | 10 | NONE | The targeted cooperatives could not finalise the other compliance documents and promised to make submission at the beginning of the new year. | The LED officals to follow up on the potential cooperatives to be assisted with application for funding | 12 | Copies of completed funding application forms
|  | # of quarterly LED forum meetings held | LED 03 | 21.2 | 4 | 1 | 2 | 2 | Achieved | NONE | NONE | 4 | Reports and Attendance Registers
Develop partnerships |  | Hosting of a LED Summit by 30 Jun 2017 | LED 04 | 84.8 | 1 | N/A | N/A |  |  |  |  | 1 | Reports and Attendance Register
|  | Tourism Association established by Dec 2016 | LED 05 | 0 | 0 | N/A | 1 | 0 | Not Achieved |  | To liase with Limpopo Tourism Agency to conduct seminar to encourage tourism product owners prior the launching on the Association by end of 3rd quarter. | 1 | Reports and Attendance Register
Develop partnerships | LED | Hosting of a Businesses Tourism Indaba by 30 Jun 2017 | LED 09 | 0 | 2 | N/A | N/A |  |  |  |  | 1 | Reports and Attendance Register
|  | # of quarterly reports submitted to Council with respect to the implementation of Social Labour Plan (SLP) programmes of Mining Companies | New | Oper | New | 0 | 2 | 0 | Not Achieved | The minning companies could not confirm the proposed meetings. | The LED unit approached the Minning Development Agency to intervene in ensuring that the meeting become successful | 4 | Quarterly report and Council resolution
|  | # of quarterly reports submitted to Council with respect to the Corporate Social Investment (CSI) programmes of both Business and Mining organisations | New | Oper | New | 0 | 2 | 0 | Not Achieved | The minning companies could not confirm the proposed meetings. | The LED unit approached the Minning Development Agency to intervene in ensuring that the meeting become successful | 4 | Quarterly report and Council resolution
Grow the economy and provide livelihood support |  | Review and update the cooperative database by 30 June 2017 | LED 06 | 0 | 1 | N/A | N/A |  |  |  |  | 1 | Updated Cooperatives database
KPA 4: Municipal Transformation and Institutional Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 31 March 2017 (P&ED) | MTOD 09 | Oper | 0 | N/A | N/A |  |  |  |  | 1 | Council Resolution and agenda
KPA 6: Good Governance and Public Participation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Build effective and efficient Organization | Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (P&ED) | GG 14/15 | Oper | New | N/A | 100% |  |  |  |  | 100% | Quarterly IA status reports
|  | % of AG Management Letter findings resolved by 30 Jun 2017 (P&ED) | GG 11/12/13 | Oper | New | N/A | N/A |  |  |  |  | 100% | Quarterly AG Action Plan report
|  | % execution of identified risk management plan within prescribed timeframes per quarter (P&ED) | GG 16 | Oper | New | N/A | 100% |  |  |  |  | 100% | Quarterly Risk management committee reports
Note on M46: Alan Percy: Refers to Sale/Disposal of Council