## Social
Social Services
KPA 2 - Basic Service Delivery and Infrastructure Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Improved community wellbeing through accelerated service delivery | Waste removal | % of households with access to a minimum level of basic waste removal by 30 June 2017 (once per week) (GKPI) | BS 94 | Oper | 17.4% | N/A | N/A | 5619 | Status quo remains, no increase in collection | No extension of services to other areas | Finalise payment -Leeufontein , Elandskraal . | >17,4% | Weekly waste collection schedules
|  | # of existing households in formal settlements provided with solid waste removal services by 30 Jun 2017 | BS 94 | Oper | 5619 | N/A | N/A | 5619 | 5619 households serviced once a week | Some fleet availibility during breakdowns | Preventative maintenance on fleet | 5619 | Weekly waste collection schedules
| SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (Social) | FV 07 | Oper | New | 100% | 100% | 100% | 100% | None | None | 100% | Attendance register
| Environmental management | External audit of the Landfill to comply with National Environmental Waste Act by 30 Jun 2017 | BS 98 | 90 | 1 | N/A | N/A | N/A | Only for quarter 4 | None | Currently working on the landfill audit action plan. | 1 | External Audit report
Effective and Efficient Community Involvement | Environmental management | # of landscaping and greening project implemented by 30 Jun 2017 | BS 102 | 120 | 1 | N/A | N/A | N/A | None | Masterplan to be presented to Management and approved. | Identification of projects for quick wins | 1 | Completion certificate
| Community Facilities | # of Cultural and Heritage festivals held by 30 Jun 2017 | BS 116/117 | 210 | 2 | N/A | N/A | N/A | Preparation was done for the Ditrupa event | Short term planning . Event is growing annually | Long term planning for the events | 2 | Approved project plan signed reports
|  | # of cemeteries fenced by 30 Jun 2017 | BS 109 | 690 | 7 | N/A | N/A | N/A | Request for procurement process was done in October 2017 | Wait for scm processes | Procurement to be finalised | 6 | Completion certificates
|  | # of Mayor’s cup events held by 30 Jun 2017 | BS 114 | 65 | 1 | N/A | N/A | N/A | First rounds of cluster competitions were held | None | None | 1 | Final report
|  | # of Mayors marathon events held by 31 Mar 2017 | BS 115 | 40 | 2 | N/A | N/A | N/A | For 3 rd qouarter | None | None | 1 | Final report
|  | # of Club Federations supported to promote sporting development by 30 Jun 2017 | BS 120 | 90 | New | 0 | 1 | 0 | Not achieved | No programme finalised | Finalise support programme | 4 | Completion Handover report
Effective and Efficient Community Involvement | HIV & AIDS and other diseases | # of quarterly Local Aids Council forum meetings held | BS 112 | 64.5 | 4 | 1 | 1 | 2 | Achieved | Launcing of LAC | Finalise LAC Structure | 4 | Attendance register and annual programme
|  | # of quarterly HIV /AIDS awareness campaigns | BS 113 | 40.8 | 4 | 0 | 1 | 1 | Achieved | None | None | 4 | Attendance register and annual programme
KPA 4: Municipal Transformation and Institutional Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 31 March 2017 (Social) | MTOD 09 | Oper | 3 | N/A | N/A | N/A | Draft sport policy sent for approval | Wait for approval finalisation | Finalise two other policies | 3 | Council Resolution and agenda
KPA 6: Good Governance and Public Participation
Strategic Objective | Priority Programme | KPI | IDP Ref No | Budget R 000's | Baseline 2014/15 | 1st Qtr Actual | 2016/17 2nd Quarter |  |  |  |  | Annual Target
[7 empty] | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Build effective and efficient Organization | Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (SS) | GG 14/15 | Oper | New | N/A | 100% |  |  |  |  | 100% | Quarterly IA status reports
|  | % of AG Management Letter findings resolved by 30 Jun 2017 (SS) | GG 11/12/13 | Oper | New | N/A | N/A |  |  |  |  | 100% | Quarterly AG Action Plan report
|  | % execution of identified risk management plan within prescribed timeframes per quarter (SS) | GG 16 | Oper | New | N/A | 100% |  |  |  |  | 100% | Quarterly Risk management committee reports
Note on G8: Alan Percy: based on backlog of 26665 and h/h 32284