## KPA 2 Social & IS
KPA 2 - Infrastructure & Social Services
KPA 2 - Basic Service Delivery and Infrastructure Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | R 000's |  | Baseline 2015/16 | Midyear YTD | 2016/17 3rd Quarter |  |  |  |  | Annual Target
|  |  |  | Budget | Spend |  |  | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Improved community wellbeing through accelerated service delivery | Roads and storm water | # of Kms of roads to be graded by 30 Jun 2017 | BS 89 | Oper 1 644 | 1238.5 | 1783.9 Km | 454.313 km | 350 | 445.74km | Achieved | None | None | 1300 | Inspection report
|  | Number of m2 of base and surface patches repaired by 30 Jun 2017 | BS 90 | Oper |  | 2170,91 m2 | 863.31m2 | 280 | 1274.83km | Achieved | None | None | 1200 | Inspection report
|  | Review Roads Master plan and adopted by Council by 31 March 2017 | BS 59 | Oper | 174.9 | 1 | N/A | N/A | The final documentation has been submitted to the Municipality to be presented in next EXCO meeting | Not Achieved | The final documentation has been submitted to the Municipality to be presented in next EXCO meeting | To be submiitted in the next Council meeting | 1 | Council Resolution and agenda
|  | # of Kms of gravel roads to be constructed in tar by 30 Jun 2017 | BS 48/50/52/53/54/70 | MIG 7 000 |  | 3,9 | N/A | N/A | Contractors appointed for : Rathoke Internal Streets, Phetwane Internal Road and Elandskraal Internal Streets | N/A | Project stoppages due to subcontracting and social issues regarding appointment of CLO's | Proper community engagement during project handovers | 3.9 | Completion Certificate
|  | # of kms of Storm Water to be constructed in Ext 6 by 30 Jun 2017 | BS 45 | 6000 |  | 400m | N/A | N/A | Contractor busy with construction, busy with installation of 900mm pipes. | N/A | Contractor encounting rock during excavations. | contractor to deploy more resources on site. | 1294 | Completion Certificate
|  | # of Kms of roads to be rehabilitated by 30 Jun 2017 | BS 71/84 | MIG 4 500 |  | New | N/A | N/A | Rehabilitation of Leeuwfotein Internal Streets on Practical Completion. | N/A | None | None | 1.1 | Completion Certificate
Improved community wellbeing through accelerated service delivery | Roads and storm water | Number of Km of roads to be constructed by 30 Jun 2017 (Industrial Road) | BS 57 | MIG 1 000 |  | 400m | N/A | N/A | Tender closed on the 27/03/2017, awaiting evaluation. | N/A | None | None | 250 | Completion Certificate
| Electricity | Number of high mast lights connected Morarela, Mbuzini, Mohlotsi, Matseding and Mohlalaotwane by 30 Jun 2017 | BS 17 | 60 | 0 | 11 | N/A | N/A | 7 | 7 masts connected | ESKOM slow with installation of supply points. Eskom must still install 5 points. | None | 16 | Certificate of compliance
|  | # of Quarterly reports in terms of households with access to basic levels of electricity submitted to the MM (GKPI) | New | Oper | Oper | New | 2 | 1 | 1 | Achieved | None | None | 4 | Copy of Quarterly reports and Eskom monthly report
|  | # of Energy Master & OM plan and submit to Council for adoption by 31 March 2017 | BS 22 | 500 | 0 | New | N/A | 1 master | 1 draft | Not achieved. Draft Energy Master plan | Energy Master Plan: Service provider appointed by MISA. Many corrects needed in draft. OM Plan: Waiting for Bid Adjudication | Energy Master Plan: Reported mistakes to MISA and Service provider OM Plan: Request SCM to facilitate BAC as soon as possible. | 2 | Council Resolution and agenda
|  | # high mast lights upgraded to LED fittings at Matlala Ramoshebo by 30 Jun 2017 | BS 25 | 435 | 435 | New | N/A | N/A | 30 | Achieved | None | None | 30 | Completion Certificate
Improved community wellbeing through accelerated service delivery | Electricity | % of faulty streetlights fittings maintained within 90 days | BS 07/08 | Oper | 69 | 508 | 100% | 100% | 100% | Achieved | No material in stores. SCM slow to process request | Request SCM to maintain stock levels in stores. Request SCM to arrange BAC as soon as possible | 100% | Inspection/repair reports. Monthly reports.
|  | % of faulty Mast light fittings repaired within 90 days | BS 09/10 | Oper |  | 142 | 100% | 100% | 100% | Achieved | No material in stores. SCM slow to process request | Request SCM to maintain stock levels in stores. Request SCM to arrange BAC as soon as possible | 100% | Inspection/repair reports. Monthly reports.
|  | % of households with access to basic levels of electricity by the 30 June 2017 (GKPI) | New | Oper | Oper | 97% | N/A | N/A | N/A | N/A | ESKOM completed only 21 connections to date and deferred 5 projects | Update backlog | >97% | Completion certificates provided by contracted consultants
| Project Management | % of new Capital projects started on time In terms of the appointment of consultants / contractors for EPMLM funded projects as per the Capital implementation plan | New | Oper |  | New | 100% | 100% | 70% | Not Achieved (5 contractors are appointed for construction, two consultnats are appointed for designs only.) | Procurement process for implementation of projects started late. | all appointements should be fast tracked. | 100% | Individual project appointment letters in terms of consultants / contractors
Improved community wellbeing through accelerated service delivery | Project Management | % of new Capital projects completed in terms of agreed schedule for EPMLM funded projects by Jun 30 2017 | New | Oper |  | New | 50% | N/A | 0% | Not Achieved (one project on practical completion) | Implementation of projects started late. | all appointements should be fast tracked. | 100% | Individual project certificates of completion (COC)
|  | % of Capital budget spend in terms of new IDP identified projects as per the Capital implementation plan by the 30 June 2017 (GKPI) | New | Oper |  | New | 0% | 60% | 23.7% | Not achieved | Late appointments of service providers. | all appointements should be fast tracked. | 100% | Section 72 financial report
| Roads and storm water | % spending on MIG funding by the 30 June 2017 | New | Oper |  | New | 100% | 60% | 11% | Not Achieved (All MIG appointments are made except for Ngwalemong Internal Streets that needs budget maintenance.) | Late appointments of service providers. | Appointments to be finalized for projects to be completed before June 2017. | 100% | Section 72 financial report
| SCM | % attendance at scheduled Bid Committee meetings by 30 Jun 2017 (Social & IS) | FV 07 | Oper |  | New | 100% | 100% | 100% | Achieved | Delay in terms of receiving reports from Evaluation committee. | Evaluations of bids to be expedited. | 100% | Attendance register
|  | # of quarterly reports submitted to Council in terms of compliance to the CoGHSTA Back to Basics reporting system | New | Oper |  | New | 2 | 1 | 2 | Achieved | N/A | N/A | 400% | Copy of Quarterly report submitted to CoGHSTA
| Waste removal | % of households with access to a minimum level of basic waste removal by 30 June 2017 (once per week) (GKPI) | BS 94 | Oper | Oper | 17.4% | N/A | N/A | N/A | N/A | There is currently no increase in household collection | A decision needs to be taken on the placement of containers in the identified areas as per the strategies. | >17,4%
|  | # of existing households in formal settlements provided with solid waste removal services by 30 Jun 2017 | BS 94 | Oper | Oper | 5619 per week | 5619 per week | 5619 per week | 5619 per week | Achieved | None | None | 5619 per week
| Environmental management | External audit of the Landfill to comply with National Environmental Waste Act by 30 Jun 2017 | BS 98 | 90 | 0 | 1 | N/A | N/A | N/A | N/A but Service provider appointed. Audit will take place first week in May 2017 | None | None | 1
Effective and Efficient Community Involvement |  | # of landscaping and greening project implemented by 30 Jun 2017 | BS 102 | 320 | 0 | 1 | N/A | N/A | N/A | N/A | Funds adjusted.Only purchasing of materials | Finalise specificiations for materials | 1
| Community Facilities | # of Cultural and Heritage festivals held by 30 Jun 2017 | BS 116/117 | 210 | 206 | 2 | N/A | 1 | 1 | Achieved | None | None | 2
|  | # of cemeteries fenced by 30 Jun 2017 | BS 109 | 690 | 0 | 7 | N/A | N/A | N/A | N/A but Tender closed 27/2/2017 .BEC 3 April 2017 | Procurement process not finalised yet | Appointment to be fasttrack asap | 6
|  | # of Mayor’s cup events held by 30 Jun 2017 | BS 114 | 95 | 40,7 | 1 | N/A | N/A | N/A | N/A but First cluster games finalised | Finalise final programme | Final programme to be finalised in consultation with Mayors for May 2017 | 1
|  | # of Mayors marathon events held by 31 Mar 2017 | BS 115 | 40 | 0 | New | N/A | 1 | 0 | Not achieved. | Marathon to be registered one year in advance with Limpopo Athletic Association | Registration can only take place now for next year year | 1
|  | # of Club Federations supported to promote sporting development by 30 Jun 2017 | BS 120 | 71,2 | 40 | New | 0 | 1 | 0 | Not achieved. | No programme to support Club federations | Plan to support one Federation in 4th quarter | 4
| HIV & AIDS and other diseases | # of quarterly Local Aids Council forum meetings held | BS 112 | 24.5 | 0 | 4 | 3 | 1 | 1 | Achieved | None | None | 4
|  | # of quarterly HIV /AIDS awareness campaigns | BS 113 | 40.8 | 7,2 | 4 | 1 | 1 | 0 | Not achieved. | Programme for Morarela in March was shifted to April 2017 | Morarela campaign to be finalise with a campaign for 4th quarter | 4
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 31 March 2017 (Social) | MTOD 09 | Oper |  | 3 | N/A | 3 | 0 | Not achieved. | Employee Sport Policy submitted to LLFwait for approval | Hiv /Aids policy and paupers burial policy to be submitted for comments | 3
|  | # of new / reviewed policies adopted by Council by 31 March 2017 (IS) | MTOD 10 | Oper |  | 4 | N/A | N/A |  |  |  |  | 2
| Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (SS) | GG 14/15 | Oper |  | New | 0% | 100% | 100% |  |  |  | 100%
|  | % of AG Management Letter findings resolved by 30 Jun 2017 (SS) | GG 11/12/13 | Oper |  | New | N/A | N/A | 100% |  |  |  | 100%
|  | % execution of identified risk management plan within prescribed timeframes per quarter (SS) | GG 16 | Oper |  | New | 0% | 100% | 100% |  |  |  | 100%
KPA 3: Local Economic Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | R 000's |  | Baseline 2015/16 | Midyear YTD | 2016/17 3rd Quarter |  |  |  |  | Annual Target
|  |  |  | Budget | Spend |  |  | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Grow the economy and provide livelihood support | LED | # of EPWP job opportunities provided through EPWP grant by 30 June 2017 (GKPI) | LED 03/08 | 601.2 | 590.9 | 382 | 83 | 100 | 56 | Not achived | Late appointments of on capital projects | The Municipality to procure and appoint contractors as soon as possible | 305 | Quarterly reports submitted to the Department of Public Work
KPA 4: Municipal Transformation and Institutional Development
Strategic Objective | Priority Programme | KPI | IDP Ref No | R 000's |  | Baseline 2015/16 | Midyear YTD | 2016/17 3rd Quarter |  |  |  |  | Annual Target
|  |  |  | Budget | Spend |  |  | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Build effective and efficient Organization | Institutional Development | # of new / reviewed policies adopted by Council by 31 March 2017 (IS) | MTOD 09 | Oper |  | new | N/A | N/A | 1 | Not achieved | Gaps identified in the policy | To be re-submitted to council | 2 | Council Resolution and agenda
KPA 6: Good Governance and Public Participation
Strategic Objective | Priority Programme | KPI | IDP Ref No | R 000's |  | Baseline 2015/16 | Midyear YTD | 2016/17 3rd Quarter |  |  |  |  | Annual Target
|  |  |  | Budget | Spend |  |  | Target | Actual | Achievements | Challenges | Corrective Action |  | POE
Build effective and efficient Organization | Good Governance | % of Internal Audit Findings resolved per quarter as per the Audit Plan by 30 Jun 2017 (IS) | GG 14/15 | Oper |  | New | N/A | 100% | N/A | N/A | N/A | N/A | 100% | Quarterly IA status reports
|  | % of AG Management Letter findings resolved by 30 Jun 2017 (IS) | GG 11/12/13 | Oper |  | New | N/A | 100% |  |  |  |  | 100% | Quarterly AG Action Plan report
|  | % execution of identified risk management plan within prescribed timeframes per quarter (IS) | GG 16 | Oper |  | New | N/A | 100% | I00% | Achieved | N/A | N/A | 100% | Quarterly Risk management committee reports
Note on H21: Alan Percy: based on backlog of 958 and h/h 32284
Note on J22: Alan Percy: should have been completed Midyear
Note on I25: Alan Percy: target was only 25%
Note on H28: Alan Percy: based on backlog of 26665 and h/h 32284