## Sheet1
NO. | TENDER NUMBER | DATE ADVERTISED | DATE CLOSED | PROJECT/SERVICE DESCRIPTION | DATE WHICH SHORTLIST WAS RECEIVED | DATE OF EVALUATION | DATE ADJUDICATED AND AWARDED | EVALUATED WITHIN 45 DAYS AFTER CLOSURE | ADJUDICATED WITHIN 20 DAYS AFTER EVALAUTION | ADJUDCTD WITHIN 90 DAYS OF CLOSURE | NAME OF SUCCESSFUL BIDDER | APPROVED TENDER AMOUNT | BBBEE POINTS | LOCALITY STATUS
Ephraim Mogale Local Municipality tender awarded 2013/2014 financial year.
1 | R/LP/6525/09/14 | 01\07/2013 | 19/07/2013 | upgrading of Leeuwfontein internal streets phase 2 | 19/07/2013 | 31/07/2013 | 16/09/2013 | Yes | NO | Yes | Ramatlane 's Construction | 5100000 | 8 | Bronkhorspruit
2 | 1931-08-03 | 15/08/2013 | 30/08/2013 | The Construction of Uitvlug Community Hall | 30/08/2013 | 30/08/2013 | 16/09/2013 | Yes | Yes | Yes | Mahovy 's Construction | 3040000 | 8 | Polokwane
8140000
Prepared by:- | ______________________________ |  |  | Reviewed by:- | ______________________________
| Ms P Malesoene ( Acquisition Officer) |  |  |  | Mr T Chitauro (Resident Accountant)
Signed Off:- | ______________________________ |  |  | Approved for Publishing:- | ______________________________
| Mr R Mohaudi (Acting CFO) |  |  |  | Mr P J Phahlamohlaka (Acting MM)